## Pricing Schedule
Balfour Beatty
DRET Primary School
Carpentry Package
Pricing Schedule
Ref: | Description | Quantity | Unit | Rate | Total
Commercial
1 | 5% Retention, 50% released at Practical Completion, the remainer 12 months threafter at the end of the rectification period. |  |  |  | Included
2 | Monthly valuations at months end, with a 35 day payment period. |  |  |  | Included
3 | Off site payments will not be made, without an agreed vesting certificate |  |  |  | Included
4 | The price is a design, manufacture, supply and fix, Lump-Sum contract, based on the specifications, drawings and all other documentation attached. This price is to be fixed and firm to 30th September 2017. |  |  |  | Included
5 | Collateral warranties will be be required; with an agreed wording in favour of any party as the authority may direct. |  |  |  | Included
6 | Product warranties will be required for all supplied products |  |  |  | Included
7 | A bond from your bank will be required |  |  |  | Included
8 | Daywork Rate for normal working hours |  | hr |  | Rate Only
9 | Daywork Rate for normal working hours (labourer) |  | hr |  | Rate Only
10 | Daywork rate % uplift for weekend working, Saturday |  | % |  | Rate Only
11 | Daywork rate % uplift for weekend working, Sunday |  | % |  | Rate Only
12 | Material % uplift |  | % |  | Rate Only
13 | Plant % uplift |  | % |  | Rate Only
Construction
14 | Your price is to include for working Monday to Friday 7:30am to 5:30pm; with Saturday mornings 9am to 1pm by prior agreement with Balfour Beatty. |  |  |  | Included
15 | The current programme (Rev 23/05/16) shows the following work that is to be carried out. |  |  |  | Included
16 | Practical Completion is set for 28/09/17 and the sub-contractor must make best endeavors to ensure this date is met. |  |  |  | Included
17 | Deliveries must be coordinated with Balfour Beatty and other trades. All deliveries must be booked in with Balfour Beatty Management with 48 hours notice. |  |  |  | Included
18 | Unloading and distribution of all goods by the sub-contractor. Hoist will be available from 14th November 2016. BB will be in control of this hoist. |  |  |  | Included
19 | If the Subcontractor wishes to work on Saturdays, the cost of the hoist driver and Balfour Beatty supervisors costs will be deducted from your Account. |  |  |  | Included
20 | All small plant by the Subcontractor. All to be certified to the necessary standards. |  |  |  | Included
21 | The sub-contractor to stipulate what storage / office space they require, but must provide their own cabin/containers. |  |  |  | Included
22 | There is no on site security protection with the exception of the hoarding and padlocked gates. All Plant and materials are the risk of the Subcontractor and are left on site at the owners risk. |  |  |  | Included
23 | The sub-contractor is responsible for protection of materials until handed over and signed for by Balfour Beatty. Any damaged sustained prior to handover, however cuased is your responsibility. |  |  |  | Included
24 | All materials must be offered clean for inspection by Balfour Beatty Site Management, dirty materials where damage can not be accertained will not be accepted. |  |  |  | Included
Health & Safety
25 | Buy in to Balfour Beatty Zero Harm Innovative |  |  |  | Included
26 | All staff to have a valid CSCS card which must be produced at induction |  |  |  | Included
27 | Supervisors to have relevant health and safety qualifications - 5 day SMSTS/SSSTS qualification. |  |  |  | Included
28 | All staff will have a daily briefing, from their Supervisor before starting work and sign to that effect. |  |  |  | Included
29 | All staff must sign a daily 'fit for work' declaration, prior to starting work each morning. |  |  |  | Included
30 | All on site operatives must undergo health surveillance in accordance with the Balfour Beatty Health and Safety Policy |  |  |  | Included
31 | Safe methods of work to be discussed on site and signed off by Balfour Beatty site management as the best practice. |  |  |  | Included
32 | Arrange for fortnightly NEBOSH qualified Health and Safety advisor visits to site and produce reports, hold toolbox talks and training with operatives. |  |  |  | Included
33 | You will need to provide trained first aiders and trained fire marshalls amongst your operatives at a rate of 1:10 (with 1nr of each as a minimum if less than 10nr operatives). |  |  |  | Included
34 | All work must be in accordance with agreed risk assessments and method statements, incorporating the Balfour Beatty Health and Safety Document (7.11). |  |  |  | Included
Design
35 | The main contract is design and build and the sub-contract will be let on a D&B Contractors Framework 2013 step down contract. |  |  |  | Included
36 | This is a full sub-contractor design package. |  |  |  | Included
37 | Your price includes for developing the design from the current drawings, to completion in accordance with the Contractors Proposals; with any resultant costs from design development included within the contract sum. |  |  |  | Included
38 | Your design must be fully compliant with the Contractors Proposals, without deregation, unless given with written agreement from Balfour Beatty. |  |  |  | Included
39 | Complying with the acoustic requirements, as set out in the Contractors Proposals have been included within your price and your design includes for ensuring that your finished rooms pass the acoustic tests. |  |  |  | Included
40 | Your price allows for ensuring that your design is in accordance with the fire strategy, as set out in the Contractors Proposals. |  |  |  | Included
41 | Your price allows for ensuring the thermal insulation requrements are met, as set out in the Contractors Proposals. |  |  |  | Included
| Prelims |  |  |  | 0
0
45 | The basic prelim requirement is set out below. The list is not exhaustive, so you must include sufficient prelims to deliver the project in accordance with the Balfour Beatty requirements |  |  |  | 0
0
46 | Refer to the Programme, in which includes the requirements your prelims are based on. | 1 | item |  | Included
47 | Setting Out Engineer - (setting out from main datums provided by Balfour Beatty) | 1 | item |  | Included
48 | Non working Project Manager - full time with SMSTS and trade specific CSCS Card | 1 | item |  | Included
49 | Foreman / supervisor - full time with SSSTS & trade specific CSCS Card | 1 | item |  | Included
50 | Operatives - trade specific CSCS card | 1 | item |  | Included
51 | Labourers for cleaning & unloading - with trade specific CSCS cards | 1 | item |  | Included
56 | Balfour Beatty to provide skips for general waste. You are responsible for keeping your working area clear at all times and must clear rubbish to skips as soon as possible - this is not 24 hours, it could be immediatley depending on the safety risk posed. | 1 | item |  | Included
57 | You are to provide your own storage and office set up | 1 | item |  | Included
58 | PPE | 1 | item |  | Included
59 | All access equipement is to be your responsibility | 1 | item |  | Included
60 | Task Lighting | 1 | item |  | Included
61 | O&M Manual | 1 | item |  | Included
62 | Health and safety visits; fortnightly minimum. | 1 | item |  | Included
63 | A sample of each window type will be used as the benchmark of quality expected by the client. | 1 | item |  | Included
Measured Works
Timber Roof (3rd Floor Future Proof) - As per DSP-TER-00-ZZ-DG-S-311010 GA, DSP-TER-00-ZZ-DG-S-111010 GA
| Joists over future stair and lift shaft - Joists notched into web of UC's with Nailed packers between to prevent lateral movement. | 1 | Item | Included | Included
| Joists to sit on 60m deep timber packs on the bottom flange of UC's. | 1 | Item | Included | Included
| Grid Line A joists sit on angle welded face of RHS edge beam with packers between joists | 1 | Item | Included | Included
| 200x50mm Timber joistrs @ 300mm C/C with 22mm Plywood decking to be nailed to joists, Left ready for hot melt roof application | 53 | m² | 0 | 0
Access Hatches - Installation Only
To form 200x50mm Timber joist opening void for access hatch to be installed - Joists to be supported on nailed multijoists with nailed BAT speedy hangers.
| Fix Access hatches (fold down ladders) - 1200x1200mm hatch | 1 | Nr | 0 | 0
Internal Doors
All items on this schedule must be priced in conjunction with the drawings and specifications contained within the enquiry documents to ensure you capture all specific labours, materials or services required within the items general description.
| Where obtainable, they should be certified by the Forest Stewardship Council (FSC). If not obtainable with FSC certification, they should be certified under the programme for Endorsement of Forest Certification (PEFC) | 1 | item |  | Included
| Doorsets and Ironmongery to be supplied by others, but your price is to include for the call off, offload, material check and distribution from the delivery lane on Goldhawk Road to the workface. | 1 | item |  | Included
| Door Sets; frames and doors to be supplied as a unit (except pairs of doors, which will be delivered flat packed) ; hinges & intumescent seals factory fitted ; Stop is pinned to the frame, which will require permanant fixing once the door is in position. | 1 | Item |  | Included
| Locks are to be suited ; with sub-master and master keys provided. All keys to be provided to Balfour Beatty upon sign off, correctly labelled. Allowance to unload and distribute Ironmongery. | 1 | item |  | Included
Doors are Factory finished doors. Frames to be decorated.
Refer to attached Internal door schedule for full door details
Door Type
| Door Type A1 - 1010x2100 | 6 | nr | incl | incl
| Door Type A2 - 1010x2100 | 12 | nr | incl | incl
| Door Type A3 - 810x2100 | 4 | nr | incl | incl
| Door Type A4 - 1010x2100 | 1 | nr | incl | incl
| Door Type B1 - 1500x2100 | 16 | nr | incl | incl
| Door Type B2 - 2400x2100 | 2 | nr | incl | incl
| Door Type C1 - 1800x2700 | 4 | nr | incl | incl
| Door Type C2 - 1800x2100 | 1 | nr | incl | incl
| Door Type C3 - 1500x2100 | 2 | nr | incl | incl
| Door Type C4 - 1800x2100 | 6 | nr | incl | incl
| Door Type C5 - 1800x2100 | 2 | nr | incl | incl
| Door Type C6 - 2650x2700 | 1 | nr | incl | incl
| Door Type D1 - 1500X2700 | 2 | nr | incl | incl
| Door Type D2 - 1500x2100 | 2 | nr | incl | incl
| Door Type D3 - 1500x2100 | 1 | nr | incl | incl
| Distribution and installation of above listed doorset; to include all fixtures and fittings. Installed in accordance with spec 25-50-20/120 Internal doorset system. | 1 | Sum | 0 | 0
| Distribution and installation of ironmongery,Access Controls, Mag locks &Hold open devices listed within doorsets; to include all fixtures and fittings. Installed in accordance with spec DSP-PPA-00-XX-DR-92500 Rev C02. | 1 | Sum | 0 | 0
| Distribution and installation of Internal Screens listed within Internal Screens schedule; to include all fixtures and fittings. Installed in accordance with spec 25-50-95/140 | 1 | Sum | 0 | 0
| Lock cut outs for doors (if not pre-cut by the door supplier) | 62 | nr | 0 | Rate Only
| Allowance for packers & fixings | 1 | item | 0 | Included
| Intumescent mastic to door frames & Screens; measured to both sides of partition | 750 | m | 0 | 0
| Fix protection to corridor face of doors (Corex of similar). (Cost per single door) | 62 | Nr | 0 | 0
| Fix Only 50mm x 19mm MDF architrave (pre-primed) to doors & Internal Screens | 750 | m | 0 | 0
| E/O for providing softwood architrave in lieu of MDF | 750 | m | 0 | Rate Only
Skirting
| Supply and fix 100mmx19mm pencil round MDF skirting ; fixed to plasterboard partitions. To be delivered pre-primed. | 1132 | m | 0 | 0
| Supply and fix 100mmx19mm pencil round MDF Stair Stringer Skirting skirting ; fixed to plasterboard partitions. To be delivered pre-primed. | 26 | m | 0 | 0
Window Boards
| Supply and fix moisture resistant 19mm thick MDF window board, cut to width and routered bullnose. Rate to include for packing line and level. | 71 | m | 0 | 0
| MDF Lining to top of plasterboard partition to staircase as per drawing DPS-PPA-00-XX-DR-A-30702 - Stair Section & DPS-PPA-00-XX-DR-A-30704 - Stair Section 19mm MDF 150mm Wide | 10 | m | 0 | 0
| MDF Lining to top of plasterboard partition to staircase as per drawing DPS-PPA-00-XX-DR-A-30701 - Stair Plan & DPS-PPA-00-XX-DR-A-30703 - Stair Plan 19mm MDF 350mm Wide | 5 | m | 0 | 0
Bathrooms
| Supply and install Mirrors 1600mm(L)x500mm(W); screw fixed Class C Safety Glass to BS6206 Aluminium Backing Foil Polished Edges | 13 | nr | 0 | 0
| Supply & Install Doc M Shower room pack Manufacturer: Armitage Shanks WRAS Approved RAL: TBC | 4 | Nr | 0 | 0
| Temporary Fire doorset to be supplied and fitted on each staircase lobby area and hoist rooms ; with perspex vision panel 500x500 ; door n/e area of 3m² ; rim nightlatch ; hinges, overhead door closer, push plate, pull handle etc. (Prov Qaunt) | 6 | nr | 0 | 0
| Wall and ceiling patresses 600x600 ply to allow for light,detectors, fixtures, fitting to be installed through plasterboard. To be fixed behind platerboard to steel frame stud/celing grid support. . (Prov Qaunt) | 150 | nr | 0 | 0
| Wall and ceiling patresses 1200x600 ply to allow for light,detectors, fixtures, fitting to be installed through plasterboard. To be fixed behind platerboard to steel frame stud/celing grid support. (Prov Qaunt) | 150 | nr | 0 | 0
| Polycarbonate Roof to canopy areas to be mechaically fixed to steel sections (Rodeca Multi walls sheets) - Prov Sum | 76 | m² | 0 | 0
Prelims - for Carpentry
The basic prelim requirement is set out below. The list is not exhaustive, so you must include sufficient prelims to deliver the project based on the information provided in the enquiry.
Refer to Document 10 for the Programme, but the basic sequence is stated below:
The below dates and durations are based on calandar weeks and not working weeks and therefore do not take into account Chrismas shutdown and bank holidays.
We will be working up the details on programme with the sub-contractor, to finalise the exact sequence / programme / and numbers of operatives required
Assume start in 5th December 2016, complete 10th November 2017
| Provisional Duration on Site - To be adjusted accordingly | 12 | wks | 0 | 0
| Access and Scaffold - up to and including 4.0m high | 1 | item |  | Included
Prelims Total
235 | Sub-Total |  |  |  | 0
236 | Discount |  |  |  | 0
237 | Total |  |  |  | 0
0

## Internal Door Schedule & Screen
ID | Location | Door Type | Ironmongery | Width | Height | Area | Operation Type | Door Installation Cost £ | Ironmongery Installation Cost £
D0-02-01 | Access WC | D TypeA2 | Set 01 | 1010 | 2100 | 2.121 |  | 0 | 0
D0-03-01 | Interview Room | D TypeA1 | Set 04 | 1010 | 2100 | 2.121 |  | 0 | 0
D0-04-01 | Head Teacher's Office | D TypeA1 | Set 04 | 1010 | 2100 | 2.121 |  | 0 | 0
D0-06-01 | Hygiene | D TypeA2 | Set 01 | 1010 | 2100 | 2.121 |  | 0 | 0
D0-07-01 | Central Stock | D TypeA3 | Set 06/FR | 810 | 2100 | 1.701 |  | 0 | 0
D0-08-01 | Circulation | D TypeC4 | Set 09 | 1800 | 2100 | 3.78 | Hold Open | 0 | 0
D0-09-01 | Cleaners | D TypeA2 | Set 06/FR | 1010 | 2100 | 2.121 |  | 0 | 0
D0-12-01 | Circulation | D TypeC4 | Set 08 | 1800 | 2100 | 3.78 | Access Control - Hold Open | 0 | 0
D0-14-01 | Reception classroom | D TypeB1 | Set 01/FR | 1500 | 2100 | 3.15 |  | 0 | 0
D0-14-02 | Reception classroom | Moving Wall Type B | as supplied |  |  |  |  | 0 | 0
D0-15-01 | Reception classroom | D TypeA1 | Set 01/FR | 1010 | 2100 | 2.121 |  | 0 | 0
D0-17-01 | Infant classroom | D TypeB1 | Set 01/FR | 1500 | 2100 | 3.15 |  | 0 | 0
D0-20-01 | Infant classroom | D TypeB1 | Set 01/FR | 1500 | 2100 | 3.15 |  | 0 | 0
D0-21-01 | General Office | Roller Shutter Type B | as supplied |  |  |  |  | 0 | 0
D0-22-01 | Entrance | D TypeC6 | Set 08 | 2650 | 2700 | 7.155 | Access Control | 0 | 0
D0-23-01 | Small Hall | D TypeC2 | Set 03 | 1800 | 2100 | 3.78 |  | 0 | 0
D0-23-02 | Small Hall | D TypeD3 | Set 10 | 1500 | 2100 | 3.15 |  | 0 | 0
D0-24-01 | Main Hall | D TypeD1 | Set 03 | 1500 | 2700 | 4.05 | Hold Open | 0 | 0
D0-24-02 | Main Hall | Moving Wall Type A | as supplied |  |  |  |  | 0 | 0
D0-25-01 | Multi Store | D TypeC5 | Set 05/FR | 1800 | 2100 | 3.78 |  | 0 | 0
D0-28-01 | Kitchen | Roller Shutter Type A | as supplied |  |  |  |  | 0 | 0
D0-28-02 | Kitchen | D TypeA1 | Set 01/FR | 1010 | 2100 | 2.121 |  | 0 | 0
D0-28-03 | Kitchen | D TypeA2 | Set 01 | 1010 | 2100 | 2.121 |  | 0 | 0
D0-28-04 | Kitchen | D TypeA3 | Set 06 | 810 | 2100 | 1.701 |  | 0 | 0
D0-28-05 | Kitchen | D TypeA3 | Set 06 | 810 | 2100 | 1.701 |  | 0 | 0
D0-32-01 | Circulation | D TypeD2 | Set 09/FR | 1500 | 2100 | 3.15 | Hold Open | 0 | 0
D0-32-02 | Circulation | D TypeC4 | Set 08/FR | 1800 | 2100 | 3.78 | Access Control - Hold Open | 0 | 0
D0-34-01 | Junior classroom | D TypeB1 | Set 01/FR | 1500 | 2100 | 3.15 |  | 0 | 0
D0-37-01 | Junior classroom | D TypeB1 | Set 01/FR | 1500 | 2100 | 3.15 |  | 0 | 0
D0-38-01 | Group room | D TypeB2 | Set 01/FR | 2400 | 2100 | 5.04 |  | 0 | 0
D0-39-01 | Junior classroom | D TypeB1 | Set 01/FR | 1500 | 2100 | 3.15 |  | 0 | 0
D0-42-01 | Junior classroom | D TypeB1 | Set 01/FR | 1500 | 2100 | 3.15 |  | 0 | 0
D0-43-01 | Maintenance Store | D TypeA3 | Set 06/FR | 810 | 2100 | 1.701 |  | 0 | 0
D0-45-01 | Store / Future lift | D TypeA2 | Set 01/FR | 1010 | 2100 | 2.121 |  | 0 | 0
D0-47-01 | Circulation | D TypeD1 | Set 03/FR | 1500 | 2700 | 4.05 | Access Control - Hold Open | 0 | 0
D0-48-01 | Lobby | D TypeD2 | Set 09/FR | 1500 | 2100 | 3.15 | Hold Open | 0 | 0
DS0-01-01 | Stair | D TypeC1 | Set 08/FR | 1800 | 2100 | 3.78 | Access Control - Hold Open | 0 | 0
First Floor
D1-01-01 | Circulation | D TypeC1 | Set 03 | 1800 | 2700 | 4.86 | Hold Open | 0 | 0
D1-02-01 | Science / FT | D TypeB1 | Set 01/FR | 1500 | 2100 | 3.15 |  | 0 | 0
D1-03-01 | MI / Therapy Room | D TypeA2 | Set 01 | 1010 | 2100 | 2.121 |  | 0 | 0
D1-04-01 | Circulation | D TypeC4 | Set 09/FR | 1800 | 2100 | 3.78 | Hold Open | 0 | 0
D1-05-01 | Access WC | D TypeA2 | Set 01 | 1010 | 2100 | 2.121 |  | 0 | 0
D1-08-01 | Cleaners | D TypeA2 | Set 06/FR | 1010 | 2100 | 2.121 |  | 0 | 0
D1-09-01 | Infant classroom | D TypeB1 | Set 01/FR | 1500 | 2100 | 3.15 |  | 0 | 0
D1-12-01 | Infant classroom | D TypeB1 | Set 01/FR | 1500 | 2100 | 3.15 |  | 0 | 0
D1-13-01 | SEN Resource base | D TypeA1 | Set 01/FR | 1010 | 2100 | 2.121 |  | 0 | 0
D1-14-01 | Group room | D TypeA1 | Set 01/FR | 1010 | 2100 | 2.121 |  | 0 | 0
D1-15-01 | Specialist Store | D TypeA2 | Set 06/FR | 1010 | 2100 | 2.121 |  | 0 | 0
D1-16-01 | Staff Room | D TypeB1 | Set 04 | 1500 | 2100 | 3.15 |  | 0 | 0
D1-17-01 | Plant | D TypeC5 | Set 07/FR | 1800 | 2100 | 3.78 |  | 0 | 0
D1-20-01 | Store | D TypeA2 | Set 01/FR | 1010 | 2100 | 2.121 |  | 0 | 0
D1-21-01 | Circulation | D TypeC4 | Set 08/FR | 1800 | 2100 | 3.78 | Access Control - Hold Open | 0 | 0
D1-21-02 | Circulation | D TypeC4 | Set 08/FR | 1800 | 2100 | 3.78 | Access Control - Hold Open | 0 | 0
D1-22-01 | Access WC | D TypeA2 | Set 01 | 1010 | 2100 | 2.121 |  | 0 | 0
D1-23-01 | Server Room | D TypeC3 | Set 07/FR | 1500 | 2100 | 3.15 |  | 0 | 0
D1-24-01 | Junior classroom | D TypeB1 | Set 01/FR | 1500 | 2100 | 3.15 |  | 0 | 0
D1-27-01 | Junior classroom | D TypeB1 | Set 01/FR | 1500 | 2100 | 3.15 |  | 0 | 0
D1-28-01 | Group room | D TypeB2 | Set 01/FR | 2400 | 2100 | 5.04 |  | 0 | 0
D1-29-01 | Junior classroom | D TypeB1 | Set 01/FR | 1500 | 2100 | 3.15 |  | 0 | 0
D1-33-01 | Junior classroom | D TypeB1 | Set 01/FR | 1500 | 2100 | 3.15 |  | 0 | 0
D1-34-01 | Specialist Store | D TypeA2 | Set 06 | 1010 | 2100 | 2.121 |  | 0 | 0
D1-35-01 | Repro / Future lift | D TypeB1 | Set 04/FR | 1500 | 2100 | 3.15 |  | 0 | 0
D1-37-01 | Circulation | D TypeC1 | Set 03/FR | 1800 | 2700 | 4.86 | Hold Open | 0 | 0
D1-39-01 | Cupboard | D TypeA4 | Set 10 | 1010 | 2100 | 2.121 |  | 0 | 0
DR1-01-01 | Riser 01 | D TypeC3 | Set 10/FR | 1500 | 2100 | 3.15 |  | 0 | 0
DS1-01-01 | Stair | D TypeC1 | Set 09/FR | 1800 | 2700 | 4.86 | Hold Open | 0 | 0
|  |  |  | 87.78 | 133.8 |  |  | 0 | 0
Internal Screens
Screen Installation £
S0-22 | Entrance | S Type01 |  | 1500 | 1340 | 2.01 |  | 0
S1-01-01 | Circulation | S Type02 |  | 1500 | 1500 | 2.25 |  | 0
S1-01-02 | Circulation | S Type02 |  | 1500 | 1500 | 2.25 |  | 0
S1-13-01 | SEN Resource Base | S Type02 |  | 1500 | 1500 | 2.25 |  | 0
S1-16-01 | Staff Room | S Type02 |  | 1500 | 1500 | 2.25 |  | 0
SS1-01-01 | Stair | S Type02 |  | 1500 | 1500 | 2.25 |  | 0
SS1-01-02 | Stair | S Type02 |  | 1500 | 1500 | 2.25 |  | 0
0