## Sheet1
RAPHAEL CONTRACTING LIMITED
PRELIMS BREAKDOWN
CONTRACT: | Dixon House
PROGRAMME - | START: | 23.08.16
| FINISH: | 18.04.17
| DURATION: | 33.5 wks
AVG 3 MEN PLUS SUBCONTRACTORS
M.O'B: | [9 empty] | -
SUPERVISOR- PRE-TENDER: |  |  | 4 | wks | @ | 1650 | X | 100% | = | 6600
NON WORKING: |  |  | 34 | wks | @ | 1650 | X | 40% | = | 22440
FOREMAN- PRE-TENDER: |  |  |  | wks | @ | 1375 | X | 0% | = | 0
NON WORKING: |  |  | 34 | wks | @ | 1375 | X | 100% | = | 46750
ENHANCEMENT: |  |  |  | wks | @ | 655 | X | 0% | = | 0
UNLOAD & DISTRIBUTE/ CLEAN & CLEAR | [9 empty] | 5000
OFFICE/TELEPHONE/COPYING: | [9 empty] | 3500
PLANT: | [9 empty] | 2000
INCREASED COSTS: | LABOUR | [7 empty] | }
[9 empty] | } | Separate
| MATERIALS | [7 empty] | }
RUBBISH REMOVAL | [9 empty] | 0
PROTECTION/RISK/FRENCH POLISHER: | [9 empty] | 10000
HEALTH & SAFETY | [9 empty] | 4000
100290
OH & P | [5 empty] | 10% |  |  |  | 10029
110319
Discount
110319
CONTINGENCY
[6 empty] | TOTAL |  |  |  | 110319