Amwell

Thundridge Business Park

Cambridge Road

Thundridge

Herts

SG12 0SU								    03 January 2008

Dear Sirs,

# Re: 20 Gresham Street

We enclose herewith our Order No. 21110 for the supply and fix of toilet cubicles and duct/wall panelling at the above.  This order is based upon your quotation C40418r4 which is not fully compliant with the architects current scheme (please refer to item m) of the attached order for further details).  It is a condition of this order that you provide a fully compliant bid, for agreement between both parties, by 18.01.08.

Please refer to section j) of this order for your health and safety obligations, in addition please forward all relevant COSHH information, method statements and risk assessments to site, for the attention of Mr Mick O’Regan, before you commence work.

Please refer to section l (ii) of this order for details of the sub-sub-contractor warranty that is required for this project.

Please forward copies of your current tax and insurance details to our Chessington office for the attention of our Mr P Bennett.

We trust this is self-explanatory but, should you have any queries, please contact the undersigned.

Yours faithfully,

## S C Thorpe

Enc.

cc:	R C Hayhoe

M O’Brien

M O’Regan

D Singh

Amwell

Thundridge Business Park

Cambridge Road

Thundridge

Herts

SG12 0SU						                            03 January 2008

ORDER NO. 21110

# Re: 20 Gresham Street

To supply and fix toilet cubicles and duct/wall panelling at the above in accordance with the documentation listed below (copies of which are attached):

- RCL’s invitation to tender dated  06.11.06 and enclosures detailed therein

- Your quotation ref  C40418r4 dated 06.12.07 amended in accordance with item 3 below (amendments in red)

- David Martin’s email 12.12.07, 11:00

For a sum of £326,645.00 + a contingency of £6,500.00 = £331,145.00  TOTAL

Please note the following:

- Your price is fixed for the duration of the works

- Delivery charges are included

- Discount: 2 ½ %

d)	Retention will be held at 5%. One half will be released at practical completion and the balance at the end of the defects liability period

e)	Dayworks will only be used as the basis for valuing variations where agreed rates/sums are not applicable and they cannot be accurately pro-rata’d. In these instances sheets must be offered for signature within 7 days of the works being carried out

f)	Programme:  Drawings by 18.01.08

Installation in accordance with RCL’s Programmes, Core Fit Out typical Rev 	1 dated 06.12.07 and Core Fit Out Overall Rev 1 dated 06.12.07, all as 	attached

g)	Attendances are to be as the attached schedule.  Please note that you will be 	required to carry out site surveys and that all	dimensions taken are your 	responsibility

h)	Requests for Information must be in writing and should be addressed to our

Project Manager.  You will be required to attend package review meetings on 	a regular, at least monthly, basis.

i)	Should any terms or conditions within your quotation contradict the terms of this order, this order will take precedence

j)	Works are to be undertaken fully in accordance with all relevant Health & Safety Regulations including the provision of all necessary PPE for our operatives.  It is a condition of this order that our Health & Safety questionnaire, a copy of which should already be in your possession,  is completed to the satisfaction of our Director in charge of safety, Martin O’Brien

k)	All labour is to be employed fully in accordance with Government employment legislation and with 100% CSCS membership

l)	You are to provide the following by return:

- O & M manual data

- Completed Sub-Sub-Contractor Warranty (as attached)

Please note that your final payment will not be released until we are in receipt of these

m)	Our Project Manager will issue, under cover of an addendum order, a full set of current information. Your quotation C40418r4 will need to be updated in accordance with these drawings to include, for example, additional glass panels and a developed design for the privacy dividers.  Drawings, for approval, are to be based upon this information, not that previously issued by ourselves.

n)	The Project address is:

Raphael Contracting Ltd

c/o Skanska

20 Gresham Street

London

EC2V

Project Manager	Mr Mick O’Regan

Mobile No.		07973 675110

Email			mick@raphaelltd.co.uk