## Sheet1
RAPHAEL CONTRACTING LIMITED
SCHEDULE OF ATTENDANCES
SUBCONTRACTOR : WORKING ENVIRONMENTS
CONTRACT : COLUMBUS SCHOOL
|  |  | a | = Attendance Provided by
No |  |  | ITEM | M/C | RCL | S/C
1 | Facilities
| 1.1 |  | Statutory Health & Welfare Facilities | a
| 1.2 |  | Office / Storage
|  | (i) | Space for | a
|  | (ii) | Provision of, including power |  |  | a
2 | Services
| 2.1 |  | Water
|  | (i) | Supply of water / standpipes | a
|  | (ii) | Supply of hoses / barrels etc | a
| 2.2 |  | Lighting & Power
|  | (i) | Power Supply | a
|  | (ii) | Leads from distribution boxes |  |  | a
|  | (iii) | General / safety lighting | a
|  | (iv) | Task lighting |  |  | a
3 | Setting out
|  | (i) | Main grid lines & datum's on each floor | a
|  | (ii) | Detailed setting out |  |  | a
|  | (iii) | Site Dimensions |  |  | a
4 | Unloading and Distribution
|  | (i) | Tower crane including driver |  | N/A
|  | (ii) | Hoist including operator |  | N/A
|  | (iii) | Forklift including driver |  | N/A
|  | (iv) | Banksman / Loader |  | N/A
|  | (v) | Labour for unloading |  |  | a
|  | (vi) | Labour for distribution |  |  | a
5 | Scaffolding
|  | (i) | Main standing scaffold | a
|  | (ii) | Task scaffolding |  |  | a
6 | Sub face /protection /handover
|  | (i) | Checking & acceptance of sub-face |  |  | a
|  | (ii) | Handing over of areas upon completion |  |  | a
|  | (iii) | Adequately protecting after handover |  |  | a
|  | (iv) | Removing protection |  | a
7 | Rubbish
|  | (i) | Clearing to skip |  |  | a
|  | (ii) | Provision of skip | a
M/C = Main Contractor, RCL = Raphael Contracting, S/C = Subcontractor