| sFACSIMILE COVER SHEET |  | Please quote our 'E' No. on all correspondence |
| --- | --- | --- |

| FAX NO.: |  | 020 8391 2220 |  |  |
| --- | --- | --- | --- | --- |
| NAME: |  | M. O’ REGAN |  |  |
| COMPANY: |  | RAPHAEL CONTRACTING LTD |  |  |
| DATE: |  | 2 FEBRUARY 2007 |  |  |
| NO. OF SHEETS: |  | 6 |  |  |
| OUR REF: |  | E23271 |  |  |
| YOUR REF: |  |  |  |  |
| FROM: |  | RUSSELL GROVE |  |  |

| TELEPHONE NO.: |  | 0121 706 6363 |  | FAX NO.: |  | 0121 708 2250 |
| --- | --- | --- | --- | --- | --- | --- |

PROJECT:  THE BECKENHAM CENTRE

Further to your e-mail dated 1 February 2007 we quote as follows:

To supply & install 12 no “FIRECEL” up to FR120 fire rated and/or “SOUNDCEL” up to RW26 acoustic rated steel doorsets generally as per the enclosed specification but subject to the following technical notes.

##### TECHNICAL NOTES

- We allow for frames up to 147mm in total width as schematically indicated on the drawings provided. We note that the data provided does not identify wall widths door by door.

- All hardware other than hinges and manual flushbolts (double doors) is currently excluded from this quotation.  We would require a full set of hardware schedules and samples at time of order placement to facilitate drawing and subsequent manufacture.

- Any free issue hardware would need to be provided to Fitzpatrick prior to the doors being manufactured and in clearly marked/separately packaged doorset kits.

- Fitzpatrick Doors Ltd reserves the right to review all pricing and specifications contained within and comprising this quotation, upon receipt of any additional information

E23271

RAPHAEL

THE BECKENHAM CENTRE

2 FEBRUARY 2007

PRICING

1 no double doorset, 	ref D00-020, 1400mm w x 2500mm h	£   784.00

1 no single doorset,	 ref D00-024, 1025mm w x 2500mm h	£   719.00

1 no double doorset,	 ref D00-042, 1360mm w x 2500mm h	£   784.00

1 no double doorset, 	ref D00-045, 1360mm w x 2500mm h	£   784.00

1 no double doorset, 	ref D00-201, 1360mm w x 2500mm h	£   784.00

1 no double doorset, 	ref D00-242, 1745mm w x 2275mm h	£   784.00

1 no double doorset, 	ref D00-248, 1490mm w x 2275mm h	£1,132.00

1 no single doorset, 	ref D00-283, 1025mm w x 2100mm h	£   594.00

1 no single doorset, 	ref D00-284, 1025mm w x 2100mm h	£   594.00

1 no single doorset, 	ref D00-285, 1025mm w x 2100mm h	£   594.00

1 no double doorset, 	ref D00-286, 1810mm w x 2100mm h	£   581.00

1 no double doorset, 	ref D00-287, 1810mm w x 2100mm h	£   977.00

Sub total for 12 no doorsets ex works			£9,111.00

Delivery to Bromley in a maximum of 2

consignments		  				£   280.00

Survey and/or installation package 			£2,490.00

Total contract value supplied and installed:  	£11,881.00 (excluding VAT)

SIZING

The above quotation is based on structural opening sizes.

##### PRICES

# All prices are quoted in pounds sterling, are valid for the total quantities quoted only and are nett to

Raphael Contracting Ltd.

PROGRAMME

Survey

Can be undertaken within 5 working days of our receipt of a written instruction to proceed.

E23271

RAPHAEL

THE BECKENHAM CENTRE

2 FEBRUARY 2007

General Arrangement Drawings

We currently anticipate providing general arrangement drawings within 7 working days from receipt of official order and/or surveyed details and/or hardware samples and schedules.

Materials

Our current manufacturing period is 4-5 working weeks and is based on the materials being approved exactly as currently specified/quantified and runs from our receipt of full and final approved details and drawings and/or hardware schedules/samples.

# Installation

To commence as soon as doors are available ex-works to suit an agreed site programme.

This outline programme is however only a guide for your programming purposes and must be reconfirmed at time or order placement.

##### INSTALLATION

We include for up to two site survey visits, for site installation (during normal office hours), including manual off loading and site handling, site drilling and if required, mobile scaffold system/power for hand tools, fitting of hardware specified in the offer below, for protecting doors with Correx or equivalent following installation and for Contract Management support provided from our office in Birmingham.

Our installation price is based on the assumptions that:

A]	the openings are clean and plumb

B]	that we can have clear and uninterrupted access to the openings at all times.

C]	that the structure will accept our fixings without cracking or distortion.

D]	that the installation can be carried out during no more than four uninterrupted

visits to site.

E]	that Fitzpatrick fitting teams will be fully CSCS qualified.

F]	that Fitzpatrick will provide a full package of Health & Safety, Risk Assessment & Method Statement documentation.

E23271

RAPHAEL

THE BECKENHAM CENTRE

2 FEBRUARY 2007

Our installation price excludes:

A]	any electrical wiring, cabling or contact work that may be necessary

B]	any mastic and sealant

C]	any site storage of doors prior to installation

D]	mechanical offloading and site handling

E]	permanent site supervisory staff

F]	fitting of any signage or wall/floor mounted hardware

G]	removal and/or disposal of existing doors

##### VALIDITY

Offer valid only for total quantity quoted, for acceptance by 30 March 2007 and for delivery by

30 May 2007.

# INSTALLATION

If installation is included within this quotation, it is offered subject to sight of and our written agreement to any sub-contract clauses that may be applied.

- PERFORMANCE BONDS

Not included for in our quotation. Should you require a bond, we reserve the right to adjust our quotation accordingly.

- CONTRACTUAL LIABILITIES, RETENTIONS, L.D’S, ETC

Not included for in our quotation. Should you require these to be included we reserve the right to adjust or cancel our quotation accordingly.

- DESIGN DETAILS

Quotation submitted on basis of subject to Fitzpatrick sight of original copies of full contract drawings, specifications and design details. All doorsets offered are to Fitzpatrick design/specification.

E23271

RAPHAEL

THE BECKENHAM CENTRE

2 FEBRUARY 2007

- QUANTITIES/SIZES

Based on total quantities and sizes detailed in your enquiry, revisions to quantities or sizes may necessitate a re quote.

- TERMS & CONDITIONS

Offer made on the basis of Fitzpatrick standard trading terms & conditions. A copy of which is available on request

##### SPECIFICATION

##### DOORLEAVES

Manufactured from 1.2mm electro zinc coated (zintec) steel, with vertical interlock edge seams, honeycombe infill to comprise 44mm thick leaf, single swing hung on 3 no 114mm x 102mm heavy duty stainless steel hinges.  Double doors complete with astragal to leading edges of leaves.

##### DOORFRAMES

Manufactured from 1.6mm electro zinc coated steel, press braked to form a single or double rebated “plant on” profile to a maximum 147mm width and with a maximum of one fixing point.  Frame/s supplied in butt jointed, knockdown form with frame assembly bolts provided.  Complete with hinge shims and frame packers.

##### FIXING

Preparation for type 7 (second fix) fixing method with black plastic plugs or concealed discs included.  Masonry or steel work fixing bolts by Fitzpatrick

##### SEALS

Doors complete with E3 self adhesive draught seal, supplied loose for application on site by Fitzpatrick.

THRESHOLD – IF REQUIRED

8135 aluminium threshold with seal or steel cill.

E23271

RAPHAEL

THE BECKENHAM CENTRE

2 FEBRUARY 2007

LOUVRES – WHERE REQUIRED

Complete with 1 no L1 450mm x 1500mm, 450mm x 450mm or 450mm x 300mm aluminium louver per leaf c/w flymesh.

##### OVERPANELS – DOOR TYPES L10, L11 & L12

Solid fixed overpanels of similar construction to doorleaf, sized in accordance with schedule.

##### FINISH

Polyester powder coated to a single agreed standard BS/RAL colour selected from our standard colour range.  Pricing subject to provision of colour reference and with non standard/special colours at additional cost.

IRONMONGERY

Doorframes/sets structurally reinforced and prepared to receive conventional surface mounted lockstrike, closer and all other nominated/free-issue hardware.  Drilling for and fitting of all hardware by Fitzpatrick.

Hardware included in Fitzpatrick scope;

114mm x 102mm heavy duty stainless steel ‘dogbolt’ ball bearing hinges

Manual flushbolts to inactive leaf (double doors)

All other hardware excluded from this offer.

We trust this quotation will be of interest to you and we look forward to receiving your further instructions.

With regards

Russell Grove

Sales Director