Floorcraft Contractors (London) Limited

17a Station Road

Walthamstow

London

E17 8AA							               07 January 2008

For the attention of Mr N Croucher

Dear Sirs

Re: 311-318 High Holborn

We enclose herewith Order No. 20498 for the flooring installation at the above, on a supply and fix basis.

Please refer to section k) of this order for your health & safety obligations, in addition please forward all relevant COSHH information, method statements and risk assessments to the site address, for the attention of Mr Paul Haugh, a minimum of four weeks prior to commencement on site.

We have amended your quotation to reflect recent discussions between yourselves and our Mr Paul Haugh.  We have altered the quantities for the hardwood flooring in accordance with our own take off’s, we confirm however that all quantities, both sub floor and hardwood, are subject to re-measurement and that it is your responsibility to carry out your own survey for the purpose of material ordering.

Company information including insurances, CIS, VAT etc to be forwarded to our Chessington office for the attention of Mr Paul Bennett.

We trust this is self-explanatory but, should you have any queries, please contact the undersigned.

Yours faithfully

S Thorpe

c.c.	R C Hayhoe

M O’Brien

P Haugh

D Singh

Floorcraft Contractors (London) Limited

17a Station Road

Walthamstow

London

E17 8AA							               07 January 2008

Order No. 20498

Re: 311-318 High Holborn

To supply & fix timber flooring on a labour, plant & material basis, in accordance with the documentation listed below (copies of which are attached):

1)	Your quotation dated 03.01.08 (hand amended in accordance with the 	covering letter to this order).

For the sum of £33,795.00(+ VAT). Subject to remeasurement.

Please note the following:

a)	Your price is fixed for the duration of the works

b)	Terms:  Monthly

c)	Discount:  2 ½ %

d)	Retention will be held at 5%.  One half will be released at practical completion 	and the balance at the end of the defects liability period

e)	Daywork will only be used as the basis for valuing variations where agreed 	rates/sums are not applicable and where they cannot be accurately pro-rata’d.  	In these instances sheets must be offered for signature within 7 days of the 	works being carried out

f)	Programme:	Site Survey			       16.01.08

Commencement		w/c 04.02.08

Completion 		                   18.04.08

Our Project Manager will forward a detailed programme

g)	Our Project Manager will forward a full set of current information.  Your 	works are to be carried out to these details in preference to those issued at 	tender stage.  Your materials are to match the approved samples.

h)	Attendances are to be as the attached schedule.  It is your responsibility to 	carry out take offs for the purpose of material ordering

i)	All labour is to be employed fully in accordance with Government 	employment legislation

j)	All labour is to be CSCS qualified

k)	Works are to be undertaken fully in accordance with all relevant Health & 	Safety Regulations including the provision of all necessary PPE for our 	operatives.  It is a condition of this order that the Health & Safety 	questionnaire sent under separate cover is completed to the satisfaction of 	our Director in charge of safety, Martin O'Brien

l)	Requests for Information must be in writing and should be addressed to our 	Project Foreman

m)	Should any terms and conditions within your quotation contradict the terms of 	this order, this order will take precedence.

n)	You are to provide the following by return:

- O & M Manual data

Please note that payments may be withheld until we are in receipt of these

o)	The Project address is:

Raphael Contracting Ltd

c/o Skanska

311-318 High Holborn

London

WC2

Project Manager	Mr Paul Haugh

Mobile No.		07970 045912

Site phone/fax		020 7242 5582