Lemongrass Kitchens

Unit 12

Radford Crescent

Billericay

Essex  CM12 0DG						               03 January 2008

Dear Sirs

Re: 311-318 High Holborn

We enclose herewith Order No. 20491 for the kitchen installation at the above, on a supply and fix basis.

Please refer to section k) of this order for your health & safety obligations, in addition please forward all relevant COSHH information, method statements and risk assessments to the site address, for the attention of Mr Paul Haugh, a minimum of four weeks prior to commencement on site.

This order is based on your quotation entitled ‘revised 11.12.07”, GRP 3 option.  It currently excludes glass upstands and associated socket cut outs for which an addendum order will follow if required.

Samples are to be provided in accordance with item g) of the attached order.

Company information including insurances, CIS, VAT etc to be forwarded to our Chessington office for the attention of Mr Paul Bennett.

We trust this is self-explanatory but, should you have any queries, please contact the undersigned.

Yours faithfully

S Thorpe

c.c.	R C Hayhoe

M O’Brien

P Haugh

D Singh

Lemongrass Kitchens

Unit 12

Radford Crescent

Billericay

Essex  CM12 0DG						               03 January 2008

Order No. 20491

Re: 311-318 High Holborn

To supply & fix kitchens on a labour, plant & material basis, in accordance with the documentation listed below (copies of which are attached):

1)	Your quotation dated 11.12.07 hand amended in accordance with the covering 	letter for this order and so as to identify the VAT separately

For the sum of £81,380.97  (+ VAT)

Please note the following:

a)	Your price is fixed for the duration of the works

b)	Terms:  Monthly

c)	Discount:  Nett

d)	Retention will be held at 5%.  One half will be released at practical completion 	and the balance at the end of the defects liability period

e)	Daywork will only be used as the basis for valuing variations where agreed 	rates/sums are not applicable and where they cannot be accurately pro-rata’d.  	In these instances sheets must be offered for signature within 7 days of the 	works being carried out

f)	Programme:	Sample	s			w/c 07.01.08

Drawing Approval (RCL)	w/c 14.01.08

Site Survey			w/c 14.01.08

Commencement		w/c 14.02.08

Completion 			       11.04.08

Our Project Manager will forward a detailed programme

g)	Our Project Manager will issue comments upon/approve your drawings w/c 	14.01.08.  Your kitchens are to be manufactured to these details in preference 	to any earlier documentation.  You are to provide the following samples by 	return for approval prior to manufacture:

i)	GRP 3 spray finish and colour

ii)	The proposed alternative to “Virginia Mist granite”

iii)	Handles

h)	Attendances are to be as the attached schedule.  Your quotation allows for a 	site survey, all dimensions taken as part of this are your responsibility.

i)	All labour is to be employed fully in accordance with Government 	employment legislation

j)	All labour is to be CSCS qualified

k)	Works are to be undertaken fully in accordance with all relevant Health & 	Safety Regulations including the provision of all necessary PPE for our 	operatives.  It is a condition of this order that the Health & Safety 	questionnaire sent under separate cover is completed to the satisfaction of 	our Director in charge of safety, Martin O'Brien

l)	Requests for Information must be in writing and should be addressed to our 	Project Foreman

m)	Should any terms and conditions within your quotation contradict the terms of 	this order, this order will take precedence.

n)	You are to provide the following by return:

- O & M Manual data

Please note that payments may be withheld until we are in receipt of these

o)	The Project address is:

Raphael Contracting Ltd

c/o Skanska

311-318 High Holborn

London

WC2

Project Manager	Mr Paul Haugh

Mobile No.		07970 045912

Site phone/fax		020 7242 5582