## JMS SHEDULE OF WORKS
[11 empty] | MS | JS | PS | [7 empty] | Drawing
JMS REF | Floor | Item | Size | Nr | GA | Drawing | Details | Cost each | Total cost | Notes | HOURS | HOURS | HOURS | Stone | Glass | Metal | Corian | Fabric | Veneer | Laminate | Days |  | Revised notes | Lighting
7138/1 |  | Samples | [5 empty] | 0 | 0 | Standard small samples of materials included. None standard samples not included as do not know what is required. | #REF! | #REF! | #REF!
7138/2 |  | Mock-ups | [5 empty] | 0 | 0 | None priced as do not know what is required | #REF! | #REF! | #REF!
7138/3 |  | Fire assessment | [5 empty] | 0 | 0 |  | #REF! | #REF! | #REF!
7138/4 |  | New internal Frames SW | As schedule | 1 |  | A-52002-P22-S4 | A-52002-P22-S4 | 25594.8627 | 25594.8627 | All as attached schedule NG200-PUR-SS_25_30_20_25-SWZZ-SH-A-52000-P22-S4
7138/5 |  | New internal Frames & doors WB | As schedule | 1 |  | A-52001-P27-S4 | A-52007-P27-S4 | 10105.4157 | 10105.4157 | All as attached schedule NG200-PUR-SS_25_30_20_25-W0-SH-A-52001-P27-S4 |  |  |  |  | 2023-05-26
7138/6 |  | Whitcomb street Frame & door |  | 1 |  | A-41003-P12-S2 |  | 0 | 0 | By others | #REF! | #REF! | #REF!
7138/7 | SW Grd | MW-01.0 Espresso front & back Counter | 6229mm x 2480mm x 1350mm | 1 | A-500 | A-501, 502, 503 | A-540-A4, A6 | 54555.5482 | 54555.5482 | 4 Nr base units with doors, 6 Nr base units without doors & 1 Nr corner base unit without doors. Stone shelf, splashback & top all supplied & fitted. All electrical and plumbing equipment to be supply & fit by others. | #REF! | #REF! | #REF! | 2023-05-26 | 2023-05-26 | 2023-05-26 |  |  | 2023-06-01 |  | 10 |  | Now Purbeck Blue Marble | 525 | 6.3Lm
7138/8 | SW Grd | MW-02.0 Espresso standing counter | 2400mm x 450mm x 1100mm | 1 | A-500 | A-501, 503 | A-540-A3 | 4357.6021 | 4357.6021 | Metal support frame & stone top. | #REF! | #REF! | #REF! | 2023-05-26 |  | 2023-05-26 |  |  |  |  | 3 |  | Now Purbeck Blue Marble
7138/9 | SW Grd | MW-03.0 Espresso disposable counter | 2400mm x 600mm x 850mm | 1 | A-500 | A-501, 503 | A-540-A1 | 10495.0479 | 10495.0479 | Unit on casters with stone top. | #REF! | #REF! | #REF! | 2023-05-26 |  | 2023-05-26 |  |  |  | 2023-06-02 | 5 |  | Now Purbeck Blue Marble
7138/10 | SW Grd | MW-04.1 Sitting window counter | 4800mm x 600mm x 900mm ish | 1 | A-500 | A-501, 503 | A-540-C1 | 7480.6238 | 7480.6238 | Metal clad wall panels with metal brackets to support stone top. Trench heater and grills to be by others. | #REF! | #REF! | #REF! | 2023-05-26 |  | 2023-05-26 |  |  |  |  | 1 |  | Now Purbeck Blue Marble
7138/11 | SW Grd | MW-04.2 Sitting window counter | 4800mm x 600mm x 900mm ish | 1 | A-500 | A-501, 503 | A-540-C1 | 7480.6238 | 7480.6238 | Metal clad wall panels with metal brackets to support stone top. Trench heater and grills to be by others. | #REF! | #REF! | #REF! | 2023-05-26 |  | 2023-05-26 |  |  |  |  | 1 |  | Now Purbeck Blue Marble
7138/12 | SW Grd | MW-04.3 Sitting window counter | 4800mm x 600mm x 900mm ish | 1 | A-500 | A-501, 503 | A-540-C1 | 7480.6238 | 7480.6238 | Metal clad wall panels with metal brackets to support stone top. Trench heater and grills to be by others. | #REF! | #REF! | #REF! | 2023-05-26 |  | 2023-05-26 |  |  |  |  | 1 |  | Now Purbeck Blue Marble
7138/13 | SW Grd | MW-04.4 Sitting window counter | 4800mm x 600mm x 900mm ish | 1 | A-500 | A-501, 503 | A-540-C1 | 7480.6238 | 7480.6238 | Metal clad wall panels with metal brackets to support stone top. Trench heater and grills to be by others. | #REF! | #REF! | #REF! | 2023-05-26 |  | 2023-05-26 |  |  |  |  | 1 |  | Now Purbeck Blue Marble
7138/14 | SW Grd | MW-05.0 Point of sale | 1220mm x 500mm x 900mm | 1 | A-500 | A-504 |  | 4159.6119 | 4159.6119 | 1 Nr veneered base unit & 3 shelves above. | #REF! | #REF! | #REF! | [5 empty] | 2023-06-01 |  | 2 |  |  | 625 | 6 x 1.2Lm
7138/15 | SW Grd | MW-06.1 wall hung unit | 1590mm x 600mm x 770mm | 1 | A-500 | A-504 |  | 5722.9616 | 5722.9616 | 2 Nr veneered wall unit with 1 Nr drawer & 3 Nr shelves above. | #REF! | #REF! | #REF! | [5 empty] | 2023-06-01 |  | 1 |  |  | 775 | 6 x 1.6Lm
7138/16 | SW Grd | MW-06.2 wall hung unit | 1590mm x 600mm x 770mm | 1 | A-500 | A-504 |  | 5722.9616 | 5722.9616 | 2 Nr veneered wall unit with 1 Nr drawer & 3 Nr shelves above. | #REF! | #REF! | #REF! | [5 empty] | 2023-06-01 |  | 1 |  |  | 775 | 6 x 1.6Lm
7138/17 | SW Grd | MW-06.3 wall hung unit | 1590mm x 600mm x 770mm | 1 | A-500 | A-504 |  | 5722.9616 | 5722.9616 | 2 Nr veneered wall unit with 1 Nr drawer & 3 Nr shelves above. | #REF! | #REF! | #REF! | [5 empty] | 2023-06-01 |  | 1 |  |  | 775 | 6 x 1.6Lm
7138/18 | SW Grd | MW-07.1 display table | 1000mm x 1000mm x 770mm | 1 | A-500 | A-504 |  | 5193.9632 | 5193.9632 | 2 Nr veneered base units back to back. | #REF! | #REF! | #REF! | [5 empty] | 2023-06-01 |  | 1
7138/19 | SW Grd | MW-07.2 display table | 1000mm x 1000mm x 770mm | 1 | A-500 | A-504 |  | 5193.9632 | 5193.9632 | 2 Nr veneered base units back to back. | #REF! | #REF! | #REF! | [5 empty] | 2023-06-01 |  | 1
7138/20 | SW Grd | MW-07.3 display table | 1000mm x 1000mm x 770mm | 1 | A-500 | A-504 |  | 5193.9632 | 5193.9632 | 2 Nr veneered base units back to back. | #REF! | #REF! | #REF! | [5 empty] | 2023-06-01 |  | 1
7138/21 | SW Grd | MW-07.4 display table | 1000mm x 1000mm x 770mm | 1 | A-500 | A-504 |  | 5193.9632 | 5193.9632 | 2 Nr veneered base units back to back. | #REF! | #REF! | #REF! | [5 empty] | 2023-06-01 |  | 1
7138/22 | SW Grd | MW-07.5 display table | 1000mm x 1000mm x 770mm | 1 | A-500 | A-504 |  | 5193.9632 | 5193.9632 | 2 Nr veneered base units back to back. | #REF! | #REF! | #REF! | [5 empty] | 2023-06-01 |  | 1
7138/23 | SW 1st | MW-08.1 bookshelves | 9869mm x 375mm x 2765mm | 1 | A-500 | A-510 |  | 32469.3168 | 32469.3168 | 13 Nr veneered tall units with 1 Nr display shelf in each. | #REF! | #REF! | #REF! | [5 empty] | 2023-06-01 |  | 5
7138/24 | SW 1st | MW-08.2 bookshelves | 7167mm + 5202mm x 2765mm x 375mm | 1 | A-500 | A-511 |  | 54172.4833 | 54172.4833 | 15 Nr veneered tall units with 2 Nr doors in each. | #REF! | #REF! | #REF! | [5 empty] | 2023-06-01 |  | 10
7138/25 | SW 1st | MW-08.3 server station | 2080mm x 600mm x 900mm | 1 | A-500 | A-510 | A-542-C6 | 11026.3566 | 11026.3566 | 4 Nr base units with doors & drawers. | #REF! | #REF! | #REF! |  |  | 2023-05-26 |  |  | 2023-06-01 |  | 3
7138/26 | SW 1st | MW-09.0 café bar |  | 1 | A-500 | A-512, 513 | A-540-C3, C5, C7 | 141514.6476 | 141514.6476 | SWD stud wall clad with ply panels and Lavastone to outside and units to inside where required with catering equipment by others. Inner island units supplied with SWD & ply clad with with glass All electrical and plumbing to be by others, | #REF! | #REF! | #REF! | 2023-05-26 | 2023-05-26 | 2023-05-26 |  |  | 2023-06-01 |  | 20 |  | Now based on Pyrolave quote | 1850 | 24Lm
7138/27 | SW 1st | MW-10.0 dining back bar | 10550mm x 600mm x 900mm + display steps | 1 | A-500 | A-530, 531 | A-541-A6 | 39639.0046 | Excluded from scope | 8 Nr veneered base units. 3 Nr rear display stands. All electrical & plumbing goods to be by others. | #REF! | #REF! | #REF! |  |  | 2023-05-26 | 2023-05-26 |  | 2023-06-01 | 2023-06-02 | 5 |  |  | 900 | 6 x 1.8Lm
7138/28 | SW 1st | MW-11.0 dining bar |  | 1 | A-500 | A-530, 531 | A-541-A4 | 54308.6227 | Excluded from scope | 4 Nr veneered base units. Stud wall to support upper top and take cladding. All electrical and pulmbing to be by others. | #REF! | #REF! | #REF! | 2023-05-26 |  | 2023-05-26 |  |  | 2023-06-01 |  | 5 |  |  | 1350 | 2 x 8.5Lm
7138/29 | SW 1st | MW-12.0 kitchen pass through |  | 1 | A-500 |  |  | 0 | Excluded from scope | Drawing required | #REF! | #REF! | #REF!
7138/30 | SW 1st | MW-13.1 double banquette seat | 5500mm x 1400mm x 1150mm | 1 | A-500 | A-532 | A-541-A2 | 14448.5867 | Excluded from scope | 6 Nr sections to form 1 Nr large double sided seat. | #REF! | #REF! | #REF! |  |  |  |  | 2023-05-26 | 2023-06-01 |  | 4
7138/31 | SW 1st | MW-13.2 server station | 1400mm x 600mm x 1150mm | 3 | A-500 | A-532 | A-542-C5 | 7058.3066 | Excluded from scope | Veneered unit supplied with 2 Nr doors & 4 Nr drawers. | #REF! | #REF! | #REF! |  |  | 2023-05-26 |  |  | 2023-06-01 |  | 3
7138/32 | SW 1st | MW-14.1 banquette seat | 3600mm x 750mm x 1150mm | 1 | A-500 | A-533 | A-541-C2 | 7431.4774 | Excluded from scope | 3 Nr sections to form 1 Nr single sided seat | #REF! | #REF! | #REF! |  |  |  |  | 2023-05-26 | 2023-06-01 |  | 3
7138/33 | SW 1st | MW-14.2 banquette seat | 5500mm + 7000mm x 750mm x 1150mm | 1 | A-500 |  | A-541-C2 | 22139.8816 | Excluded from scope | Only GA and section drawings. 7 Nr sections to form long L shaped seat | #REF! | #REF! | #REF! |  | 2023-05-26 |  |  | 2023-05-26 | 2023-06-01 |  | 5
7138/34 | SW 1st | MW-14.3 banquette seat | 5500mm + 10150mm x 750mm x 1150mm | 1 | A-500 |  | A-541-C2 | 28767.9204 | Excluded from scope | Only GA and section drawings. 9 Nr sections to form long L shaped seat | #REF! | #REF! | #REF! |  |  |  |  | 2023-05-26 | 2023-06-01 |  | 5
7138/35 | SW 1st | MW-15.0 lounge bar | 2490mm x 1050mm x 1150mm | 1 | A-500 | A-534, 535 | A-541-C4 | 9463.3265 | Excluded from scope | 1 Nr veneered base unit with metal top. All electrical goods to be by others. | #REF! | #REF! | #REF! |  |  | 2023-05-26 |  |  | 2023-06-01 |  | 3 |  |  | 450 | 2 x 2.5Lm
7138/36 | SW 1st | MW-16.0 lounge back bar | 4335mm x 900mm x 1300mm | 1 | A-500 | A-534, 535 | A-541-C5 | 14140.6963 | Excluded from scope | 2 Nr veneered base units with metal top, displat shelves & mirror wall panels. All electrical & plumbing goods to be by others. | #REF! | #REF! | #REF! |  | 2023-05-26 | 2023-05-26 | 2023-05-26 |  | 2023-06-01 | 2023-06-02 | 5 |  |  | 450 | 2 x 2.5Lm
7138/37 | SW Basement | MW-17.0 seating | 2846mm x 1000mm x 800mm | 5 | A-500 | A-520 | A-542-C3 | 8780.9805 | 43904.9023 | Upholstered seats with veneered back shelf and face panels between each unit. | #REF! | #REF! | #REF! |  |  |  |  | 2023-05-26 | 2023-06-01 |  | 3
7138/38 | SW Basement | MW-18.0 cloakroom counter | 4000mm x 700mm x 900mm | 1 | A-500 | A-521 | A-542-C2 | 9826.0773 | 9826.0773 | Painted units with stone top. PC sum for ironmongery for gate & flap £250.00. Flap will have weight issues. | #REF! | #REF! | #REF! | 2023-05-26 |  |  |  |  | 2023-06-01 |  | 4 |  | Now Purbeck Blue Marble
7138/39 | SW Basement | MW-19.1 storage | 8000mm x 500mm x 2850mm | 1 | A-500 | A-521 |  | 31685.0618 | 31685.0618 | 16 Nr Painted units for storage. | #REF! | #REF! | #REF! | [5 empty] | 2023-02-01 |  | 3
7138/40 | SW Basement | MW-19.2 storage | 8000mm x 500mm x 2850mm | 1 | A-500 | A-521 |  | 31685.0618 | 31685.0618 | 16 Nr Painted units for storage. | #REF! | #REF! | #REF! | [5 empty] | 2023-06-01 |  | 3
7138/41 | SW Grd | MN-20.0 greeter station | 2050mm + 3150mm x 700mm x 850mm | 1 | A-500 | A-505 | A-542-A6 | 9333.7564 | 9333.7564 | Solid timber legs & frame with veneered panels. Will have 5 Nr drawers & 1 Nr door. Will be deliverd in 2 sections for assembley by others. Electrical goods to be by others. | #REF! | #REF! | #REF! |  |  | 2023-05-26 |  |  | 2023-06-02 |  | 6
7138/42 | SW 1st | MW-21.0 FCU cover | 2450mm x 400mm x 1000mm unit & 2450mm x 32mm x 3570mm mirror | 1 | A-500 | A-533 | A-542-A2 | 2804.7847 | Excluded from scope | Primed FCU cover with grille by others. Primed mirror frame with supply & fixed mirrors. | #REF! | #REF! | #REF! |  | 2023-05-26 | 2023-05-26 |  |  |  |  | 2
7138/43 | SW 1st | MW-22.1 FCU cover | 1500mm x 400mm x 1000mm | 1 | A-500 |  | A-542-A3 | 665.4447 | Excluded from scope | Only GA and section drawings. Primed FCU cover with grille by others. | #REF! | #REF! | #REF! |  |  | 2023-05-26 |  |  |  |  | 1
7138/44 | SW 1st | MW-22.2 FCU cover | 1500mm x 400mm x 1000mm | 1 | A-500 |  | A-542-A3 | 665.4447 | Excluded from scope | Only GA and section drawings. Primed FCU cover with grille by others. | #REF! | #REF! | #REF! |  |  | 2023-05-26 |  |  |  |  | 1
7138/45 | SW 1st | MW-22.3 FCU cover | 1500mm x 400mm x 1000mm | 1 | A-500 |  | A-542-A3 | 665.4447 | Excluded from scope | Only GA and section drawings. Primed FCU cover with grille by others. | #REF! | #REF! | #REF! |  |  | 2023-05-26 |  |  |  |  | 1
7138/46 | SW Grd | MW-23.0 waiter station | 930mm x 400mm x 2400mm | 1 | A-500 | A-501, 502 | A-540-A7 | 3358.0144 | 3358.0144 | Veneered panels & stone top. All plumbing goods by others. | #REF! | #REF! | #REF! | 2023-05-26 |  | 2023-05-26 |  |  | 2023-01-02 |  | 3 |  | Now Purbeck Blue Marble
7138/47 | SW Grd | MW-24.1 security scanner post |  | 1 | A-500 |  | A-542-A7 | 315.0392 | 315.0392 | 1 Nr post ad drawing | #REF! | #REF! | #REF! |  |  | 2023-05-26 |  |  |  |  | 0.5
7138/48 | SW Grd | MW-24.2 security scanner post |  | 1 | A-500 |  | A-542-A7 | 315.0392 | 315.0392 | 1 Nr post ad drawing | #REF! | #REF! | #REF! |  |  | 2023-05-26 |  |  |  |  | 0.5
7138/49 | SW Grd | MW-24.2 security scanner post |  | 1 | A-500 |  | A-542-A7 | 315.0392 | 315.0392 | 1 Nr post ad drawing | #REF! | #REF! | #REF! |  |  | 2023-05-26 |  |  |  |  | 0.5
7138/50 |  | Swd skirting | 400mm x 32mm | 100 |  |  |  | 38.2784 | Excluded from scope | Supplied in 3 sections in randum lengths all primed for decoration by others | #REF! | #REF! | #REF!
7138/51 |  | Oak skirting | Ex 150mm x 32mm | 100 |  |  |  | 39.9782 | 3997.8174 | Supplied in randum lengths with full finish to detail 8 on drawing 55006 | #REF! | #REF! | #REF!
7138/52 |  | Oak skirting | Ex 150mm x 25mm | 100 |  |  |  | 34.1007 | Excluded from scope | Supplied in randum lengths with full finish to detail 9 on drawing 55006 | #REF! | #REF! | #REF!
7138/53 |  | Door repairs |  | 9 |  |  |  | 827.5637 | 7448.0733 | Priced for 3 Nr hinge repairs/make good, 1 Nr closer repair/make good, 1 Nr lock case repair/make good. 1 Nr handle repair/make good & re finish. | #REF! | #REF! | #REF!
7138/54 |  | G847 WF-11 Wall panels | 10.5 M2 | 1 |  | 70043-70045 |  | 2562.4505 | 2562.4505 | Supplied as FR MDF veneered panels with split battens. All studwork and acoustic insulation to be by others | #REF! | #REF! | #REF! | [7 empty] | 3 | Elevation & section only
7138/55 |  | F837 WF-01 Wall panels | 39 M2 | 1 |  | 70060 |  | 21041.8508 | 21041.8508 | Supplied as FR MDF veneered panels with split battens. All studwork and acoustic insulation to be by others | #REF! | #REF! | #REF! | [7 empty] | 3 | Elevation & section only
7138/56 |  | F815 WF-11 Wall panels | 1.3 M2 | 1 |  | 70062 |  | 345.0394 | 345.0394 | Supplied as FR MDF veneered panels with split battens. All studwork and acoustic insulation to be by others | #REF! | #REF! | #REF! | [7 empty] | 1 | Elevation & section only
7138/57 |  | F809 WF-11 Wall panels | 24.75 M2 | 1 |  | 70063 |  | 6224.3457 | 6224.3457 | Supplied as FR MDF veneered panels with split battens. All studwork and acoustic insulation to be by others | #REF! | #REF! | #REF! | [7 empty] | 3 | Elevation & section only
7138/58 |  | F843 WF-11 Wall panels | 14.3 M2 | 1 |  | 70068 |  | 3583.7014 | 3583.7014 | Supplied as FR MDF veneered panels with split battens. All studwork and acoustic insulation to be by others | #REF! | #REF! | #REF! | [7 empty] | 3 | Elevation & section only
7138/59 |  | F801 WF-11 Wall panels | 4.59 M2 | 1 |  | 70064 |  | 1143.9819 | 1143.9819 | Supplied as FR MDF veneered panels with split battens. All studwork and acoustic insulation to be by others | #REF! | #REF! | #REF! | [7 empty] | 2 | Elevation & section only
7138/60 | Basement | L839 - Female WC - WF03 - High pressure laminate (Wall Panels) | 18.7M2 | 0 |  | 74001 | 1 | 3639.5209 | 0 | Supplied as 9 Nr panels plain colour Compact laminate (8.5Lm) with Aluminium split battens | #REF! | #REF! | #REF! | [6 empty] | 2023-06-29
7138/61 | Grd | G856 - Changing Places - WF03 - Solid grade high-pressure laminate (Wall Panels) | 28.27M2 | 0 |  | 74003 & 74004 | 1, 2, 3, 4 | 5489.0662 | 0 | Supplied as 13 Nr panels plain colour Compact laminate (12.85Lm) with Aluminium split battens | #REF! | #REF! | #REF! | [6 empty] | 2023-06-29
7138/62 | 1St | F895 - UWC - WF03 & Venturi - High pressure laminate (Wall Panels) | 7.48M2 | 0 |  | 74008 | 5, 6, 7 | 16719.7733 | 0 | Supplied as 4 Nr panels in plain colour Compact laminate & 2 Nr panels in Venturi Textile print (total 5.5Lm) with Aluminium battens. Elevation 4 IPS by others | #REF! | #REF! | #REF! | [6 empty] | 2023-06-29
7138/63 | 1St | F893 - AWC - WF03 - High pressure laminate (Wall Panels) | 0 | 0 |  | 74008 | 8, 9, 10, 11 | 0 | 0 | Elevation 8 IPS by others & no other panels | #REF! | #REF! | #REF!
7138/64 | 1St | F881 - Male WC - WF03 - High pressure laminate (Wall Panels) | 27.22M2 | 0 |  | 74005 | 1,3 | 5189.9719 | 0 | Supplied as 12 Nr panels in plain colour Compact laminate (10.47Lm) with Aluminium battens. Elevation 2 & part 1 cubical wall by others | #REF! | #REF! | #REF! | [6 empty] | 2023-06-29
7138/65 | 1St | F871 - Female WC - WF03 - High pressure laminate (Wall Panels) | 21.01M2 | 0 |  | 74006 | 1, 2, 3 | 3999.6293 | 0 | Supplied as 9 Nr panels in plain colour Compact laminate (8.7Lm) with Aluminium battens. Elevation 4 IPS by others | #REF! | #REF! | #REF! | [6 empty] | 2023-06-29
7138/66 |  | Un-named WC of F852 - WF03 - High pressure laminate (???) |  | 0 |  |  |  | 0 | 0 | Not found on drawings | #REF! | #REF! | #REF!
7138/67 |  | Un-named WC of F852 - WF03 - High pressure laminate (???) |  | 0 |  |  |  | 0 | 0 | not found on drawings | #REF! | #REF! | #REF!
7138/68 | Basement | L839 - Female WC - Hinged Mirror Unit (5 nr) | 1690mm x 1155mm x 200mm | 0 |  | 74001 & 74003 | 3 | 2328.4086 | 0 | Each set supplied as 3 Nr units in laminated MR MDF with Mirrored doors. Mirrors supplied & fitted on site by our glazer. Soap dispenser & Hand dryer by others. | #REF! | #REF! | #REF! |  | 2023-06-29 |  |  |  |  | 2023-06-29
7138/69 | Basement | L839 - Female WC - Vanity Unit (5 nr) | 1690mm x 870mm x 250mm | 0 |  | 74001 & 74003 | 3 | 2960.5237 | 0 | Supplied as 3 Nr units laminated MR MDF with Compact laminate doors & plinth. Corian top, splash back & sink all supplied & fitted by our supplier. Taps & sanitory waste bin by others. | #REF! | #REF! | #REF! |  |  |  | 2023-06-29 |  |  | 2023-06-29
7138/70 | Basement | L817 - Family Room - WF03 - High pressure laminate (Wall Panels) | 17.70M2 | 0 |  | 74002 | 1, 5 | 24709.8741 | 0 | Supplied as 9 Nr panels in plain colour Compact laminate & 3 Nr Venturi Textile print (Total 10.15Lm) with Aluminium battens. | #REF! | #REF! | #REF! | [6 empty] | 2023-06-29
7138/71 | Basement | L817 - Family Room - Hinged Mirror Unit (1 nr) | 3300mm x 1155mm x 200mm | 0 |  | 74002 | 4 | 3694.3706 | 0 | Supplied as 3 Nr units in laminated MR MDF with Mirrored doors. Mirrors supplied & fitted on site by our glazer. Soap dispenser, Hand dryer & paper towel dispenser by others. | #REF! | #REF! | #REF! |  | 2023-06-29 |  |  |  |  | 2023-06-29
7138/72 | Basement | L817 - Family Room - Vanity Unit & bench (1 nr) | 3300mm x 870mm x 590mm | 0 |  | 74002 | 4 | 5782.311 | 0 | Supplied as 3 Nr units laminated MR MDF with Compact laminate doors & plinth. Corian top, splash back, sink & seat cladding all supplied & fitted by our supplier. Taps & sanitory waste bin by others. | #REF! | #REF! | #REF! |  |  |  | 2023-06-29 |  |  | 2023-06-29
7138/73 | Basement | L835 - AWC - WF03 - Solid grade high-pressure laminate (Wall Panels) | 16.88M2 | 0 |  | 74001 | 5, 6, 7, 8 | 3197.1777 | 0 | Supplied as 6 Nr panels in plain colour Compact laminate (6.25Lm) with Aluminium battens. Elevation 5 IPS by others | #REF! | #REF! | #REF! | [6 empty] | 2023-06-29
7138/74 | Basement | L836 - Male WC - WF03 - Solid grade high-pressure laminate (Wall Panels) | 18.70M2 | 0 |  | 74001 | 3 | 3639.5253 | 0 | Supplied as 9 Nr panels in plain colour Compact laminate (8.5Lm) with Aluminium battens. | #REF! | #REF! | #REF! | [6 empty] | 2023-06-29
7138/75 | Basement | L836 - Male WC - Hinged Mirror Unit (5 nr) | 1650mm x 1155mm x 200mm | 0 |  | 74001 & 7403 | 3 | 2330.6347 | 0 | Each set supplied as 3 Nr units in laminated MR MDF with Mirrored doors. Mirrors supplied & fitted on site by our glazer. Soap dispenser & Hand dryer by others. | #REF! | #REF! | #REF! |  | 2023-06-29 |  |  |  |  | 2023-06-29
7138/76 | Basement | L836 - Male WC - Vanity Unit (5 nr) | 1650mm x 870mm x 250mm | 0 |  | 74001 & 7403 |  | 2960.5269 | 0 | Supplied as 3 Nr units laminated MR MDF with Compact laminate doors & plinth. Corian top, splash back & sink all supplied & fitted by our supplier. Taps & sanitory waste bin by others. | #REF! | #REF! | #REF! |  |  |  | 2023-06-29 |  |  | 2023-06-29
7138/77 | 1St | L871 - Female WC - Hinged Mirror Unit (13 nr) | 1690mm x 1150mm x 200mm | 0 |  | 74005 & 74006 | 1 | 2315.3413 | 0 | Each set supplied as 3 Nr units in laminated MR MDF with Mirrored doors. Mirrors supplied & fitted on site by our glazer. Soap dispenser & Hand dryer by others. | #REF! | #REF! | #REF! |  | 2023-06-29 |  |  |  |  | 2023-06-29
7138/78 | 1St | L871 - Female WC - Hinged Mirror Unit (2 nr) | 2300mm x 1150mm x 200mm | 0 |  | 74005 |  | 2602.7438 | 0 | Each set supplied as 3 Nr units in laminated MR MDF with Mirrored doors. Mirrors supplied & fitted on site by our glazer. Soap dispenser & Hand dryer by others. | #REF! | #REF! | #REF! |  | 2023-06-29 |  |  |  |  | 2023-06-29
7138/79 | 1St | L871 - Female WC - Vanity Unit (13 nr) | 1690mm x 870mm x 250mm | 0 |  | 74005 & 74006 |  | 2943.979 | 0 | Supplied as 3 Nr units laminated MR MDF with Compact laminate doors & plinth. Corian top, splash back & sink all supplied & fitted by our supplier. Taps & sanitory waste bin by others. | #REF! | #REF! | #REF! |  |  |  | 2023-06-29 |  |  | 2023-06-29
7138/80 | 1St | L871 - Female WC - Vanity Unit (2 nr) | 2300mm x 870mm x 250mm | 0 |  | 74005 |  | 3512.1378 | 0 | Supplied as 3 Nr units laminated MR MDF with Compact laminate doors & plinth. Corian top, splash back & sink all supplied & fitted by our supplier. Taps & sanitory waste bin by others. | #REF! | #REF! | #REF! |  |  |  | 2023-06-29 |  |  | 2023-06-29
7138/81 | Grd | G091 - WCS - Hinged Mirror Unit (4 nr) |  | 0 |  | 74000 | 5 | 0 | 0 | See item 7138/90 below | #REF! | #REF! | #REF! |  | 2023-06-29 |  |  |  |  | 2023-06-29
7138/82 | Grd | G857 - AWC - 1 run of 8 panels (Wall Panels) | 10.89M2 | 0 |  | 74003 & 74004 | 6, 7, 8 | 2135.7439 | 0 | Supplied as 6 Nr panels in plain colour Compact laminate (4.95Lm) with Aluminium battens. Elevation 5 IPS by others | #REF! | #REF! | #REF! | [6 empty] | 2023-06-29
7138/83 | 1St | F854 - STAFF WC - SGL WC Wall Panels (Wall Panels) | 10.27M2 | 0 |  | 74005 & 74007 | 2, 3, 4 | 1989.5514 | 0 | Supplied as 6 Nr panels in plain colour Compact laminate (3.95Lm) with Aluminium battens. Elavation 1 IPS by others | #REF! | #REF! | #REF! | [6 empty] | 2023-06-29
7138/84 | 1St | F856 - STAFF WC - SGL WC Wall Panels (Wall Panels) | 11.96M2 | 0 |  | 74005 & 74007 | 6, 7, 8 | 2317.2171 | 0 | Supplied as 7 Nr panels in plain colour Compact laminate (4.6Lm) with Aluminium battens. Elevation 5 IPS by others | #REF! | #REF! | #REF! | [6 empty] | 2023-06-29
7138/85 | 1St | F895 - UWC - Hinged Mirror Unit | 1670mm x 1150mm x 200mm | 0 |  | 74008 |  | 2424.0281 | 0 | Supplied as 3 Nr units in laminated MR MDF with Mirrored doors. Mirrors supplied & fitted on site by our glazer. Soap dispenser & Hand dryer by others. | #REF! | #REF! | #REF! |  | 2023-06-29 |  |  |  |  | 2023-06-29
7138/86 | 1St | F895 - UWC - Vanity Unit | 1670mm x 870mm x 250mm | 0 |  | 74008 |  | 2953.0782 | 0 | Supplied as 3 Nr units laminated MR MDF with Compact laminate doors & plinth. Corian top, splash back & sink all supplied & fitted by our supplier. Taps & sanitory waste bin by others. | #REF! | #REF! | #REF! |  |  |  | 2023-06-29 |  |  | 2023-06-29
7138/87 | 1St | F881 - Male WC - Hinged Mirror Unit (9 nr) | 1690mm x 1150mm x 200mm | 0 |  | 74005 | 3 | 2399.3986 | 0 | Each set supplied as 3 Nr units in laminated MR MDF with Mirrored doors. Mirrors supplied & fitted on site by our glazer. Soap dispenser & Hand dryer by others. | #REF! | #REF! | #REF! |  | 2023-06-29 |  |  |  |  | 2023-06-29
7138/88 | 1St | F881 - Male WC- Vanity Unit (9 nr) | 1690mm x 870mm x 250mm | 0 |  | 74005 | 3 | 2925.6688 | 0 | Supplied as 3 Nr units laminated MR MDF with Compact laminate doors & plinth. Corian top, splash back & sink all supplied & fitted by our supplier. Taps & sanitory waste bin by others. | #REF! | #REF! | #REF! |  |  |  | 2023-06-29 |  |  | 2023-06-29
7138/89 | 1St | F888 U WC/B Change wall panels | 14.46M2 | 0 |  | 74008 | 1, 2, 3 | 2769.5153 | 0 | Supplied as 7 Nr panels in plain colour Compact laminate (5.56Lm) with Aluminium battens. Elevation 5 IPS by others | #REF! | #REF! | #REF! | [6 empty] | 2023-06-29
7138/90 | Grd | G091 - WCS - Vanity Unit | 1650mm x 870mm x 250mm | 0 |  | 74009 | 9 | 2939.5096 | 0 | Supplied as 3 Nr units laminated MR MDF with Compact laminate doors & plinth. Corian top, splash back & sink all supplied & fitted by our supplier. Taps & sanitory waste bin by others. | #REF! | #REF! | #REF! |  |  |  | 2023-06-29 |  |  | 2023-06-29
7138/91+62:93 | Grd | G091 - WCS - Mirror unit | 1650mm x 1150mm x 200mm | 0 |  | 74009 | 9 | 2424.0281 | 0 | Each set supplied as 3 Nr units in laminated MR MDF with Mirrored doors. Mirrors supplied & fitted on site by our glazer. Soap dispenser & Hand dryer by others. | #REF! | #REF! | #REF! |  | 2023-06-29 |  |  |  |  | 2023-06-29
7138/92 |  | G858 WF11 wall panels | 33.5 M2 | 1 |  |  |  | 7433.3291 | 7433.3291 | Supplied as FR MDF veneered panels with split battens. All studwork and acoustic insulation to be by others | #REF! | #REF! | #REF!
7138/93 |  | Steps |  | 1 |  | 42015 P13 |  | 761.902 | 761.902 | SWD stud frame with HWD treads & risers | #REF! | #REF! | #REF!
7138/94 |  | Cill | 1200mm x 415mm | 1 |  | 42015 P13 |  | 126.1397 | 126.1397 | HWD | #REF! | #REF! | #REF!
7138/95 | 1st | Medical room |  | 1 |  | 70071 P22 |  | 6944.6489 | Scope to be confirmed | 4 Nr wall units, 3 Nr base units & 1 Nr tall fridge housing all in plain colour formica. Top in corian. All eletrical and plumbing goods to be by others. | #REF! | #REF! | #REF!
7138/96 |  | External signage |  | 1 |  | 84001 P59 |  | 10584.6384 | Scope to be confirmed | Letters as per drawing with metal support rods. No allowance has been made for any electrical goods or the pipe through wall. | #REF! | #REF! | #REF!
7138/97 |  | LED to joinery fitments |  | 1 |  |  |  | 8475 | 8475 |  | #REF! | #REF! | #REF! | [10 empty] | 8475
7138/98 | [7 empty] | 0 | 0 |  | #REF! | #REF! | #REF!
7138/99 | [7 empty] | 0 | 0 |  | #REF! | #REF! | #REF!
TOTAL | [8 empty] | 615393.7114 |  | #REF! | #REF! | #REF!

## SW Door schedule Rev A
New Internal Solid Doors Schedule - Sainsbury Wing
Mark | Type Mark | Door Material | Location |  | Type Comments | Door Opening |  |  |  |  | Transom Panel Height (if applicable) | Overall Frame Thickness | Operation | Acoustic Rating (Required) | Fire Rating (Required) | Smoke Seal | Vision Panel | Access Control | Hinge Side | Finish |  | Ironmongery |  |  |  | Statutory Signange (material to match adjacent ironmongery) |  | Comments
|  |  | To Room: Name | To Room: Number |  | Structural Opening Height | Structural Opening Width | Clear Opening Height | Clear Opening Width | Clear Opening Width - Single Leaf | [9 empty] | Panel Finish | Frame Finish | Ironmongery - Finish | Kick plate | Handle - Front | Handle - Back | Signage - Front | Signage - Back |  | Frame | Door | Total | Notes | MS | JS | PS
D-SWB1-001-L835 | SW-ID-1 | Solid Timber Hardwood | A WC | L835 | Single Leaf | 2850 | 1030 | 2400 | 815 |  | 410 | 270 | Manual |  | 30 mins | Yes | No |  | Right | Rift Sawn White Oak Veneer with Grey Lacuered coating RAL TBC | Rift Sawn White Oak with Grey Lacquered coating RAL TBC | Brushed Stainless Steel | Yes | L1 - Lever | L1 - Lever | FDKS | FDKS | Allow for WC Signage | 1014.6666 | 0 | 1014.6666 | A.W. Oak Split 3 sided lining & stop. Door, over panel & ironmongery by others. | #REF! | #REF! | #REF!
D-SWB1-001-L839 | SW-ID-1 | Solid Timber Hardwood | LINK CORRIDOR | L823 | Single Leaf | 2850 | 960 | 2400 | 805 |  | 410 | 258 | Manual |  | 30 mins | Yes | No |  | Right | Rift Sawn White Oak Veneer with Grey Lacuered coating RAL TBC | Rift Sawn White Oak with Grey Lacquered coating RAL TBC | Brushed Stainless Steel | Yes | PB1 - Pull Bar | PP1 - Push Plate | FDKS | FDKS | Allow for WC Signage | 973.7131 | 0 | 973.7131 | A.W. Oak Split 3 sided lining & stop. Door, over panel & ironmongery by others. | #REF! | #REF! | #REF!
D-SWB1-001-L836 | SW-ID-1 | Solid Timber Hardwood | LINK CORRIDOR | L823 | Single Leaf | 2850 | 960 | 2400 | 805 |  | 410 | 258 | Manual |  | 30 mins | Yes | No |  | Left | Rift Sawn White Oak Veneer with Grey Lacuered coating RAL TBC | Rift Sawn White Oak with Grey Lacquered coating RAL TBC | Brushed Stainless Steel | Yes | PB1 - Pull Bar | PP1 - Push Plate | FDKS | FDKS | Allow for WC Signage | 973.7131 | 0 | 973.7131 | A.W. Oak Split 3 sided lining & stop. Door, over panel & ironmongery by others. | 3.368 | 3 | 5.125
D-SWB1-001-F887 | SW-ID-7 | Solid Timber Hardwood | CLOAK ROOM | L821 | Single Leaf | 2455 | 850 | 2400 | 700 |  |  | 122 | Manual |  | 30 mins | Yes | No |  | Left | Painted to match existing dark grey - RAL 7012 | Painted to match existing dark grey - RAL 7030 | Brushed Stainless Steel | Yes | L1 - Lever | L1 - Lever | FDKS | FDKS |  | 330.1208 | 0 | 330.1208 | Sapele primed single 3 sided lining & stop. Door, over panel & ironmongery by others. | #REF! | #REF! | #REF!
D-SWB1-001-L811 | SW-ID-7 | Solid Timber Hardwood |  |  | Single Leaf | 2215 | 1080 | 2160 | 865 |  |  | 150 | Manual |  | 30 mins | Yes | No |  | Right | Painted to match existing dark grey - RAL 7012 | Painted to match existing dark grey - RAL 7030 | Brushed Stainless Steel | Yes | L1 - Lever | L1 - Lever | FDKS | FDKS |  | 338.0993 | 0 | 338.0993 | Sapele primed single 3 sided lining & stop. Door, over panel & ironmongery by others. | #REF! | #REF! | #REF!
D-SW0-001-G856 | SW-ID-1 | Solid Timber Hardwood | CHANGING PLACES LOBBY | G858 | Single Leaf | 3350 | 1220 | 2400 | 1005 |  | 910 | 137 | Motorised |  |  | No | No |  | Left | Rift Sawn White Oak Veneer Oak to be stained using WoodSong II Deep Penetrating Stain Base or similar approved | Rift Sawn White Oak to be stained using WoodSong II Deep Penetrating Stain Base or similar approved | Brushed Stainless Steel | Yes | L2 - Lever | L2 - Lever & Grab Rail |  |  | Allow for WC Signage. Timber head closer at ceiling required. | 620.779 | 0 | 620.779 | A.W.Oak Single 3 sided lining & stop. Door, over panel & ironmongery by others. | #REF! | #REF! | #REF!
D-SW0-001-G857 | SW-ID-1 | Solid Timber Hardwood | CHANGING PLACES LOBBY | G858 | Single Leaf | 3350 | 1020 | 2400 | 805 |  | 910 | 176 | Manual |  |  | No | No |  | Right | Rift Sawn White Oak Veneer Oak to be stained using WoodSong II Deep Penetrating Stain Base or similar approved | Rift Sawn White Oak to be stained using WoodSong II Deep Penetrating Stain Base or similar approved | Brushed Stainless Steel | Yes | L1 - Lever | L1 - Lever & Grab Rail |  |  |  | 909.9329 | 0 | 909.9329 | A.W. Oak Split 3 sided lining & stop. Door, over panel & ironmongery by others. | #REF! | #REF! | #REF!
D-SW0-001-G850 | SW-ID-1 | Solid Timber Hardwood | ESPRESSO BAR KITCHEN | G850 | Single Leaf | 3350 | 1020 | 2400 | 865 |  | 910 | 155 | Manual |  | 30 mins | Yes | No | Yes (New) | Left | Rift Sawn White Oak Veneer Oak to be stained using WoodSong II Deep Penetrating Stain Base or similar approved | Rift Sawn White Oak to be stained using WoodSong II Deep Penetrating Stain Base or similar approved | Brushed Stainless Steel | Yes | PB1 - Pull Bar | PP1 - Push Plate | FDKS | FDKS |  | 636.0794 | 1 | 637.0794 | A.W.Oak Single 3 sided lining & stop. Door, over panel & ironmongery by others. | #REF! | #REF! | #REF!
D-SW0-001-G849 | SW-ID-2 | Solid Timber Hardwood | SHOP | G863 | Leaf and a Half | 3350 | 1420 | 2400 | 1175 | 800 | 910 | 147 | Manual |  | 30 mins | Yes | No | Yes (New) | Left Leading Leaf | Rift Sawn White Oak Veneer Oak to be stained using WoodSong II Deep Penetrating Stain Base or similar approved | Rift Sawn White Oak to be stained using WoodSong II Deep Penetrating Stain Base or similar approved | Brushed Stainless Steel | Yes | L1 - Lever | PH1 - Panic Bar | FDKS | FDKS | Alarmed if not fully closed | 655.771 | 0 | 655.771 | A.W.Oak Single 3 sided lining & stop. Door, over panel & ironmongery by others. | #REF! | #REF! | #REF!
D-SW0-001-G843 | SW-ID-7 | Solid Timber Hardwood | IT ROOM | G853 | Single Leaf | 2455 | 1080 | 2400 | 865 |  |  | 128 | Manual |  | 30 mins | Yes | No | Yes (New) | Left | Painted to match existing dark grey - RAL 7012 | Painted to match existing dark grey - RAL 7030 | Brushed Stainless Steel | Yes | L1 - Lever | L1 - Lever | FDKS | FDKS |  | 340.2607 | 0 | 340.2607 | Sapele primed single 3 sided lining & stop. Door, over panel & ironmongery by others. | #REF! | #REF! | #REF!
D-SW0-002-G850 | SW-ID-7 | Solid Timber Hardwood | ESPRESSO BAR KITCHEN | G850 | Single Leaf | 2455 | 1080 | 2400 | 865 |  |  | 128 | Manual | 30 dB | 30 mins | Yes | No |  | Left | Painted to match existing dark grey - RAL 7012 | Painted to match existing dark grey - RAL 7030 | Brushed Stainless Steel | Yes | L1 - Lever | L1 - Lever | FDKS | FDKS |  | 352.3505 | 0 | 352.3505 | Sapele primed single 3 sided lining & stop. Door, over panel & ironmongery by others. | #REF! | #REF! | #REF!
D-SW0-001-G852 | SW-ID-8 | Solid Timber Hardwood | EGRESS CORRIDOR | G849 | Leaf and a Half | 2455 | 1485 | 2400 | 1240 | 854 |  | 128 | Manual |  | 30 mins | Yes | No |  | Right Leading Leaf | Painted to match existing dark grey - RAL 7012 | Painted to match existing dark grey - RAL 7030 | Brushed Stainless Steel | Yes | L1 - Lever | L1 - Lever | FDKS | FDKS | Alarmed if not fully closed | 351.2687 | 0 | 351.2687 | Sapele primed single 3 sided lining & stop. Door, over panel & ironmongery by others. | #REF! | #REF! | #REF!
D-SW0-002-G849 | SW-ID-8 | Solid Timber Hardwood | LOADING BAY | XXX | Leaf and a Half | 2455 | 1485 | 2400 | 1240 | 854 |  | 150 | Manual |  | 30 mins | Yes | Yes |  | Left Leading Leaf | Painted to match existing dark grey - RAL 7012 | Painted to match existing dark grey - RAL 7030 | Brushed Stainless Steel | Yes | L1 - Lever | L1 - Lever | FDKS | FDKS | Alarmed if not fully closed | 368.2545 | 0 | 368.2545 | Sapele primed single 3 sided lining & stop. Door, over panel & ironmongery by others. | #REF! | #REF! | #REF!
D-SW0-001-G862 | SW-ID-9 | Solid Timber Hardwood | EGRESS CORRIDOR | G849 | Double Leaf | 2445 | 1780 | 2400 | 1600 | 802 |  | 128 | Manual |  | 30 mins | Yes | No |  | Left ¦ Right | Painted to match existing dark grey - RAL 7012 | Painted to match existing dark grey - RAL 7030 | Brushed Stainless Steel | Yes | L1 - Lever | None | FDKS | FDKS | Alarmed if not fully closed | 358.7432 | 0 | 358.7432 | Sapele primed single 3 sided lining & stop. Door, over panel & ironmongery by others. | #REF! | #REF! | #REF!
D-SW0-001-G833 | SW-ID-10 | Steel Door for Stone Cladding | VESTIBULE | G833 | Single Leaf | 2120 | 795 | 2065 | 580 |  |  | 140 | Manual |  | 30 mins | Yes | No | Yes (New) | Left | Portland Stone Cladding | Concealed | Brushed Stainless Steel | No | E1 - Edge Pull | PP1 - Push Plate | FDKS | FDKS | Metal traydoor with honeycomb portland stone. Bespoke Door to be further detailed alongside specialist input | 0 | 0 | 0 | By Others
D-SW1-002-F833 | SW-ID-11 | Solid Timber Hardwood | CHANGING PLACES LOBBY | G858 | Single Leaf | 3350 | 1220 | 2410 | 1005 |  | 895 | 482 | N/A |  |  | No | No |  | N/A | Rift Sawn White Oak Veneer Oak to be stained using WoodSong II Deep Penetrating Stain Base or similar approved | Rift Sawn White Oak to be stained using WoodSong II Deep Penetrating Stain Base or similar approved | N/A | No | N/A | N/A |  |  | Framed Opening with Transom - No Door Panel | 1884.03 | 0 | 1884.03 | A.W. Oak Split 3 sided lining & stop. Door, over panel & ironmongery by others. | #REF! | #REF! | #REF!
D-SW1-001-F871 | SW-ID-1 | Solid Timber Hardwood | FEMALE WC | F871 | Single Leaf | 2765 | 960 | 2175 | 805 |  | 550 | 176 | Manual |  |  | No | No |  | Left | Rift Sawn White Oak Veneer Oak to be stained using WoodSong II Deep Penetrating Stain Base or similar approved | Rift Sawn White Oak to be stained using WoodSong II Deep Penetrating Stain Base or similar approved | Brushed Stainless Steel | Yes | PB1 - Pull Bar | PP1 - Push Plate |  |  | Allow for WC Signage | 831.319 | 0 | 831.319 | A.W. Oak Split 3 sided lining & stop. Door, over panel & ironmongery by others. | #REF! | #REF! | #REF!
D-SW1-001-F881 | SW-ID-1 | Solid Timber Hardwood | WCs VESTIBULE | F887 | Single Leaf | 2765 | 960 | 2175 | 805 |  | 550 | 176 | Manual |  |  | No | No |  | Left | Rift Sawn White Oak Veneer Oak to be stained using WoodSong II Deep Penetrating Stain Base or similar approved | Rift Sawn White Oak to be stained using WoodSong II Deep Penetrating Stain Base or similar approved | Brushed Stainless Steel | Yes | PB1 - Pull Bar | PP1 - Push Plate |  |  |  | 831.319 | 0 | 831.319 | A.W. Oak Split 3 sided lining & stop. Door, over panel & ironmongery by others. | 3.067 | 3 | 5.125
D-SW1-001-F893 | SW-ID-1 | Solid Timber Hardwood | AWC | F893 | Single Leaf | 2765 | 1030 | 2175 | 815 |  | 550 | 176 | Manual |  |  | No | No |  | Right | Rift Sawn White Oak Veneer Oak to be stained using WoodSong II Deep Penetrating Stain Base or similar approved | Rift Sawn White Oak to be stained using WoodSong II Deep Penetrating Stain Base or similar approved | Brushed Stainless Steel | Yes | L1 - Lever | L1 - Lever & Grab Rail |  |  |  | 835.7929 | 0 | 835.7929 | A.W. Oak Split 3 sided lining & stop. Door, over panel & ironmongery by others. | #REF! | #REF! | #REF!
D-SW1-001-F895 | SW-ID-1 | Solid Timber Hardwood | U WC | F895 | Single Leaf | 2765 | 860 | 2175 | 705 |  | 550 | 176 | Manual |  |  | No | No |  | Left | Rift Sawn White Oak Veneer Oak to be stained using WoodSong II Deep Penetrating Stain Base or similar approved | Rift Sawn White Oak to be stained using WoodSong II Deep Penetrating Stain Base or similar approved | Brushed Stainless Steel | Yes | L1 - Lever | L1 - Lever |  |  |  | 824.9276 | 0 | 824.9276 | A.W. Oak Split 3 sided lining & stop. Door, over panel & ironmongery by others. | #REF! | #REF! | #REF!
D-SW1-001-F888 | SW-ID-1 | Solid Timber Hardwood | WCs VESTIBULE | F889 | Single Leaf | 2765 | 1030 | 2175 | 815 |  | 550 | 176 | Manual |  |  | No | No |  | Left | Rift Sawn White Oak Veneer Oak to be stained using WoodSong II Deep Penetrating Stain Base or similar approved | Rift Sawn White Oak to be stained using WoodSong II Deep Penetrating Stain Base or similar approved | Brushed Stainless Steel | Yes | L1 - Lever | L1 - Lever & Grab Rail |  |  |  | 835.7929 | 0 | 835.7929 | A.W. Oak Split 3 sided lining & stop. Door, over panel & ironmongery by others. | 3.088 | 3 | 5.125
D-SW1-001-F852 | SW-ID-1 | Solid Timber Hardwood | CORRIDOR | F852 | Single Leaf | 2765 | 1160 | 2175 | 1005 |  | 550 | 137 | Manual |  | 30 mins | Yes | No | Yes (New) | Right | Rift Sawn White Oak Veneer Oak to be stained using WoodSong II Deep Penetrating Stain Base or similar approved | Rift Sawn White Oak to be stained using WoodSong II Deep Penetrating Stain Base or similar approved | Brushed Stainless Steel | Yes | L1 - Lever | L1 - Lever | FDKS | FDKS | Timber head closer at ceiling required - Type 2 | 587.3358 | 0 | 587.3358 | A.W.Oak Single 3 sided lining & stop. Door, over panel & ironmongery by others. | #REF! | #REF! | #REF!
D-SW1-002-F837 | SW-ID-1 | Solid Timber Hardwood | CORRIDOR | F860 | Single Leaf | 2745 | 1030 | 2155 | 805 |  | 550 | 177 | Manual | 35 dB | 30 mins | Yes | No | Yes (New) | Left | Rift Sawn White Oak Veneer Oak to be stained using WoodSong II Deep Penetrating Stain Base or similar approved | Rift Sawn White Oak to be stained using WoodSong II Deep Penetrating Stain Base or similar approved | Brushed Stainless Steel | Yes | L1 - Lever | L1 - Lever | FDKS | FDKS | Timber head closer at ceiling required - Type 2 | 859.5014 | 0 | 859.5014 | A.W. Oak Split 3 sided lining & stop. Door, over panel & ironmongery by others. | #REF! | #REF! | #REF!
D-SW1-003-F837 | SW-ID-1 | Solid Timber Hardwood | EVENT SPACE | F837 | Single Leaf | 2765 | 1040 | 2175 | 825 |  | 550 | 177 | Manual | 35 dB | 30 mins | Yes | No | Yes (New) | Left | Rift Sawn White Oak Veneer Oak to be stained using WoodSong II Deep Penetrating Stain Base or similar approved | Rift Sawn White Oak to be stained using WoodSong II Deep Penetrating Stain Base or similar approved | Brushed Stainless Steel | Yes | L1 - Lever | L1 - Lever | FDKS | FDKS |  | 862.6971 | 0 | 862.6971 | A.W. Oak Split 3 sided lining & stop. Door, over panel & ironmongery by others. | #REF! | #REF! | #REF!
D-SW1-001-F843 | SW-ID-3 | Solid Timber Hardwood | KITCHEN | F843 | Double Leaf | 2765 | 1900 | 2175 | 1710 | 886 | 550 | 137 | Manual | 30 dB | 30 mins | Yes | Yes |  | Left ¦ Right | Rift Sawn White Oak Veneer Oak to be stained using WoodSong II Deep Penetrating Stain Base or similar approved | Rift Sawn White Oak to be stained using WoodSong II Deep Penetrating Stain Base or similar approved | Brushed Stainless Steel | Yes | PB1 - Pull Bar | PP1 - Push Plate | FDKS | FDKS | Alarmed if not fully closed. Timber head closer at ceiling required | 585.6658 | 0 | 585.6658 | A.W.Oak Single 3 sided lining & stop. Door, over panel & ironmongery by others. | #REF! | #REF! | #REF!
D-SW1-001-F891 | SW-ID-3 | Solid Timber Hardwood | CLEANERS STORE | F891 | Double Leaf | 2765 | 1080 | 2175 | 890 | 476 | 550 | 134 | Manual |  |  | No | No |  | Left ¦ Right | Painted to match existing dark grey - RAL 7012 | Painted to match existing dark grey - RAL 7030 | Brushed Stainless Steel | Yes | PB1 - Pull Bar | PP1 - Push Plate |  |  | Alarmed if not fully closed | 330.8473 | 0 | 330.8473 | Sapele primed single 3 sided lining & stop. Door, over panel & ironmongery by others. | #REF! | #REF! | #REF!
D-SW1-001-F817 | SW-ID-4 | Solid Timber Hardwood | STAIR | F817 | Single Leaf | 2100 | 1035 | 2040 | 805 |  |  | 122 | Manual |  | 30 mins | Yes | No | Yes (New) | Left | Painted to match existing dark grey - RAL 7012 | Painted to match existing dark grey - RAL 7030 | Brushed Stainless Steel | Yes | L1 - Lever | PH1 - Panic Bar | FDKS | FDKS | Door Panelling to match existing. | 315.8512 | 0 | 315.8512 | Sapele primed single 3 sided lining & stop. Door, over panel & ironmongery by others. | #REF! | #REF! | #REF!
D-SW1-001-F855 | SW-ID-4 | Solid Timber Hardwood | KITCHEN | F843 | Single Leaf | 2230 | 1040 | 2175 | 825 |  |  | 152 | Manual | 30 dB | 30 mins | Yes | Yes |  | Right | Painted to match existing dark grey - RAL 7012 | Painted to match existing dark grey - RAL 7030 | Brushed Stainless Steel | Yes | L1 - Lever | L1 - Lever | FDKS | FDKS |  | 342.802 | 0 | 342.802 | Sapele primed single 3 sided lining & stop. Door, over panel & ironmongery by others. | #REF! | #REF! | #REF!
D-SW1-001-F821 | SW-ID-5 | Solid Timber Hardwood | SERVERY / PANTRY | F821 | Single Leaf | 2100 | 1035 | 2040 | 810 |  |  | 122 | Manual | 35 dB | 30 mins | Yes | No | Yes (New) | Right | Painted to match existing dark grey - RAL 7012 | Painted to match existing dark grey - RAL 7030 | Brushed Stainless Steel | Yes | L1 - Lever | L1 - Lever | FDKS | FDKS | Door Panelling to match existing. | 320.8507 | 0 | 320.8507 | Sapele primed single 3 sided lining & stop. Door, over panel & ironmongery by others. | #REF! | #REF! | #REF!
D-SW1-001-F866 | SW-ID-7 | Solid Timber Hardwood | IMR / SECURITY | F866 | Single Leaf | 2230 | 985 | 2175 | 830 |  |  | 128 | Manual | 30 dB |  | No | No | Yes (Existing) | Left | Painted to match existing dark grey - RAL 7012 | Painted to match existing dark grey - RAL 7030 | Brushed Stainless Steel | Yes | PB1 - Pull Bar | PP1 - Push Plate |  |  |  | 337.5374 | 0 | 337.5374 | Sapele primed single 3 sided lining & stop. Door, over panel & ironmongery by others. | #REF! | #REF! | #REF!
D-SW1-001-F856 | SW-ID-7 | Solid Timber Hardwood | STAFF WC | F856 | Single Leaf | 2500 | 920 | 2445 | 705 |  |  | 167 | Manual |  |  | No | No |  | Left | PPC/Painted to match existing dark grey - RAL 7012 | Painted to match existing dark grey - RAL 7030 | Brushed Stainless Steel | Yes | L1 - Lever | L1 - Lever |  |  | Allow for WC Signage | 473.4923 | 0 | 473.4923 | Sapele primed Split 3 sided lining & stop. Door, over panel & ironmongery by others. | #REF! | #REF! | #REF!
D-SW1-001-F854 | SW-ID-7 | Solid Timber Hardwood | CORRIDOR | F852 | Single Leaf | 2500 | 920 | 2445 | 705 |  |  | 167 | Manual |  |  | No | No |  | Left | PPC/Painted to match existing dark grey - RAL 7012 | Painted to match existing dark grey - RAL 7030 | Brushed Stainless Steel | Yes | L1 - Lever | L1 - Lever |  |  | Allow for WC Signage | 473.4923 | 0 | 473.4923 | Sapele primed Split 3 sided lining & stop. Door, over panel & ironmongery by others. | 2.896 | 3 | 1.2812
D-SW1-002-F841 | SW-ID-7 | Solid Timber Hardwood | MEDICAL ROOM | F862 | Single Leaf | 2500 | 1040 | 2445 | 825 |  |  | 128 | Manual | 30 dB | 30 mins | Yes | Yes |  | Right | Rift Sawn White Oak Veneer Oak to be stained using WoodSong II Deep Penetrating Stain Base or similar approved | Rift Sawn White Oak to be stained using WoodSong II Deep Penetrating Stain Base or similar approved | Brushed Stainless Steel | Yes | L1 - Lever | L1 - Lever | FDKS | FDKS |  | 518.5909 | 0 | 518.5909 | A.W.Oak Single 3 sided lining & stop. Door, over panel & ironmongery by others. | #REF! | #REF! | #REF!
D-SW1-002-F852 | SW-ID-7 | Solid Timber Hardwood | CORRIDOR | F860 | Single Leaf | 2500 | 985 | 2445 | 830 |  |  | 128 | Manual |  | 30 mins | Yes | Yes | Yes (New) | Left | Rift Sawn White Oak Veneer Oak to be stained using WoodSong II Deep Penetrating Stain Base or similar approved | Rift Sawn White Oak to be stained using WoodSong II Deep Penetrating Stain Base or similar approved | Brushed Stainless Steel | Yes | PB1 - Pull Bar | PP1 - Push Plate | FDKS | FDKS |  | 488.7806 | 0 | 488.7806 | A.W.Oak Single 3 sided lining & stop. Door, over panel & ironmongery by others. | #REF! | #REF! | #REF!
D-SW1-001-F864 | SW-ID-7 | Solid Timber Hardwood | CATERING KITCHEN | F864 | Single Leaf | 2500 | 985 | 2445 | 830 |  |  | 128 | Manual | 30 dB | 30 mins | Yes | Yes |  | Left | Rift Sawn White Oak Veneer Oak to be stained using WoodSong II Deep Penetrating Stain Base or similar approved | Rift Sawn White Oak to be stained using WoodSong II Deep Penetrating Stain Base or similar approved | Brushed Stainless Steel | Yes | PB1 - Pull Bar | PP1 - Push Plate | FDKS | FDKS |  | 516.1567 | 0 | 516.1567 | A.W.Oak Single 3 sided lining & stop. Door, over panel & ironmongery by others. | #REF! | #REF! | #REF!
D-SW1-001-F865 | SW-ID-7 | Solid Timber Hardwood | IMR LOBBY | F865 | Single Leaf | 2500 | 985 | 2445 | 830 |  |  | 128 | Manual | 30 dB | 30 mins | Yes | No | Yes (Existing) | Left | Rift Sawn White Oak Veneer Oak to be stained using WoodSong II Deep Penetrating Stain Base or similar approved | Rift Sawn White Oak to be stained using WoodSong II Deep Penetrating Stain Base or similar approved | Brushed Stainless Steel | Yes | PB1 - Pull Bar | PP1 - Push Plate | FDKS | FDKS |  | 521.7117 | 0 | 521.7117 | A.W.Oak Single 3 sided lining & stop. Door, over panel & ironmongery by others. | #REF! | #REF! | #REF!
D-SW1-003-F843 | SW-ID-7 | Solid Timber Hardwood | KITCHEN | F843 | Single Leaf | 2500 | 985 | 2445 | 830 |  |  | 128 | Manual | 30 dB | 30 mins | Yes | Yes |  | Right | Rift Sawn White Oak Veneer Oak to be stained using WoodSong II Deep Penetrating Stain Base or similar approved | Rift Sawn White Oak to be stained using WoodSong II Deep Penetrating Stain Base or similar approved | Brushed Stainless Steel | Yes | PB1 - Pull Bar | PP1 - Push Plate | FDKS | FDKS |  | 521.7117 | 0 | 521.7117 | A.W.Oak Single 3 sided lining & stop. Door, over panel & ironmongery by others. | 3.0405 | 2.625 | 3.8438
D-SW1-002-F821 | SW-ID-9 | Solid Timber Hardwood | ELEC CUPBOARD | F823 | Double Leaf | 2220 | 1080 | 2175 | 900 | 452 |  | 122 | Manual |  | 30 mins | Yes | No |  | Left ¦ Right | Painted to match existing dark grey - RAL 7012 | Painted to match existing dark grey - RAL 7030 | Brushed Stainless Steel | Yes | L1 - Lever | L1 - Lever | FDKS | FDKS | Alarmed if not fully closed | 323.5976 | 0 | 323.5976 | Sapele primed single 3 sided lining & stop. Door, over panel & ironmongery by others. | #REF! | #REF! | #REF!
D-SW1-002-F868 | SW-ID-9 | Solid Timber Hardwood | STORE ROOM | F868 | Double Leaf | 2220 | 1280 | 2175 | 1100 | 552 |  | 128 | Manual |  |  | No | No |  | Left ¦ Right | Painted to match existing dark grey - RAL 7012 | Painted to match existing dark grey - RAL 7030 | Brushed Stainless Steel | Yes | L1 - Lever | L1 - Lever |  |  | Alarmed if not fully closed | 322.211 | 0 | 322.211 | Sapele primed single 3 sided lining & stop. Door, over panel & ironmongery by others. | #REF! | #REF! | #REF!
D-SW1-001-F868 | SW-ID-9 | Solid Timber Hardwood | STORE ROOM | F868 | Double Leaf | 2220 | 1280 | 2175 | 1100 | 552 |  | 128 | Manual |  |  | No | No |  | Left ¦ Right | Painted to match existing dark grey - RAL 7012 | Painted to match existing dark grey - RAL 7030 | Brushed Stainless Steel | Yes | L1 - Lever | L1 - Lever |  |  | Alarmed if not fully closed | 322.211 | 0 | 322.211 | Sapele primed single 3 sided lining & stop. Door, over panel & ironmongery by others. | 1.724 | 1.75 | 1.025
D-SW1-002-F843 | SW-ID-9 | Solid Timber Hardwood | LIFT MOTOR ROOM | F845 | Double Leaf | 2220 | 1080 | 2175 | 900 | 452 |  | 128 | Manual | 30 dB | 30 mins | Yes | No |  | Left ¦ Right | Painted to match existing dark grey - RAL 7012 | Painted to match existing dark grey - RAL 7030 | Brushed Stainless Steel | Yes | L1 - Lever | L1 - Lever | FDKS | FDKS | Alarmed if not fully closed | 339.5759 | 0 | 339.5759 | Sapele primed single 3 sided lining & stop. Door, over panel & ironmongery by others. | #REF! | #REF! | #REF!
D-SW1-002-F866 | SW-ID-9 | Solid Timber Hardwood | SERVER CUPBOARD | F867 | Double Leaf | 2220 | 1080 | 2175 | 900 | 452 |  | 128 | Manual |  |  | No | No |  | Left ¦ Right | Painted to match existing dark grey - RAL 7012 | Painted to match existing dark grey - RAL 7030 | Brushed Stainless Steel | Yes | L1 - Lever | L1 - Lever |  |  | Alarmed if not fully closed | 316.775 | 0 | 316.775 | Sapele primed single 3 sided lining & stop. Door, over panel & ironmongery by others. | #REF! | #REF! | #REF!
D-SW1-001-F850 | SW-ID-9 | Solid Timber Hardwood | STORE ROOM | F850 | Double Leaf | 2500 | 1900 | 2455 | 1710 | 857 |  | 128 | Manual |  | 30 mins | Yes | No |  | Left ¦ Right | PPC/Painted to match existing dark grey - RAL 7012 | Painted to match existing dark grey - RAL 7030 | Brushed Stainless Steel | Yes | PB1 - Pull Bar | PP1 - Push Plate | FDKS | FDKS | Alarmed if not fully closed | 364.9946 | 0 | 364.9946 | Sapele primed single 3 sided lining & stop. Door, over panel & ironmongery by others. | #REF! | #REF! | #REF!
D-SW1-003-F852 | SW-ID-9 | Solid Timber Hardwood | CORRIDOR | F852 | Double Leaf | 2500 | 1080 | 2455 | 890 | 447 |  | 128 | Manual |  | 30 mins | Yes | No |  | Left ¦ Right | PPC/Painted to match existing dark grey - RAL 7012 | Painted to match existing dark grey - RAL 7030 | Brushed Stainless Steel | Yes | PB1 - Pull Bar | PP1 - Push Plate | FDKS | FDKS | Alarmed if not fully closed | 342.7069 | 0 | 342.7069 | Sapele primed single 3 sided lining & stop. Door, over panel & ironmongery by others. | #REF! | #REF! | #REF!
D-SW1-001-F889 | SW-ID-11 | Solid Timber Hardwood | WCs VESTIBULE | F889 | Single Leaf | 2765 | 985 | 2175 | 770 |  | 550 | 146 | N/A |  |  | No | No |  | N/A | Rift Sawn White Oak Veneer Oak to be stained using WoodSong II Deep Penetrating Stain Base or similar approved | Rift Sawn White Oak | N/A | No | N/A | N/A |  |  | Framed Opening with Transom - No Door Panel | 937.8316 | 0 | 937.8316 | A.W. Oak Split 3 sided lining & stop. Door, over panel & ironmongery by others. | #REF! | #REF! | #REF!
[31 empty] | 25594.8627 |  | #REF! | #REF! | #REF!

## WB DOOR SCHEDULE
New Internal Solid Doors Schedule - Wilkins Building
Mark | Type Mark | Door Material | Location |  | Type Comments | Door Opening | [11 empty] | Finish | [5 empty] | Statutory Signange (material to match adjacent ironmongery) |  | Comments
|  |  | To Room: Name | To Room: Number |  | Structural Opening Height | Structural Opening Width | Clear Opening Height | Clear Opening Width | Operation | Overall Frame Thickness | Acoustic Rating (Required) | Fire Rating (Required) | Smoke Seal | Vision Panel | Access Control | Hinge Side | Panel Finish | Frame Finish | Ironmongery - Finish | Kickplate | Handle - Front | Handle - Back | Signage - Back | Signage - Front |  | Frame | door | Total | Notes | MS | JS | PS
0 - GROUND FLOOR (WB)
D-W0-001-G103 | WB-ID-1 | Solid Timber Hardwood | WC VESTIBULE | G103 | Single Leaf | 2220 | 1180 | 2160 | 1020 | Motorised | 87 |  | 30 mins | Yes | Yes |  | Right | Oak to be stained using WoodSong II Deep Penetrating Stain Base or similar approved | Oak to be stained using WoodSong II Deep Penetrating Stain Base or similar approved | Unlacquered Brass | Yes | PB2 - Pull Bar | PP2 - Push Plate | FDKS | FDKS | Allow for WC Signage | 693.3672 | 3807.8509 | 4501.2181 | A.W.Oak Single 3 sided frame. 6 Panel door (1 glazed) using Mann McGowan SW panel system. All ironmongery by others. | 22.28 | 25 | 10.76
D-W0-001-G127 | WB-ID-2 | Solid Timber Hardwood | POT WASH | G119 | Single Leaf | 2340 | 1100 | 2250 | 720 | Manual | 94 | 35 dB | 30 mins | Yes | Yes | Yes (Existing) | Right | Oak to be stained using WoodSong II Deep Penetrating Stain Base or similar approved | Oak to be stained using WoodSong II Deep Penetrating Stain Base or similar approved | Unlacquered Brass | Yes | PB2 - Pull Bar | PP2 - Push Plate | FDKS | FDKS |  | 1771.5208 | 3832.6767 | 5604.1976 | A.W.Oak Single 3 sided frame with architraves both sides. 6 Panel door (2 glazed) using Mann McGowan SW panel system. All ironmongery by others. | 29.05 | 25 | 13.33
D-W0-002-G123 | WB-ID-3 | Carbon Steel Doorset | KITCHEN | G123 | Double Leaf Riser | 1120 | 1130 | 1000 | 1010 | [8 empty] | PPC | PPC |  | Yes | Manufacture's Standard | Manufacture's Standard |  |  |  | 0 | 0 | 0 | By Others
[29 empty] | 10105.4157 |  | 51.33 | 50 | 24.09