## Trade Contract Payment cycle
Payment cycle |  |  | Clause 4.7 |  | Clause 4.8 | 4.9.3 |  | Clause 4.10
| Trade Contractor issues application to CM |  | Interim Valuation Date (last Thursday of the month) |  | CM Interim Certificate | Trade Contractor issues |  | Final date
[5 empty] | (Payment Notice 4.8) | tax invoice |  | for payment
| 7 days |  | 7 days | 5 days | 3 days
30 days
|  |  | Clause 4.7 | Clause 4.7
|  |  | Valuation date | Payment due date
SRM Internal
|  | Issue Cash Flow on Monday | Issue draft certs to G&T | G&T approve |  |  | -1 day for payless notices
| 4 days | 3 days | 7 days
May 2023 - Example
last Thursday of month
| 2023-05-18 | 2023-05-22 | 2023-05-25 | 2023-06-01 | 2023-06-06 | 2023-06-09 |  | 2023-07-01

## Valuation Schedule
Valuation Schedule
Mth in which Works carried out | T/C Application Date | Interim Valuation Date last Thursday | Due Date | Interim Certificate (Payment notice) | 8 | Trade contractor invoice | Final Date for Payment to T/C | Final MC Date For Payment | Difference
| -14 days from Due Date | -7 days from Due Date | day 0 | 5 days from Due Date |  | 8 days from Due date | 30 days from Due date
| -14 | -7 | 0 | 5 |  | 8 | 30
2023-05-01 | 2023-05-18 | 2023-05-25 | 2023-06-01 | 2023-06-06 |  | 2023-06-09 | 2023-07-01 | 2020-11-02 | 971
2023-06-01 | 2023-06-22 | 2023-06-29 | 2023-07-06 | 2023-07-11 |  | 2023-07-14 | 2023-08-05 | 2020-11-30 | 978
2023-07-01 | 2023-07-20 | 2023-07-27 | 2023-08-03 | 2023-08-08 |  | 2023-08-11 | 2023-09-02 | 2021-01-04 | 971
2023-08-01 | 2023-08-24 | 2023-08-31 | 2023-09-07 | 2023-09-12 |  | 2023-09-15 | 2023-10-07 | 2021-02-01 | 978
2023-09-01 | 2023-09-21 | 2023-09-28 | 2023-10-05 | 2023-10-10 |  | 2023-10-13 | 2023-11-04 | 2021-03-01 | 978
2023-10-01 | 2023-10-19 | 2023-10-26 | 2023-11-02 | 2023-11-07 |  | 2023-11-10 | 2023-12-02 | 2021-03-29 | 978
2023-11-01 | 2023-11-23 | 2023-11-30 | 2023-12-07 | 2023-12-12 |  | 2023-12-15 | 2024-01-06 | 2021-05-04 | 977
2023-12-01 | 2023-12-21 | 2023-12-28 | 2024-01-04 | 2024-01-09 |  | 2024-01-12 | 2024-02-03 | 2021-06-01 | 977
2024-01-01 | 2024-01-18 | 2024-01-25 | 2024-02-01 | 2024-02-06 |  | 2024-02-09 | 2024-03-02 | 2021-07-05 | 971
2024-02-01 | 2024-02-22 | 2024-02-29 | 2024-03-07 | 2024-03-12 |  | 2024-03-15 | 2024-04-06 | 2021-08-02 | 978
2024-03-01 | 2024-03-21 | 2024-03-28 | 2024-04-04 | 2024-04-09 |  | 2024-04-12 | 2024-05-04 | 2021-08-30 | 978
2024-04-01 | 2024-04-18 | 2024-04-25 | 2024-05-02 | 2024-05-07 |  | 2024-05-10 | 2024-06-01 | 2021-10-04 | 971
2024-05-01 | 2024-05-23 | 2024-05-30 | 2024-06-06 | 2024-06-11 |  | 2024-06-14 | 2024-07-06 | 2021-11-01 | 978
2024-06-01 | 2024-06-20 | 2024-06-27 | 2024-07-04 | 2024-07-09 |  | 2024-07-12 | 2024-08-03 | 2021-11-29 | 978
2024-07-01 | 2024-07-18 | 2024-07-25 | 2024-08-01 | 2024-08-06 |  | 2024-08-09 | 2024-08-31 | 2022-01-03 | 971
2024-08-01 | 2024-08-22 | 2024-08-29 | 2024-09-05 | 2024-09-10 |  | 2024-09-13 | 2024-10-05 | 2022-01-31 | 978
2024-09-01 | 2024-09-19 | 2024-09-26 | 2024-10-03 | 2024-10-08 |  | 2024-10-11 | 2024-11-02 | 2022-03-07 | 971
2024-10-01 | 2024-10-24 | 2024-10-31 | 2024-11-07 | 2024-11-12 |  | 2024-11-15 | 2024-12-07 | 2022-04-04 | 978
2024-11-01 | 2024-11-21 | 2024-11-28 | 2024-12-05 | 2024-12-10 |  | 2024-12-13 | 2025-01-04 | 2022-05-02 | 978
2024-12-01 | 2024-12-19 | 2024-12-26 | 2025-01-02 | 2025-01-07 |  | 2025-01-10 | 2025-02-01 | 2022-05-31 | 977
2025-01-01 | 2025-01-23 | 2025-01-30 | 2025-02-06 | 2025-02-11 |  | 2025-02-14 | 2025-03-08 | 2022-07-04 | 978
2025-02-01 | 2025-02-20 | 2025-02-27 | 2025-03-06 | 2025-03-11 |  | 2025-03-14 | 2025-04-05 | 2022-08-01 | 978
2025-03-01 | 2025-03-20 | 2025-03-27 | 2025-04-03 | 2025-04-08 |  | 2025-04-11 | 2025-05-03 | 2022-08-26 | 981
2025-04-01 | 2025-04-17 | 2025-04-24 | 2025-05-01 | 2025-05-06 |  | 2025-05-09 | 2025-05-31 | 2022-10-03 | 971
2025-05-01 | 2025-05-22 | 2025-05-29 | 2025-06-05 | 2025-06-10 |  | 2025-06-13 | 2025-07-05 | 2022-10-31 | 978
2025-06-01 | 2025-06-19 | 2025-06-26 | 2025-07-03 | 2025-07-08 |  | 2025-07-11 | 2025-08-02 | 2022-12-09 | 967
2025-07-01 | 2025-07-24 | 2025-07-31 | 2025-08-07 | 2025-08-12 |  | 2025-08-15 | 2025-09-06
2025-08-01 | 2025-08-21 | 2025-08-28 | 2025-09-04 | 2025-09-09 |  | 2025-09-12 | 2025-10-04
2025-09-01 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-07 |  | 2025-10-10 | 2025-11-01
2025-10-01 | 2025-10-23 | 2025-10-30 | 2025-11-06 | 2025-11-11 |  | 2025-11-14 | 2025-12-06
2025-11-01 | 2025-11-20 | 2025-11-27 | 2025-12-04 | 2025-12-09 |  | 2025-12-12 | 2026-01-03
2025-12-01 | 2025-12-18 | 2025-12-25 | 2026-01-01 | 2026-01-06 |  | 2026-01-09 | 2026-01-31
2026-01-01 | 2026-01-22 | 2026-01-29 | 2026-02-05 | 2026-02-10 |  | 2026-02-13 | 2026-03-07
2026-02-01 | 2026-02-19 | 2026-02-26 | 2026-03-05 | 2026-03-10 |  | 2026-03-13 | 2026-04-04
2026-03-01 | 2026-03-19 | 2026-03-26 | 2026-04-02 | 2026-04-07 |  | 2026-04-10 | 2026-05-02
2026-04-01 | 2026-04-23 | 2026-04-30 | 2026-05-07 | 2026-05-12 |  | 2026-05-15 | 2026-06-06
2026-05-01 | 2026-05-21 | 2026-05-28 | 2026-06-04 | 2026-06-09 |  | 2026-06-12 | 2026-07-04
2026-06-01 | 2026-06-18 | 2026-06-25 | 2026-07-02 | 2026-07-07 |  | 2026-07-10 | 2026-08-01
2026-07-01 | 2026-07-23 | 2026-07-30 | 2026-08-06 | 2026-08-11 |  | 2026-08-14 | 2026-09-05
2026-08-01 | 2026-08-20 | 2026-08-27 | 2026-09-03 | 2026-09-08 |  | 2026-09-11 | 2026-10-03
2026-09-01 | 2026-09-17 | 2026-09-24 | 2026-10-01 | 2026-10-06 |  | 2026-10-09 | 2026-10-31
2026-10-01 | 2026-10-22 | 2026-10-29 | 2026-11-05 | 2026-11-10 |  | 2026-11-13 | 2026-12-05
2026-11-01 | 2026-11-19 | 2026-11-26 | 2026-12-03 | 2026-12-08 |  | 2026-12-11 | 2027-01-02
2026-12-01 | 2026-12-24 | 2026-12-31 | 2027-01-07 | 2027-01-12 |  | 2027-01-15 | 2027-02-06
2027-01-01 | 2027-01-21 | 2027-01-28 | 2027-02-04 | 2027-02-09 |  | 2027-02-12 | 2027-03-06
2027-02-01 | 2027-02-18 | 2027-02-25 | 2027-03-04 | 2027-03-09 |  | 2027-03-12 | 2027-04-03
2027-03-01 | 2027-03-18 | 2027-03-25 | 2027-04-01 | 2027-04-06 |  | 2027-04-09 | 2027-05-01
2027-04-01 | 2027-04-22 | 2027-04-29 | 2027-05-06 | 2027-05-11 |  | 2027-05-14 | 2027-06-05
2027-05-01 | 2027-05-20 | 2027-05-27 | 2027-06-03 | 2027-06-08 |  | 2027-06-11 | 2027-07-03
2027-06-01 | 2027-06-17 | 2027-06-24 | 2027-07-01 | 2027-07-06 |  | 2027-07-09 | 2027-07-31
2027-07-01 | 2027-07-22 | 2027-07-29 | 2027-08-05 | 2027-08-10 |  | 2027-08-13 | 2027-09-04
2027-08-01 | 2027-08-19 | 2027-08-26 | 2027-09-02 | 2027-09-07 |  | 2027-09-10 | 2027-10-02
2027-09-01 | 2027-09-23 | 2027-09-30 | 2027-10-07 | 2027-10-12 |  | 2027-10-15 | 2027-11-06
2027-10-01 | 2027-10-21 | 2027-10-28 | 2027-11-04 | 2027-11-09 |  | 2027-11-12 | 2027-12-04
2027-11-01 | 2027-11-18 | 2027-11-25 | 2027-12-02 | 2027-12-07 |  | 2027-12-10 | 2028-01-01
2027-12-01 | 2027-12-23 | 2027-12-30 | 2028-01-06 | 2028-01-11 |  | 2028-01-14 | 2028-02-05
Formulas:
T/C Application Date = [Interim Valuation Date last Thursday]-7
Due Date = [Interim Valuation Date last Thursday]+7
Interim Certificate (Payment notice) = [Due Date]+5
Trade contractor invoice = [Due Date]+8
Final Date for Payment to T/C = [Due Date]+30
Interim Valuation Date last Thursday = DATE(YEAR([Mth in which Works carried out]),MONTH([Mth in which Works carried out])+1,1)-WEEKDAY(DATE(YEAR([Mth in which Works carried out]),MONTH([Mth in which Works carried out])+1,3))

## Timetable
Museum of London
Payment Timetable
Valuation | Month | Year | Trade Contractor Application | G&T & Museum Sign Certificate | Construction Managers Certificate | Trade Contractor Invoice | Final Date for Payment
1 | May | 2023 | 2023-05-18 | 2023-06-01 | 2023-06-06 | 2023-06-09 | 2023-07-01
2 | June |  | 2023-06-22 | 2023-07-06 | 2023-07-11 | 2023-07-14 | 2023-08-05
3 | July |  | 2023-07-20 | 2023-08-03 | 2023-08-08 | 2023-08-11 | 2023-09-02
4 | August |  | 2023-08-24 | 2023-09-07 | 2023-09-12 | 2023-09-15 | 2023-10-07
5 | September |  | 2023-09-21 | 2023-10-05 | 2023-10-10 | 2023-10-13 | 2023-11-04
6 | October |  | 2023-10-19 | 2023-11-02 | 2023-11-07 | 2023-11-10 | 2023-12-02
7 | November |  | 2023-11-23 | 2023-12-07 | 2023-12-12 | 2023-12-15 | 2024-01-06
8 | December |  | 2023-12-21 | 2024-01-04 | 2024-01-09 | 2024-01-12 | 2024-02-03
9 | January | 2024 | 2024-01-18 | 2024-02-01 | 2024-02-06 | 2024-02-09 | 2024-03-02
10 | February |  | 2024-02-22 | 2024-03-07 | 2024-03-12 | 2024-03-15 | 2024-04-06
11 | March |  | 2024-03-21 | 2024-04-04 | 2024-04-09 | 2024-04-12 | 2024-05-04
12 | April |  | 2024-04-18 | 2024-05-02 | 2024-05-07 | 2024-05-10 | 2024-06-01
13 | May |  | 2024-05-23 | 2024-06-06 | 2024-06-11 | 2024-06-14 | 2024-07-06
14 | June |  | 2024-06-20 | 2024-07-04 | 2024-07-09 | 2024-07-12 | 2024-08-03
15 | July |  | 2024-07-18 | 2024-08-01 | 2024-08-06 | 2024-08-09 | 2024-08-31
16 | August |  | 2024-08-22 | 2024-09-05 | 2024-09-10 | 2024-09-13 | 2024-10-05
17 | September |  | 2024-09-19 | 2024-10-03 | 2024-10-08 | 2024-10-11 | 2024-11-02
18 | October |  | 2024-10-24 | 2024-11-07 | 2024-11-12 | 2024-11-15 | 2024-12-07
19 | November |  | 2024-11-21 | 2024-12-05 | 2024-12-10 | 2024-12-13 | 2025-01-04
20 | December |  | 2024-12-19 | 2025-01-02 | 2025-01-07 | 2025-01-10 | 2025-02-01
21 | January | 2025 | 2025-01-23 | 2025-02-06 | 2025-02-11 | 2025-02-14 | 2025-03-08
22 | February |  | 2025-02-20 | 2025-03-06 | 2025-03-11 | 2025-03-14 | 2025-04-05
23 | March |  | 2025-03-20 | 2025-04-03 | 2025-04-08 | 2025-04-11 | 2025-05-03
24 | April |  | 2025-04-17 | 2025-05-01 | 2025-05-06 | 2025-05-09 | 2025-05-31
25 | May |  | 2025-05-22 | 2025-06-05 | 2025-06-10 | 2025-06-13 | 2025-07-05
26 | June |  | 2025-06-19 | 2025-07-03 | 2025-07-08 | 2025-07-11 | 2025-08-02
27 | July |  | 2025-07-24 | 2025-08-07 | 2025-08-12 | 2025-08-15 | 2025-09-06
28 | August |  | 2025-08-21 | 2025-09-04 | 2025-09-09 | 2025-09-12 | 2025-10-04
29 | September |  | 2025-09-18 | 2025-10-02 | 2025-10-07 | 2025-10-10 | 2025-11-01
30 | October |  | 2025-10-23 | 2025-11-06 | 2025-11-11 | 2025-11-14 | 2025-12-06
31 | November |  | 2025-11-20 | 2025-12-04 | 2025-12-09 | 2025-12-12 | 2026-01-03
32 | December |  | 2025-12-18 | 2026-01-01 | 2026-01-06 | 2026-01-09 | 2026-01-31
33 | January | 2026 | 2026-01-22 | 2026-02-05 | 2026-02-10 | 2026-02-13 | 2026-03-07
34 | February |  | 2026-02-19 | 2026-03-05 | 2026-03-10 | 2026-03-13 | 2026-04-04
35 | March |  | 2026-03-19 | 2026-04-02 | 2026-04-07 | 2026-04-10 | 2026-05-02
36 | April |  | 2026-04-23 | 2026-05-07 | 2026-05-12 | 2026-05-15 | 2026-06-06
37 | May |  | 2026-05-21 | 2026-06-04 | 2026-06-09 | 2026-06-12 | 2026-07-04
38 | June |  | 2026-06-18 | 2026-07-02 | 2026-07-07 | 2026-07-10 | 2026-08-01
39 | July |  | 2026-07-23 | 2026-08-06 | 2026-08-11 | 2026-08-14 | 2026-09-05
40 | August |  | 2026-08-20 | 2026-09-03 | 2026-09-08 | 2026-09-11 | 2026-10-03
41 | September |  | 2026-09-17 | 2026-10-01 | 2026-10-06 | 2026-10-09 | 2026-10-31
42 | October |  | 2026-10-22 | 2026-11-05 | 2026-11-10 | 2026-11-13 | 2026-12-05
43 | November |  | 2026-11-19 | 2026-12-03 | 2026-12-08 | 2026-12-11 | 2027-01-02
44 | December |  | 2026-12-24 | 2027-01-07 | 2027-01-12 | 2027-01-15 | 2027-02-06
45 | January | 2027 | 2027-01-21 | 2027-02-04 | 2027-02-09 | 2027-02-12 | 2027-03-06
46 | February |  | 2027-02-18 | 2027-03-04 | 2027-03-09 | 2027-03-12 | 2027-04-03
47 | March |  | 2027-03-18 | 2027-04-01 | 2027-04-06 | 2027-04-09 | 2027-05-01
48 | April |  | 2027-04-22 | 2027-05-06 | 2027-05-11 | 2027-05-14 | 2027-06-05
49 | May |  | 2027-05-20 | 2027-06-03 | 2027-06-08 | 2027-06-11 | 2027-07-03
50 | June |  | 2027-06-17 | 2027-07-01 | 2027-07-06 | 2027-07-09 | 2027-07-31
51 | July |  | 2027-07-22 | 2027-08-05 | 2027-08-10 | 2027-08-13 | 2027-09-04
52 | August |  | 2027-08-19 | 2027-09-02 | 2027-09-07 | 2027-09-10 | 2027-10-02
53 | September |  | 2027-09-23 | 2027-10-07 | 2027-10-12 | 2027-10-15 | 2027-11-06
54 | October |  | 2027-10-21 | 2027-11-04 | 2027-11-09 | 2027-11-12 | 2027-12-04
55 | November |  | 2027-11-18 | 2027-12-02 | 2027-12-07 | 2027-12-10 | 2028-01-01
56 | December |  | 2027-12-23 | 2028-01-06 | 2028-01-11 | 2028-01-14 | 2028-02-05
57 | January | 2028
58 | February
Notes: | Applications to be issued to G&T in one batch on valuation date.
G&T, MoL and CM certificate date is the latest date.
Formulas:
G&T & Museum Sign Certificate = [Trade Contractor Application]+14
Construction Managers Certificate = [Trade Contractor Application]+19
Trade Contractor Invoice = [Trade Contractor Application]+22
Final Date for Payment = [Trade Contractor Application]+44

## Dec 23
Valuation Schedule
Mth in which Works carried out | T/C Application Date | Interim Valuation Date last Thursday | Due Date | Interim Certificate (Payment notice) | 8 | Trade contractor invoice | Final Date for Payment to T/C | Final MC Date For Payment | Difference
| -14 days from Due Date | -7 days from Due Date | day 0 | 5 days from Due Date |  | 8 days from Due date | 30 days from Due date
| -14 | -7 | 0 | 5 |  | 8 | 30
2023-05-01 | 2023-05-18 | 2023-05-25 | 2023-06-01 | 2023-06-06 |  | 2023-06-09 | 2023-07-01 | 2020-11-02 | 971
2023-06-01 | 2023-06-22 | 2023-06-29 | 2023-07-06 | 2023-07-11 |  | 2023-07-14 | 2023-08-05 | 2020-11-30 | 978
2023-07-01 | 2023-07-20 | 2023-07-27 | 2023-08-03 | 2023-08-08 |  | 2023-08-11 | 2023-09-02 | 2021-01-04 | 971
2023-08-01 | 2023-08-24 | 2023-08-31 | 2023-09-07 | 2023-09-12 |  | 2023-09-15 | 2023-10-07 | 2021-02-01 | 978
2023-09-01 | 2023-09-21 | 2023-09-28 | 2023-10-05 | 2023-10-10 |  | 2023-10-13 | 2023-11-04 | 2021-03-01 | 978
2023-10-01 | 2023-10-19 | 2023-10-26 | 2023-11-02 | 2023-11-07 |  | 2023-11-10 | 2023-12-02 | 2021-03-29 | 978
2023-11-01 | 2023-11-23 | 2023-11-30 | 2023-12-07 | 2023-12-12 |  | 2023-12-15 | 2024-01-06 | 2021-05-04 | 977
Nov 23 Advanced | 2023-11-23 | 2023-11-30 | 2023-12-07 | 2023-12-07 |  | 2023-12-12 | 2024-01-06
2023-12-01 | 2023-12-21 | 2023-12-28 | 2024-01-04 | 2024-01-09 |  | 2024-01-12 | 2024-02-03 | 2021-06-01 | 977
2024-01-01 | 2024-01-18 | 2024-01-25 | 2024-02-01 | 2024-02-06 |  | 2024-02-09 | 2024-03-02 | 2021-07-05 | 971
2024-02-01 | 2024-02-22 | 2024-02-29 | 2024-03-07 | 2024-03-12 |  | 2024-03-15 | 2024-04-06 | 2021-08-02 | 978
2024-03-01 | 2024-03-21 | 2024-03-28 | 2024-04-04 | 2024-04-09 |  | 2024-04-12 | 2024-05-04 | 2021-08-30 | 978
2024-04-01 | 2024-04-18 | 2024-04-25 | 2024-05-02 | 2024-05-07 |  | 2024-05-10 | 2024-06-01 | 2021-10-04 | 971
2024-05-01 | 2024-05-23 | 2024-05-30 | 2024-06-06 | 2024-06-11 |  | 2024-06-14 | 2024-07-06 | 2021-11-01 | 978
2024-06-01 | 2024-06-20 | 2024-06-27 | 2024-07-04 | 2024-07-09 |  | 2024-07-12 | 2024-08-03 | 2021-11-29 | 978
2024-07-01 | 2024-07-18 | 2024-07-25 | 2024-08-01 | 2024-08-06 |  | 2024-08-09 | 2024-08-31 | 2022-01-03 | 971
2024-08-01 | 2024-08-22 | 2024-08-29 | 2024-09-05 | 2024-09-10 |  | 2024-09-13 | 2024-10-05 | 2022-01-31 | 978
2024-09-01 | 2024-09-19 | 2024-09-26 | 2024-10-03 | 2024-10-08 |  | 2024-10-11 | 2024-11-02 | 2022-03-07 | 971
2024-10-01 | 2024-10-24 | 2024-10-31 | 2024-11-07 | 2024-11-12 |  | 2024-11-15 | 2024-12-07 | 2022-04-04 | 978
2024-11-01 | 2024-11-21 | 2024-11-28 | 2024-12-05 | 2024-12-10 |  | 2024-12-13 | 2025-01-04 | 2022-05-02 | 978
2024-12-01 | 2024-12-19 | 2024-12-26 | 2025-01-02 | 2025-01-07 |  | 2025-01-10 | 2025-02-01 | 2022-05-31 | 977
2025-01-01 | 2025-01-23 | 2025-01-30 | 2025-02-06 | 2025-02-11 |  | 2025-02-14 | 2025-03-08 | 2022-07-04 | 978
2025-02-01 | 2025-02-20 | 2025-02-27 | 2025-03-06 | 2025-03-11 |  | 2025-03-14 | 2025-04-05 | 2022-08-01 | 978
2025-03-01 | 2025-03-20 | 2025-03-27 | 2025-04-03 | 2025-04-08 |  | 2025-04-11 | 2025-05-03 | 2022-08-26 | 981
2025-04-01 | 2025-04-17 | 2025-04-24 | 2025-05-01 | 2025-05-06 |  | 2025-05-09 | 2025-05-31 | 2022-10-03 | 971
2025-05-01 | 2025-05-22 | 2025-05-29 | 2025-06-05 | 2025-06-10 |  | 2025-06-13 | 2025-07-05 | 2022-10-31 | 978
2025-06-01 | 2025-06-19 | 2025-06-26 | 2025-07-03 | 2025-07-08 |  | 2025-07-11 | 2025-08-02 | 2022-12-09 | 967
2025-07-01 | 2025-07-24 | 2025-07-31 | 2025-08-07 | 2025-08-12 |  | 2025-08-15 | 2025-09-06
2025-08-01 | 2025-08-21 | 2025-08-28 | 2025-09-04 | 2025-09-09 |  | 2025-09-12 | 2025-10-04
2025-09-01 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-07 |  | 2025-10-10 | 2025-11-01
2025-10-01 | 2025-10-23 | 2025-10-30 | 2025-11-06 | 2025-11-11 |  | 2025-11-14 | 2025-12-06
2025-11-01 | 2025-11-20 | 2025-11-27 | 2025-12-04 | 2025-12-09 |  | 2025-12-12 | 2026-01-03
2025-12-01 | 2025-12-18 | 2025-12-25 | 2026-01-01 | 2026-01-06 |  | 2026-01-09 | 2026-01-31
2026-01-01 | 2026-01-22 | 2026-01-29 | 2026-02-05 | 2026-02-10 |  | 2026-02-13 | 2026-03-07
2026-02-01 | 2026-02-19 | 2026-02-26 | 2026-03-05 | 2026-03-10 |  | 2026-03-13 | 2026-04-04
2026-03-01 | 2026-03-19 | 2026-03-26 | 2026-04-02 | 2026-04-07 |  | 2026-04-10 | 2026-05-02
2026-04-01 | 2026-04-23 | 2026-04-30 | 2026-05-07 | 2026-05-12 |  | 2026-05-15 | 2026-06-06
2026-05-01 | 2026-05-21 | 2026-05-28 | 2026-06-04 | 2026-06-09 |  | 2026-06-12 | 2026-07-04
2026-06-01 | 2026-06-18 | 2026-06-25 | 2026-07-02 | 2026-07-07 |  | 2026-07-10 | 2026-08-01
2026-07-01 | 2026-07-23 | 2026-07-30 | 2026-08-06 | 2026-08-11 |  | 2026-08-14 | 2026-09-05
2026-08-01 | 2026-08-20 | 2026-08-27 | 2026-09-03 | 2026-09-08 |  | 2026-09-11 | 2026-10-03
2026-09-01 | 2026-09-17 | 2026-09-24 | 2026-10-01 | 2026-10-06 |  | 2026-10-09 | 2026-10-31
2026-10-01 | 2026-10-22 | 2026-10-29 | 2026-11-05 | 2026-11-10 |  | 2026-11-13 | 2026-12-05
2026-11-01 | 2026-11-19 | 2026-11-26 | 2026-12-03 | 2026-12-08 |  | 2026-12-11 | 2027-01-02
2026-12-01 | 2026-12-24 | 2026-12-31 | 2027-01-07 | 2027-01-12 |  | 2027-01-15 | 2027-02-06
2027-01-01 | 2027-01-21 | 2027-01-28 | 2027-02-04 | 2027-02-09 |  | 2027-02-12 | 2027-03-06
2027-02-01 | 2027-02-18 | 2027-02-25 | 2027-03-04 | 2027-03-09 |  | 2027-03-12 | 2027-04-03
2027-03-01 | 2027-03-18 | 2027-03-25 | 2027-04-01 | 2027-04-06 |  | 2027-04-09 | 2027-05-01
2027-04-01 | 2027-04-22 | 2027-04-29 | 2027-05-06 | 2027-05-11 |  | 2027-05-14 | 2027-06-05
2027-05-01 | 2027-05-20 | 2027-05-27 | 2027-06-03 | 2027-06-08 |  | 2027-06-11 | 2027-07-03
2027-06-01 | 2027-06-17 | 2027-06-24 | 2027-07-01 | 2027-07-06 |  | 2027-07-09 | 2027-07-31
2027-07-01 | 2027-07-22 | 2027-07-29 | 2027-08-05 | 2027-08-10 |  | 2027-08-13 | 2027-09-04
2027-08-01 | 2027-08-19 | 2027-08-26 | 2027-09-02 | 2027-09-07 |  | 2027-09-10 | 2027-10-02
2027-09-01 | 2027-09-23 | 2027-09-30 | 2027-10-07 | 2027-10-12 |  | 2027-10-15 | 2027-11-06
2027-10-01 | 2027-10-21 | 2027-10-28 | 2027-11-04 | 2027-11-09 |  | 2027-11-12 | 2027-12-04
2027-11-01 | 2027-11-18 | 2027-11-25 | 2027-12-02 | 2027-12-07 |  | 2027-12-10 | 2028-01-01
2027-12-01 | 2027-12-23 | 2027-12-30 | 2028-01-06 | 2028-01-11 |  | 2028-01-14 | 2028-02-05
Dec 23 Advanced | 2023-12-15 | 2023-12-21 | 2024-01-04 | 2024-01-09 |  | 2024-01-12 | 2024-02-03
Key Action |  | SRM valuations complete and issued to G&T/MoL |  | Date -1 day G&T Issue recommendation. Date: SRM issue to trades |  | SRM Issue Invoice pack to MoL
Formulas:
T/C Application Date = [Interim Valuation Date last Thursday]-7
Due Date = [Interim Valuation Date last Thursday]+7
Interim Certificate (Payment notice) = [Due Date]+5
Trade contractor invoice = [Due Date]+8
Final Date for Payment to T/C = [Due Date]+30
Interim Valuation Date last Thursday = DATE(YEAR([Mth in which Works carried out]),MONTH([Mth in which Works carried out])+1,1)-WEEKDAY(DATE(YEAR([Mth in which Works carried out]),MONTH([Mth in which Works carried out])+1,3))