Becker (Sliding Partitions) Ltd

Wemco House

477 Whippendell Rd

Watford

Herts

WD18 7QY							18th February 2005

Dear Sirs,

# Re: East London Lift – Barking Rd

We enclose herewith our Order No. 16347 to supply & fix 1 No sliding, folding partition at the above.

Please refer to section j) of this order for your health & safety obligations, in addition please forward all relevant COSSH information, method statements and risk assessments to site, for the attention of Mr M O’Regan, before you commence work.

We trust this is self-explanatory but, should you have any queries, please contact the undersigned.

Yours faithfully,

S C Thorpe

cc  R C Hayhoe

M O’Brien

MOR

IW

Becker (Sliding Partitions) Ltd

Wemco House

477 Whippendell Rd

Watford

Herts WD18 7QY	                                                              18th February 2005

Order No. 16347

To supply & fix a sliding, folding partition, on a labour, plant & material basis, in accordance with the documentation listed below (copies of which are attached):-

- Our enquiry e-mail dated  11.11.04 and documentation detailed therein

- Beckers quotation CTP/sc/17905 dated 15.11.04

- Our e mail dated 18.11.04

- Beckers e-mail dated 19.11.04

For the sum of £3,626.00 plus £504.00 = £4,130.00

Please note the following:-

a)	Your price is fixed for the duration of the works

b)	Terms: Monthly

c)	Discount: Nett

d)	Retention will be held at 5%. One half will be released at practical completion and the balance at the end of the defects liability period

e)	Daywork will only be used as the basis for valuing variations where agreed rates/sums are not applicable and where they cannot be accurately pro-rata’d. In these instances sheets must be offered for signature within 7 days of the works being carried out.

f)	Programme:-   First Fix mid March 2005

Second Fix early May 2005

g)	Attendances to be as attached schedule

h)	Our Project Manager will forward a full set of current information. Your           products are to be manufactured to these details in preference to those issued at Tender Stage.

- 1 -				cont/…

i)	All labour is to be employed fully in accordance with Government employment legislation

i)	All labour is to be CSCS qualified.

j)	Works are to be undertaken fully in accordance with all relevant Health & Safety Regulations including the provision of all necessary PPE for our operatives. It is a condition of this order that the attached Health & Safety questionnaire is completed to the satisfaction of our Director in charge of safety.

k)	Requests for Information must be in writing and should be addressed to our Project Manager

l)	Should any terms and conditions within your quotation contradict the terms of this order, this order will take precedence

m)	You are to provide the following by return:-

- O & M Manual data

- All relevant fire & acoustic certificates

Please note that payments may be withheld until we are in receipt of these

n)	The Project address is:-

Raphael Contracting Ltd

c/o Balfour Beatty Construction Ltd

Site Office

169 Barking Road

London

E16

Project Manager	Mr M O’Regan

Mobile No.		07973 675110