## Sheet1
BAM - BROADGATE TOWER
PROCUREMENT SCHEDULE | All sums exclude Tower Stacker |  |  |  |  | 04/06/202
Trade | Supplier | Order | Tender | Supplier | Profit/Loss | Comments
|  | Placed | Allowance | Quote
Timber doorsets | EDSi |  | 182911.03 | 114528.34 | 68382.69
Ironmongery | John Planck |  | 99000 | 99000 | 0 | Approx allowances, updated quote to be obtained from John Planck
Composite Joinery | Quest |  | 822114.12 | 622712.79 | 199401.33
"Joinery" panelling WF-25, WF-27, WF-28, WF-29 | T T Gillard |  | 85281.48 | 87094.4 | -1812.92
WF-23 Feature wall panelling | T T Gillard |  | 432611 | 432611 | 0
Samples / Mock ups - Generally | Quest / T T Gillard |  | 41537 | ???
Samples / Mock ups - Level 3 Joinery | Quest |  |  |  |  | RCL to work within £17,500.00 CRI
WF-12 wall panelling | Duncan Reeds |  |  |  |  | Now Omitted
CF-09 ceilings | LSA |  |  |  |  | Now Omitted
CF-12 ceilings to L01 & L02 | LSA |  | 107837.8 |  |  | Stand alone quote for CF-12 to be obtained *
WF-30 wall panelling & CF-15 ceilings | LSA |  | 30480.88 | 28593.13 | 1887.75 | WF-30 L03 - CF-15 Ground
WF-31, WF-32, WF-44 wall panelling | Resonics |  | 82298.18 | 82298.18 | 0 | Buiidability issues !?
WF-36 wall panelling | Resonics |  | included | included | included | Part of joinery by Quest ?
WF-34 wall panelling | Buxkin (made possible) |  | included | included | included | Part of joinery by Quest ?
WF-35 & WF-38 wall panelling L03 pods | Baux / Relay design |  | 25497.8 | 25497.8 | 0 | at current exchange rate. Buiidability issues !?
Drawings for Resonics, Baux & LSA panelling | ???
WT-17 folding partition incl WF-36 fabric | Style partions |  | 19364.73 | 16825 | 2539.73
Bespoke Angled Balustrade | Littlehampton Welding |  | 129665 | 129665 | 0
Curtain Railing (J0.3.02) | Waverley |  | 3385.64 | 3385.64 |  | RCL to work within £4,375.00 CRI
FM Kitchen | Howdens |  |  |  |  | RCL to work within £8,750.00 CRI
Horizontal shutter to L3 Garden bar | UK roller shutters |  | 11023.84 | 11023.84 | 0
Skirting | The Timber Group |  | 23462.22 | 14204.77 | 9257.45
|  |  | 2096470.72 |  | 279656.03