## Sheet1
BAM - CANNON STREET
PROCUREMENT SCHEDULE | [8 empty] | 26.01.22
Trade | Supplier | Start | Delivery | Order by | Order | Tender | Supplier | Profit/Loss | Comments
|  | Date (w/c) | Period |  | Placed | Allowance | Quote
Flush doors | Shadbolt |  |  |  | 29.07.20 | 70101.31 | 70101.31 | 0 | Clear finished American Black Walnut. Shadcore cores
Metal cladding to doors DG.02, .03 & .42 | JMS |  |  |  | 28.01.21 | 8262.75 | 12535.27 | -4272.52 | Plugged rate at RCL risk. JMS to supply?
Door frames | JMS |  |  |  | 28.01.21 | 48550.76 | 49960.5 | -1409.74 | Reduced from 44mm thick to 32mm at RCL risk
Ironmongery | Elite |  |  |  | 30.04.20 | 86418.8 | 86418.8 | 0
Washroom system and wall panelling | Formwise |  |  |  | 23.02.21 | 278810 | 273775 | 5035 | Oak. BoQ item 98 not by JMS
Shower cubicles | Formwise |  |  |  | 23.02.21 | 37000 | 36075 | 925 | Oak
Lockers & Benches | Formwise |  |  |  | 23.02.21 | 100174.06 | 78394.88 | 21779.18 | Excludes "ironing board lockers"
MDF Skirtings | JMS |  |  |  | 28.01.21 | 664.5 | 664.5 | 0
Hardwood skirtings to new build stairs | JMS |  |  |  | 28.01.21 | 4985 | 4985 | 0 | Priced as walnut, specification to be confirmed
Flush skirtings to café | JMS |  |  |  | 28.01.21 | 498.5 | 498.5 | 0 | Priced as walnut, specification to be confirmed
Window boards | JMS |  |  |  | 28.01.21 | 687.57 | 687.57 | 0
Reception desk | JMS |  |  |  | 28.01.21 | 34277.39 | 34277.39 | 0
Fluted urinal wall panels | JMS |  |  |  | 28.01.21 | 34540.9 | 34540.9 | 0 | Oak
Changing room & WC mirror units & mirrors | JMS |  |  |  | 28.01.21 | 186499.07 | 186499.07 | 0
Vanity units | JMS |  |  |  | 28.01.21 | 246687.71 | 246687.71 | 0 | Oak
Urinal screens | Formwise |  |  |  | 23.02.21 | 6930 | 6930 | 0 | VE'd specification NOT by JMS
Changing room towel units | JMS |  |  |  | 28.01.21 | 29886.65 | 29021.31 | 865.34 | VE'd at RCL risk. Has it been taken?
Shower benches | JMS |  |  |  | 28.01.21 | 14784.33 | 14784.33 | 0
Reception mirror | JMS |  |  |  | 28.01.21 | 9016.34 | 9016.34 | 0
Stair 3 wall panelling | JMS |  |  |  | 28.01.21 | 4285.04 | 7755.48 | -3470.44 | Revised spec at RCL risk.
Reception bench seating | JMS |  |  |  | 28.01.21 | 15701.37 | 15701.37 | 0
Reception planters, benches & ledges | JMS |  |  |  | 28.01.21 | 14199.46 | 14199.46 | 0
Reception divider unit | JMS |  |  |  | 28.01.21 | 13010.62 | 13010.62 | 0
Reception high table | JMS |  |  |  | 28.01.21 | 10585.64 | 10585.64 | 0
Café window ledges | JMS |  |  |  | 28.01.21 |  |  |  | Omitted
Café counters | JMS |  |  |  | 28.01.21 |  |  |  | Omitted
Changing rooms accessible cistern top | JMS |  |  |  | 28.01.21 | 235.45 | 235.45 | 0
Shower screens | C P Hart |  |  |  |  | 12450.36 | 11574.75 | 875.61
Coat hooks | 3v |  |  |  |  | 2888.6 | 2888.6 | 0 | By Elite?
Soap dispensers | Dolphin |  |  |  |  | 10051.66 | 15058.8 | -5007.14 | Manual not infra red. Incorrect VE saving advised
Paper towel dispensers | Dolphin |  |  |  |  | 11675.4 | 11675.4 | 0
Doc M rails | 3v |  |  |  |  | 9825.6 | 9825.6 | 0 | By Elite?
Single toilet roll holder | Waterbury |  |  |  |  | 3093.64 | 3093.64 | 0
Spare toilet roll holder | Waterbury |  |  |  |  | 2994.85 | 2994.85 | 0
Toilet brush holder | Waterbury |  |  |  |  | 4405.5 | 4405.5 | 0
WC lobby panelling | JMS |  |  |  | 28.01.21 | 2848.04 | 6621.47 | -3773.43 | RCL risk
11546.86