## Sheet1
MCL - HOXTON HOTEL
PROCUREMENT SCHEDULE | [9 empty] | 09.07.22
Profit/Loss
Trade | Supplier | Start | Delivery | Order by | Order | Tender | Supplier |  |  | Comments
|  | Date (w/c) | Period |  | Placed | Allowance | Quote
Timber doors | Fields |  |  |  | 01.12.21 | 82930.6 | 82930.6 | 0 | } | We are making a margin of £5,020.36 but this needs to cover the costs for double handling, additional deliveries etc resulting from fixing the mouldings at Chessington
}
Guestroom WC doors | SDC |  |  |  | 01.12.21 | 24174 | 24174 | 0 | }
}
Bedroom & WC mouldings | Promould & JMS |  |  |  | Site order | 6370.56 | 6370.56 | 0 | }
Timber door frames | JMS |  |  |  | 06.05.22 | 194991.5 | 198970.92 | -3979.42
Riser doorsets | Selo |  |  |  | 08.12.21 | 110396.57 | 110396.57 | 0
Metal doorset | Ascot |  |  |  | 23.06.22 | 2727.27 | 4760 | -2032.73 |  | Site order
Ironmongery | I Innovations |  |  |  | 17.03.22 | 41716.9 | 31468.75 | 10248.15
Acrovyn | Acrovyn |  |  |  |  | 10579.2
Shower screens | Mega glass |  |  |  | 09.03.22 | 62130.29 | 62130.29 | 0 |  | Supply only, RCL to fix
Vanity units | JMS |  |  |  | 06.05.22 | 115886.22 | 118251.24 | -2365.02
Skirting | JMS |  |  |  | 06.05.22 | 14189.78 | 14479.37 | -289.59
Window boards | JMS |  |  |  | 06.05.22 | 3721.78 | 3797.73 | -75.95
Handrails | JMS |  |  |  | 06.05.22 | 6690.25 | 6826.79 | -136.54
Luggage store equipment | Big Dug |  |  |  | 15.06.22 | 680 | 1004.08 | -324.08 |  | Site order
Vanity units | Amwell |  |  |  | 07.04.22 | 1853.23 | 1853.23 | 0
BoH cubicles | Formwise |  |  |  | 13.05.22 | 3575 | 3575 | 0 |  | Site order
BoH lockers & benches | Equip4work |  |  |  | 17.06.22 | 3024 | 4191 | -1167 |  | Site order
Sanitary fittings etc | Various |  |  |  |  | 47382.42
Kitchenette | ??? |  |  |  |  | 0
-122.18