## Sheet1
OSBORNE - ST PAULS SCHOOL PHASE 2
PROCUREMENT SCHEDULE | ALL SUMS EXCLUDE THE FIXED PRICE ADJUSTMENT | [7 empty] | 18.12.19
Trade | Supplier | Start | Delivery | Order by | Order | Tender | Supplier | Profit/Loss | Comments
|  | Date (w/c) | Period |  | Placed | Allowance | Quote
Doors | Shadbolt |  |  |  | 18.03.19 | 91547.38 | 91547.38 | 0
Frames | JMS |  |  |  | 12.04.19 | 49880.18 | 49880.18 | 0
Ironmongery | Allgood |  |  |  | 27.03.19 | 36725.07 | 36725.07 | 0
Mdf window linings | JMS |  |  |  | 12.04.19 | 6636.72 | 6636.72 | 0
Oak window linings | JMS |  |  |  | 12.04.19 | 1107.72 | 1107.72 | 0
Mdf skirtings | JMS |  |  |  | 12.04.19 | 1491.84 | 1491.84 | 0
Oak skirtings | JMS |  |  |  | 12.04.19 | 8086.9 | 8086.9 | 0
Oak batten wall cladding | JMS |  |  |  | 12.04.19 | 62594.58 | 62594.58 | 0
Slotted laminate panelling | JMS |  |  |  | 12.04.19 | 24592.62 | 24592.62 | 0
Valchromat panelling | JMS |  |  |  | 12.04.19 | 44332.74 | 44332.74 | 0
Oak veneered panelling | JMS |  |  |  | 12.04.19 | 71999.96 | 71999.96 | 0
Mirrors | JMS |  |  |  | 12.04.19 | 2906.16 | 2906.16 | 0
Shelving | JMS |  |  |  | 12.04.19 | 12393.57 | 12393.57 | 0
Staff room pigeon holes | JMS |  |  |  | 12.04.19 | 20266.22 | 20266.22 | 0
Kitchens | JMS |  |  |  | 12.04.19 | 54777.76 | 54777.76 | 0
Project room & ICT work benches | JMS |  |  |  | 12.04.19 | 11904.91 | 11904.91 | 0
Classroom storage units | JMS |  |  |  | 12.04.19 | 54050 | 54050 | 0
Bag storage units | JMS |  |  |  | 12.04.19 | 15338.85 | 15338.85 | 0
Pinboards | JMS |  |  |  | 12.04.19 | 24490.62 | 24490.62 | 0
Spur shelving | JMS |  |  |  | 12.04.19 | 4371.75 | 4371.75 | 0
Meeting room & Montgomery cupboards | JMS |  |  |  | 12.04.19 | 12091.9 | 12091.9 | 0
Secular Hall balcony seating | JMS |  |  |  | 12.04.19 | 22991.15 | 12091.9 | 0
Signage | Elite |  |  |  |  | 8437.61 | 8437.61 | 0
Sanitary fittings | Lovair |  |  |  |  | 12464.01 | 12464.01 | 0
Roof access hatch | Surespan |  |  |  |  | 5183.75 | 5183.75 | 0
0