## Sheet1
ISG - SUMMIT HOUSE
PROCUREMENT | [8 empty] | 24.09.14
Trade | Supplier | Start | Delivery | Order by | Order | Tender | Supplier | Profit/Loss | Comments
|  | Date (w/c) | Period |  | Placed | Allowance | Quote
Timber doors | Shadbolt |  |  |  | 30.01.14 | TBA | 34719.21 | 0
Primed frames | JMS |  |  |  | 19.12.13 | 18260.94 | 18260.94 | 0
Metal doorsets | IRMR |  |  |  |  | 9686.47 | 9686.47 | 0 | Addendum 32. 27.01.14.
Ironmongery | Franchi |  |  |  | 21.10.13 | 47548.27 | 45170.86 | 2377.41
Primed mdf skirtings | JMS |  |  |  | 19.12.13 | 959 | 959 | 0
Primed mdf strings | JMS |  |  |  | 19.12.13 |  |  | 0
Stainless steel skirting | JMS |  |  |  | 19.12.13 | 275 | 275 | 0
Primed window boards | JMS |  |  |  | 19.12.13 | 1809 | 1809 | 0
Mastic | ?????? | [6 empty] | 0
Vanity units/walls | JMS |  |  |  | 19.12.13 | 77060 | 77060 | 0
Double cupboard cabinets | JMS |  |  |  | 19.12.13 | 3680 | 3680 | 0
Shelf units to "niche" | ?????? | [6 empty] | 0 | P Sum
Glass screens/dividers | Formwise | [6 empty] | 0
Benches | Formwise |  |  |  |  | 1000 | 990 | 10
Lockers | Formwise |  |  |  |  | 10125 | 8100 | 2025
Stand alone mirrors | JMS |  |  |  | 19.12.13 | 617 | 617 | 0
Sanitary fittings & Doc M's | Various | [6 empty] | 0
Veneered wall panelling | JMS |  |  |  | 19.12.13 | 2500 | 2500 | 0
Reception desk | JMS |  |  |  | 19.12.13 | TBA | TBA | 0 | P Sum
Free standing furniture 1 - 4 | JMS |  |  |  | 19.12.13 | TBA | TBA | 0
Kitchenettes | JMS |  |  |  | 19.12.13 | TBA | TBA | 0
East Cabinets levels 1 - 4 | JMS |  |  |  | 19.12.13 | TBA | TBA | 0 | P Sum
Bar level 5 | JMS |  |  |  | 19.12.13 | TBA | TBA | 0 | P Sum
Store level 5 | JMS |  |  |  | 19.12.13 | 676 | 676 | 0
Library units level 6 | JMS |  |  |  | 19.12.13 | TBA | TBA | 0 | P Sum
Storage units level 6 | JMS |  |  |  | 19.12.13 | TBA | TBA | 0 | P Sum
Open space units level 6 | JMS |  |  |  | 19.12.13 | TBA | TBA | 0 | P Sum
Sanitary fittings & Doc M's | Various | [6 empty] | 0
4412.41

## Sheet2
Summit House
Scope
Item Ref | Element
1 | Generally
1.01 | Factory paint finished door leafs including wc partition doors
1.02 | Primed frames
1.03 | Primed mdf skirtings
1.04 | Primed mdf strings
1.05 | Stainless steel skirting behind reception desk
1.06 | Primed window boards
1.07 | Mastic
1.08 | Plywood infill to support insulation drawing 1002
2 | Washrooms
2.01 | Grd Floor Disabled WC & Shower
2.011 | Sanitary fittings including coat hooks & bins
2.012 | Doc M rails
2.013 | Face fixed mirror
2.02 | Cyclists Showers
2.021 | Bench units
2.022 | Glass lockers
2.023 | Shelf units to "niche"
2.024 | Glass shower screens
2.025 | Vanity unit including mirror
2.026 | Sanitary fittings including coat hooks & bins
2.03 | Ground floor unisex toilet
2.031 | Vanity unit including mirror & bin
2.032 | Sanitary fittings including coat hooks
2.04 | West side male and female Levels 1 - 5
2.041 | Double cupboard cabinet (laquered 18mm MDF)
2.042 | Vanity walls including corian sinks
2.043 | Glass screen to side of basin
2.044 | Sanitary fittings including coat hooks & bins
2.05 | East side Male & Female Levels 1 - 4
2.051 | Vanity walls including corian sinks
2.052 | Glass screen to side of basin
2.053 | Sanitary fittings including coat hooks & bins
2.054 | Ambulant grab rails
2.055 | Glass urinal dividers
2.06 | Disabled WC Levels 1 - 4
2.061 | Sanitary fittings including coat hooks & bins
2.062 | Doc M rails
2.063 | Face fixed mirror
2.07 | East side Male & Female Level 5
2.071 | Vanity walls including corian sinks
2.072 | Sanitary fittings including coat hooks & bins
2.08 | West side Level 6
2.081 | Vanity walls including corian top
2.082 | Glass partition
2.083 | Sanitary fittings including coat hooks & bins
2.09 | East side Level 6
2.091 | Vanity walls including corian top
2.092 | Veneered wall panelling
2.093 | Glass screen to side of basin
2.094 | Sanitary fittings including coat hooks & bins
3 | Offices
3.01 | Reception desk
3.02 | Free standing furniture elements type A1/A2 levels 1 - 4
3.03 | Free standing furniture elements type B1/B2/B3 levels 1 - 4
3.04 | Free standing furniture element type C1 levels 1 - 4
3.05 | Kitchenettes including taps and sinks Levels Grd - 4 & 6
3.06 | East Cabinets levels 1 - 4
3.07 | Bar level 5
3.08 | Library units level 6
3.09 | Storage units level 6
3.1 | Open space units level 6
Contractual/Financial
Date | Correspondence
31/05/12 | Original tender with letter & pricing notes, £967,014.16. Prelims based upon 16 weeks
27/03/13 | RCL most recent query response schedule issued. Not commented upon or agreed by ISG
10/04/13 | RCL schedule of clarifications issued. Not commented upon or agreed by ISG
28/06/13 | Final pricing schedule issued. Prelims figure as original tender