## Sheet1
BB - WILLIAM TYNDALE SCHOOL
PROCUREMENT SCHEDULE | [8 empty] | 10.02.2011
Phase 1
Trade | Supplier | Start | Delivery | Order by | Order | Tender | Supplier | Profit/Loss | Comments
|  | Date (w/c) | Period |  | Placed | Allowance | Quote
Doors/Frames/Screens/Windows | JMS | 07.02.11 |  |  |  | 60023.09 |  | 0 | Frames & Screens delivered
Ironmongery | Gatcliff | 14.02.11 |  |  | 09.02.11 | ??? | 11790.57 | 0 | £15,000.00 Provisional Sum S & Fix
Duct panelling | Bushboard | 14.02.11 |  |  | 09.02.11 | 17379.93 | 17379.93 | 0 | Marked up at 15%
Skirting | RCL | Complete |  |  |  | 619.78 |  | 0 | Sheets of MDF being ripped down
Window Boards | RCL | 14.02.11 |  |  |  | 277.65 |  | 0 | Sheets of MDF being ripped down
Reception Desk | JMS | N/A | [6 empty] | £6,000.00 Provisional Sum S & Fix
Whiterock | AWFC | Complete |  |  |  |  | 24148.34 |  | Marked up at 12.5%. Order No provided 13.01.11. Order Value to be checked
0