## Sheet1
SRM - WOKING MOCK UP
PROCUREMENT SCHEDULE | [8 empty] | 29.07.19
Trade | Supplier | Start | Delivery | Order by | Order | Tender | Supplier | Profit/Loss | Comments
|  | Date (w/c) | Period |  | Placed | Allowance | Quote
Carcassing timber and I beams | Brewers |  |  |  | 09.04.18 | 8298.97 | 5557.42 | 2741.55
Doors | Shadbolt |  |  |  | 16.04.18 | 1690.87 | 1158.41 | 532.46
Frames | JMS |  |  |  | 16.04.18 | 1792.72 | 1792.72 | 0
Selo doorset | Selo |  |  |  | 19.04.18 | 1000 | 877.2 | 122.8
Ironmongery | 3v |  |  |  | 19.04.18 | 449.9 | 449.9 | 0
Access control | Salto |  |  |  | 23.04.18 | 301.24 | 301.24 | 0
Skirtings | JMS |  |  |  | 16.04.18 | 90.29 | 90.29 | 0
Wardrobe | JMS |  |  |  | 16.04.18 | 5293.46 | 5293.46 | 0
Headboard | JMS |  |  |  | 16.04.18 | 2043.93 | 2043.93 | 0
Bathroom shelf unit | JMS |  |  |  | 16.04.18 | 696.9 | 696.9 | 0
Temporary doorsets | RCL |  |  |  | 27.04.18 | 500 | 125.85 | 374.15
Dry lining & suspended ceilings | SIF |  |  |  | 19.04.18 | 19383 | 19383 | 0
Wall and floor tiling & thresholds | D Briggs |  |  |  | 18.04.18 | 3469.95 | 3469.95 | 0 | Revised spec to be costed
Vinyl wall covering | RCL |  |  |  |  | 1500
Painting & fix only vinyl wall covering | Hazelmere |  |  |  | 08.05.18 | 2400 | 2400 | 0
Electrics | Network |  |  |  | 19.04.18 | 8347.03 | 8347.03 | 0
Pumbing | Opus Aqua |  |  |  | 19.04.18 | 8727.97 | 8727.97 | 0
Fan coil unit | SRM |  |  |  |  | 758 |  |  | Omitted from RCL scope
Ductwork | Opus Aqua? |  |  |  |  | 742
Mastic | RCL |  |  |  |  | 350
Bedroom glazed screen | JMS/MJ |  |  |  |  | 1000 |  |  | Addendum 001 to JMS 19/4/18
Final clean | ??? |  |  |  |  | 500
Sanitary fittings | Waterbury |  |  |  |  | 182.81 | 0 | 182.81 | FOC. Being delivered w/c 07.05.18
Shower Screen | Roman |  |  |  |  | 621.88
Carpet Laying | Abbotsbury |  |  |  | 02.05.18 | 300 | 210 | 90
Coat hooks | JMS |  |  |  | 16.04.18 | 248.87 | 248.87 | 0
4043.77