## Sheet1
SRM - WOKING - RED CAR PARK AND PUBLIC WC'S
PROCUREMENT SCHEDULE | [8 empty] | 12.07.22
Trade | Supplier | Start | Delivery | Order by | Order | Tender | Supplier | Profit/Loss | Comments
|  | Date (w/c) | Period |  | Placed | Allowance | Quote
Doors | Shadbolt |  |  |  | 18.06.21 | 71844.81 | 71844.81 | 0 | Only issued internally for now
Frames | JMS |  |  |  | 24.06.21 | 32845.67 | 32845.67 | 0
Ironmongery | Elite |  |  |  | 28.04.21 | 43488.4 | 41313.98 | 2174.42 | "Normbau" option
WC cubicles | Formwise |  |  |  | 13.08.21 | 30000 | 30000 | 0 | "Greenlam" option
Duct panelling | Formwise |  |  |  | 13.08.21 | 24400 | 24400 | 0 | "Greenlam" option
Urinal dividers | Formwise |  |  |  | 13.08.21 | 1120 | 1120 | 0
Vanity units | JMS |  |  |  | 12.08.21 | 42019 | 41543.39 | 475.61 | "Greenlam" option
Mirrors | JMS |  |  |  | 12.08.21 | 9259.96 | 5070.91 | 4189.05
"Changing Place" equipment | Astor Bannerman |  |  |  | 14.05.21 | 8957 | 8957 | 0 | Revision A issued 30.06.21
Sanitary fittings | Various |  |  |  |  | 30727.32 | 30727.32 | 0 | Site order have been placed
Wall protection | Gradus |  |  |  | 28.06.21 | 98731.56 | 98178.95 | 552.61
Wall protection delivery | Gradus |  |  |  | 28.06.21 | 0 | 1490 | -1490
Aluminium chequer plate | Gradus |  |  |  | 28.06.21 | 29822.74 | 11698.53 | 18124.21
Cut plate to size | JMS |  |  |  | 07.07.21 | 0 | 1816.61 | -1816.61
Stratum skirting | Volante |  |  |  |  | 1346.8 | 5783.05 | -4436.25 | Site order have been placed
Forkguard protection | Asafe |  |  |  | 04.02.22 | 13113.78 | 13113.78 | 0
Pipe protectors | [5 empty] | 1260 |  |  | Omitted
17773.04