## Sheet1
25 Cannon Street
Tender Query Schedule
WP15 Carpentry & Joinery - Raphael Contracting Ltd
Section A - to be completed by person requesting clarification |  |  |  | Section B - to be completed by person providing clarification | Section B - to be completed by person providing clarification
Item No. | Raised By | Date Raised | Clarification Description | Clarification Response 29.10.19 | Clarification Response 11.11.19
Covering Letter
1 | BAM |  | Item 2 - The documents that your tender is to be based on is as per the Data Enquiry Sheet which was appended to the tender documents. Within the drawing section, folder 48, we have included a mark-up set of drawings which provides clarity on the exact scope. The remaining drawings are there for you to review for any potential impact on your works. | Noted but we would like to discuss this further as part of the post bid meeting | Refer previous comment (29.10.19)
2 | BAM |  | Item 4 - Please confirm the level of protection that you have included for. Please note that your works will remain the full responsibility of yourselves until fully handed over and signed off. In addition, we will require you to return at completion to remove and dispose of all of your protection. | We have allowed for the same levels of protection as we provide on all Bam projects. Comments re "fully handed over and signed off" and "remove and dispose" noted and agreed | Refer previous comment (29.10.19)
3 | BAM |  | Item 5 - We will provide 110v power supply to central locations around the project. You will be required to provide any leads necessary to ensure power source adjacent to your works, bearing in mind the majority of your tools will be battery powered. | Noted & closed out
4 | BAM |  | Item 6 - Bam confirm that a hoist will be located within Watling St for the vertical distribution of your materials. Please refer to the durations included within the Appendix B for when the hoist is available. When the hoist is dismantled, please note that we will have a BBU arrangement for the Goods Lift; please refer to the Appendix B for dates. Also included within the Appendix B are the dimensions and capacity of both the hoist and the goods lift. | Noted & closed out
5 | BAM |  | Item 6 - In addition to the above, please note that BAM will provide an external scaffold and a birdcage within the double height reception only. All other internal access, irrespective of height, is to be by you. | Noted but we would like to discuss the scaffolding for the stair 3 panelling further as part of the post bid meeting | Refer previous comment (29.10.19)
6 | BAM |  | Item 7 - We confirm that Bam will provide an Easting, a Northing and a Datum per floor. All other setting out is to be by yourselves. | Noted & closed out
7 | BAM |  | Item 8 - Please note that site hours are 8.00am to 6.00pm, Monday to Friday. This is the site hours that your programme of works are to be based on. | We note that these are the site ours are 8.00am to 6.00pm, but our working hours would be 8.00am to 5.30pm | Refer previous comment (29.10.19)
8 | BAM |  | Item 8 - With regards to noisy works, please note that you will be restricted by the City of London Code of Practice for Construction site which is included within our standard tender documents. Please confirm you will work in accordance with this document where applicable to the scope of your works. | Confirmed and closed out
9 | BAM |  | Item 8 - With regards to return visits, please confirm that your prelims and programme of works is in accordance with the sequence and return visits as identified by the Appendix B included within the tender documents. | Confirmed and closed out
10 | BAM |  | Item 11 - Please note that retention will be held at 3%, with half being released at main contract PC and the remaining half upon completion of the making good defects period. | Noted & closed out
11 | BAM |  | Item 12 - Please refer to the Appendix B for the programme of works. Please confirm you are fully compliant with this document. | Confirmed and closed out
12 | BAM |  | Item 13 - Please note that your tender is to be fully lump sum and not subject to remeasurement based upon the tender documentation issued. | We have not as yet checked the quantities within the pricing schedule but we are quite happy to do this, advise upon any anomolies found, and then commit to a lump sum bid | We have amended the quantities to BoQ items 119, 120 & 121. We would like to discuss the skirtings, window boards & stair string scope in more detail as part of the post bid meeting. Otherwise we are happy with the quantities that we have priced. Please note that there are benches that appear on the EOT series drawings that do not appear to be included within the pricing schedule ie Male Change around the isolated column and Female Change 2 nr penninsular benches projecting out from the lockers, should these be included?
13 | BAM |  | Item 13 - In addition to the above, please provide details of the items you would wish to discuss further. | We would welcome the oppurtunity of discussing these as part of a post bid meeting | We will provide a set of project specific pricing notes prior to the post-bid meeting
14 | BAM |  | Item 13 - With regards to mock-ups, please confirm that you have allowed for the provision of samples and mock-ups as detailed within the tender documents. As a minimum we would expect a toiler area to be fully constructed and completed to act as a benchmark for the remaining areas. | We have allowed for samples and, provided time allows, the construction of a benchmark area in advance of the main bulk of the works. Please note however that the benchmark we have allowed for would be for quality purposes only, should it result in the scope being revisited we would expect to be reimbursed for all costs incurred | Refer previous comment (29.10.19)
15 | BAM |  | Item 14 - Please confirm that your tender is based on the specified supplier for veneered toilet cubicles as detailed within the K32 specification. | Our tender is based upon the specified veneer supplier ie Oberflex but the veneer will be procured directly from Oberflex not via Shadbolt, we will be able to expand upon the reasons for this at the post bid meeting | Refer previous comment (29.10.19)
16 | BAM |  | Item 15 - Bam will provide office accommodation for you during the works as part of a shared open plan office environment. You will however be required to supply your own furniture and equipment as required. With regards to a store, we will provide space for you to provide your own store for. | Noted & closed out
17 | BAM |  | Item 17 - With regards to VE, can you please provide us with a full schedule of proposals for VE together with firm cost allowances should the client choose to deviate from the original specification. | We have approached our supply chain for firm costs for the suggested V E we will forward these once we receive a response | Particleboard door core in lieu of laminboard a saving of approx £25k. Alternative ironmongery supplier approx £30k.
18 | BAM |  | Item 18 - Please note that the level of daywork rates isn't acceptable, and should your quotation be of interest we would wish to discuss firm rates with you. | Noted, we would suggest that the rates are as those agreed for Sebastian Street with an appropriate allowance for any pay awards since they were agreed | Refer previous comment (29.10.19)
19 | BAM |  | Item 19 - We confirm that any subcontract order will not be issued to you until circa March / April 2020, therefore please confirm that your tender will remain open for acceptance through until beyond this approximate duration. | Confirmed and closed out
20 | BAM |  | Item 19 - Please note that we require your quotation to be fixed priced through until December 2021. Please confirm acceptance of this. | Given the current vaguries with regard to Brexit and the looming General Election it would be extremely difficult to commit to a fixed price through to December 2021 but we would welcome the oppurtunity of discussing this further as part of a post bid meeting | Refer previous comment (29.10.19)
Measured Works
21 | BAM |  | Can you please provide a breakdown of your preliminaries | Please refer to the attached | Refer previous comment (29.10.19)
22 | BAM |  | Can you please confirm if you have included for return visits for the ground floor window cill North elevation | Please refer to item 8 above, if this element is identified seperately within Appendix then yes we have | Refer previous comment (29.10.19)
23 | BAM |  | Item 21&24 - Can you please confirm if you have inlcuded for solid timber batten to back painted glass as dwg WC_40 detail 4 | There would not appear to be a solid timber batten to the back painted glass on this detail but we can discuss this further as part of a post bid meeting | Refer previous comment (29.10.19)
24 | BAM |  | Item 25&27 - In reference to the fluted timber panels to urinal walls can you please confirm what specification you have based your price on. The rate you have used seems to be high compared to your competitors. Please can you review your rates. | The fluted timber panels are described as being veneered however this would not produce the effect that is shown on the sketch that was issued in response to our Tender RFI's we have therefore enhanced the specification so as to produce the desired effect. We have raised the query with our supply chain and will advise upon the exact specification once we receive a response | We attach a copy of 1069-SK-238 which shows that the flutes are 10mm deep on a backing board, this cannot be achieved with a veneered panel, we have allowed for 28mm thick solid walnut without the backing board
25 | BAM |  | Item 47,49,51,53,55 & 57 - In reference to the bespoke mirror unit can you please confirm what specification you have based your price on. The rate you have used seems to be high compared to your competitors. Please can you review your rates. | We have raised the query with our supply chain and will advise upon the exact specification once we receive a response | We have priced the metalwork to the mirror units exactly as drawn which is a very expensive detail, perhaps our competitors have allowed for a simpler design. However we have noticed that Shadbolt had based their quotation for the veneered components within the joinery fitments generally upon a matt lacquered Oberflex veneer whereas the specification is for "unfinished", Shadbolt have since corrected this error and we have reduced the relevant sums within our pricing schedule, please see attached. Please note however that we would have serious reservations with regard to the suitability of "unfinished" veneered components
26 | BAM |  | Item 65,69,73&78 - Can you please confirm what specification you have based your price on. | We have raised the query with our supply chain and will advise upon the exact specification once we receive a response | Hafele 502.94.000 recessed bins
27 | BAM |  | Item 100 - Can you please include for integrated solid timber bench to lockers in the EOT changing areas within your bid | Maxwood, the specified supplier for these benches have declined to price, we have therefore approached our own supply chain and will respond in due course | Please refer to the attached updated pricing schedule, please be aware that the walnut slats for these benches may not match the oberflex veneer specified for other joinery elements. Please note that there are other benches that appear on the EOT series drawings that do not appear to be included within the pricing schedule ie Male Change around the isolated column and Female Change 2 nr penninsular benches projecting out from the lockers, should these be included?
28 | BAM |  | Item 105&106 - Can you please include for full height locker with intergrated fold down ironing board unit within your bid | Maxwood, the specified supplier for these benches have declined to price, we have therefore approached our own supply chain and will respond in due course | Please refer to the attached updated pricing schedule
29 | BAM |  | Item 107 - Can you please include for the heavy duty hanging clothes/garment rail to the EOT drying room within your bid | Please provide drawings as to what is required | Refer previous comment (29.10.19)
30 | BAM |  | Item 112&116 - Can you please confirm what specification you have based your price on. | We have raised the query with our supply chain and will advise upon the exact specification once we receive a response | Hafele 502.94.000 recessed bins
31 | BAM |  | In reference to your total price for doors and ironmongery, the rates you have used seem to be higher then your competitors. Can you please review your rates. | Shadbolt the specified door manufacturer did not originally allow for the specified Oberflex veneer, and did not correct this error until 23.10.19, this correction was made at our request and, as far as we are aware, we are the only trade contractor that has received the correct quotation from Shadbolt | Shadbolt had based their quotation upon a matt lacquered Oberflex veneer whereas the specification is for "unfinished", Shadbolt have since corrected this error and we have amended the doors sum within our pricing schedule, please see attached. Please note however that we would have serious reservations with regard to the suitability of "unfinished" veneered components
32 | BAM |  | Item 162 - Can you please include the automatic opeining vent within your allowance for the smoke extract doors | We would normally expect these to be supplied and fixed as part of the M & E package however if you could please supply a specification for these we will try to obtail a quotation | Refer previous comment (29.10.19)
33 | BAM |  | Item 163&164 - Can you please include the metal cladding bonded to door with bronze satin stainless finish within your allowance for the Reception lift lobby doors | These doors are fire rated, the application of these applied finishes would almost certainly mean that a fire certificate could not be provided but we would welcome the oppurtunity of discussing this further as part of a post bid meeting | The panelling matches that to adjacent walls, which is to be by others, we would therefore assume that the matching panelling to the doors would be by the same contractor. We nust also reiterate our previous comments (29.10.19)
34 | BAM |  | Item 165 - Can you please include the profile plaster wall panel, over panel, granite tiles and bronze reveals within your allowance for the concealed Recpetion door. | There is a real risk that the application of these applied finishes would, over time, cause the door to distort. We would usually expect that the profile plaster panels and granite tiles would be by others but we would welcome the oppurtunity of discussing this further as part of a post bid meeting | Please add £6,213.71 to our quote for the bronze elements . We must however reiterate our previous comments (29.10.19)
35 | BAM |  | Item 168 - Can you please provide an E.O for the timber clad access hatch adjacent to platform lift overrun within your bid | As we understand it this hatch is external but we would welcome the oppurtunity of discussing this further as part of a post bid meeting | The panelling to Stair 3 is to a semi-external / external environment, we have priced BoQ item 167 as specified / drawn but veneer is not a suitable material in these conditions. We can discuss suitable alternatives at the post bid meeting and reprice on this basis, we will then be able to also price the cladding of the hatch referred to within BoQ item 168
36 | BAM |  | Item 169 - Can you please confirm if you have included for all hardwood timber skirting to new build stair floors to all floors and to Café area | No, apologies, we will address this as part of item 13 above | Please refer to item 012 above
37 | BAM |  | Item 185&186 - Can you please include for the Granite bench and ledge to the Reception Area within your bid. | Please provide drawings as to what is required and a specification | Refer previous comment (29.10.19)
38 | BAM |  | Additonal Items - Can you please include for a full fit out including sink and adjustable shelving to the cleaners cupboard | Please provide drawings as to what is required and a specification | Refer previous comment (29.10.19)
39 | BAM |  | Additonal items - Can you please include an allowance for mock ups as per the BGY mock up schdule within your bid | Please refer to item 13 above | Refer previous comment (29.10.19)
40 | BAM |  | Additonal items - Can you please include an allowance for 2nr filtered water tap & chiller unit as per EOT_40 | Please provide drawings as to what is required and a specification | Refer previous comment (29.10.19)
41 | BAM |  | Can you please include for fixed price for the duration of the contract works. | Given the current vaguries with regard to Brexit and the looming General Election it would be extremely difficult to commit to a fixed price through to December 2021 but we would welcome the oppurtunity of discussing this further as part of a post bid meeting | Refer previous comment (29.10.19)
42 | BAM |  | Can you please confirm what protection strategy you have allowed for. Can you please confirm if you have included for in situ correx protection to all panelling, bespoke joinery and WC cubicles. | Please refer to item 4 above | Refer previous comment (29.10.19)
alinea Consulting Tender Queries
43 | alinea |  | Please confirm your tender sum is a fixed price for the duration of the works | Given the current vaguries with regard to Brexit and the looming General Election it would be extremely difficult to commit to a fixed price through to December 2021 but we would welcome the oppurtunity of discussing this further as part of a post bid meeting | Refer previous comment (29.10.19)
44 | alinea |  | Please provide suggestions in respect of Veneer panels in respect reducing cost. | We have approached our supply chain for firm costs for the suggested V E we will forward these once we receive a response | Please refer to item 035 above, hopefully the design solution for the semi-external environment will result in savings against the veneered panelling
45 | alinea |  | Concealed paper towel dispenser- please provide VE suggestions in respect of this. Equal and approved. | In our experience the specified product is a cost effective solution | Refer previous comment (29.10.19)
46 | alinea |  | Dolphin inra red dispenser- please provide cost saving opps in respect of this. Equal and approved. Please also provide option for non- infra red | Please provide a specification for an equal and approved infra red dispenser. We have approached our supply chain for a non - infra red option and will forward the saving once we receive a response | Please provide a specification for an equal and approved infra red dispenser. The saving for a dolphin non - infra red option is £222.47 each
47 | alinea |  | Urinal dividing screens- Please provide VE suggestions in respect of this. Contractor suggestion appreciated. | We will provide suggestions as part of the post bid meeting and following this provide cost advice for solutions that will be considered | We can offer a saving of £708.00 each for Solid Grade Laminate dividers or £503.00 each for laminated glass dividers with a bronze painted interlayer
48 | alinea |  | Hair dryer unit/ straighteners- should these be excluded? | We would welcome the oppurtunity of discussing this further as part of a post bid meeting | Refer previous comment
47 | alinea |  | Toilet brushes, roll holders and spares- please provide contractor alternative for these works | We will provide suggestions as part of the post bid meeting and following this provide cost advice for solutions that will be considered | We have looked into this further and the specified products would appear to be cost effective solutions
50 | alinea |  | Timber cladding to External terrace stair- please confirm- this is aligned with design Spec? Please also provide suggestions for cost savings for Equal and approved products/ systems. | We would welcome the oppurtunity of discussing these further as part of a post bid meeting | Please refer to item 035 above, hopefully the design solution for the semi-external environment will result in savings against the veneered panelling