## Sheet1
25 Cannon Street
Tender Query Schedule
WP15 Carpentry & Joinery - Raphael
Section A - to be completed by person requesting clarification |  |  |  | Section B - to be completed by person providing clarification
Item No. | Raised By | Date Raised | Clarification Description | Clarification Response
Prelims
1 | BAM | 2019-11-15 | Can you please confirm you have included for all site staff in order to complete the required works. | Confirmed
2 | BAM | 2019-11-15 | Can you please confirm if you have included for any access scaffold for the scope of works | We have not allowed for access scaffolding for the stair 3 wall panelling, we note that as previously advised Bam will be providing a birdcage scaffold to the double height reception
3 | BAM | 2019-11-15 | Can you please confirm what protection you have allowed for? Can you please confirm what is included in the protection for all BAM projects. | All finished joinery will be fixed as late on as possible in the programme so as to reduce the risk of damage. Door frames in high traffic areas will have proprietary jamb protectors. Door leaf faces will be protected with Corec fixed with Low Tac tape. Joinery fitments will have corner protectors, corex to vertical faces and sheet material to horizontal surfaces.
Measured Works
4 | BAM | 2019-11-15 | Item 185 &186 Granite bench/ledge - These items are to be the same as the Reception bench seating already priced [excluding the upholstered cushion] (item 173). Please refer to the attached Reception bench seating mark up and specification N10 [FF-05] for details. Can you please include this within your bid. | To follow
5 | BAM | 2019-11-15 | Item 177 Internal cladding support system to Reception walls - We now require the cladding support system for the plaster wall panels to hang on. Please refer to attached cladding support system mark up and specification K13/135. Can you please price this as a stand alone item. | Please see attached amended pricing schedule which now allows for these works. We have allowed for a developed design based upon locally packed timber support work NOT helping hand brackets. Split battens and bronze channels to be by the cladding contractor. We have not allowed for any structural engineer calcs, our proposal and the completed installation will need to be signed off by the cladding contractor, once this has occured we will not be able to accept any defects within the panelling installation. We are unsure as to the meaning of "a stand alone item" we could only carry out these works if they formed part of the complete carpentry & joinery package (their will be no reduction in prelims if they do not)
6 | BAM | 2019-11-15 | Can you please provide a stand alone price for the following internal glazed screen to the café area. Please refer to the attached WP16 glazed screen folder which contains the marked up scope of work drawings/specification and pricing schedule. | We have sent the enquiry to six trade contractors, including the specified company. Two have declined directly and Bam have advised that the specified company have previously declined. There has not been sufficient time for the other three to review the enquiry but we are hopeful that we will receive at least one or two quotes however we have been advised that we will not receive these for up to two weeks
7 | BAM | 2019-11-15 | Can you please provide a install only cost for the metal mesh curtain. Can you please provide a cost for the drop rod and unistrut head fixing for the curtain track fixed to the concrete soffit. Please refer to mesh curtain folder which contains marked up scope drawings and specification. | As per email from Bam 18.11.19 (CW) this in now to be priced supply & fix. RCL have verbally raised queries with regard to the suppliers quotation provided by Bam
8 | BAM | 2019-11-15 | Item 107 heavy duty hanging clothes/ garment rail - Can you please propose a product and clarify a solution for this item | We will propose a solution but before we san we will need to fully understand the Design Team's expectations, perhaps we can discuss this at the post bid meeting
9 | BAM | 2019-11-15 | In reference to the Benches in the EOT series drawings, the benches around the isolated column and 2nr peninsular benches in the female changing room are incorporated in the measure of 34m. Please note these items are to be included in your fully lump sum bid. | Please see attached amended pricing schedule which now allows for these benches
10 | BAM | 2019-11-15 | Item 117 & 118 - Can you please confirm if you have included for 2nr bespoke below sink units as per drawing EOT 04. | Confirmed
11 | BAM | 2019-11-15 | Item 163&164 - These fire rated doors to the lift lobby are under review. Can you please provide a price for the bronze SS finish. Is this the £6,213.71 sum provided in the post tender queries. | The panelling matches that to adjacent walls, which is to be by others, we would therefore assume that the matching panelling to the doors would be by the same contractor. The £6,213.71 is for the bronze elements of item 165
12 | BAM | 2019-11-15 | Item 169 SK-04 hardwood timber skirting to stairs - Can you please amend your quotation to 500m | Please see attached amended pricing schedule items 169 & 170. Please note that we originally priced these as clear finished american walnut, they are now priced as primed polar for on site decoration by others. As previously advised we would like to run through the skirtings and stair strings quote with you as part of the post bid meeting
13 | BAM | 2019-11-15 | Item 181 - Can you please propose a solution for fitting out the cleaners cupboard. The cupboard is to include a sink and adjustable shelving | We will propose a solution but before we can we will need to fully understand the Design Team's expectations, perhaps we can discuss this at the post bid meeting
14 | BAM | 2019-11-15 | Item 184 - In reference to the filtered water tap & chiller unit please refer to item no 25 SA-37 in the Sanitaryware schedule for details. | To follow
15 | BAM | 2019-11-15 | Can you please include a firm allowance for the bins and bin flaps to the male and female changing room towel units | Please forward detail drawings / specification to enable us to do this
16 | BAM | 2019-11-15 | Please refer to BGY drawing 1069_CO-31. Can you please confirm you have included for the Timber veneer panelling within your lump sum bid | We have NOT allowed for this panelling which is specified as Oberflex Brut D'Ober, given our concerns re this "unfinished" product we would suggest postponing providing a quotation until after the post bid meeting
17 | BAM | 2019-11-18 | Can you please confirm if you have included for the removal and subsequant reinstatement of all ironmongery for the doors that are to be painted. | The door leafs are factory painted off site so there will be no need to remove ironmongery, we have not allowed to remove and refix ironmongery to primed frames
18 | BAM | 2019-11-18 | Can you please confirm as part of your protection measure we would request that you hang the doors initial to ensure they fit, then subsequently re-move, store in coffins on site and subsequently re-hang ready for completion. Please confirm if this is included. | Frames are delivered in advance of the frames and fixed. Doors are only delivered immediately before they need to be fixed and are hung immediately. There is therefore no need to remove doors, put them in coffins and refix them. This is the proceedure that we have previously adopted on Bam projects
19 | BAM | 2019-11-18 | In additon to the item above, can you please confirm if you have included for the protection for pre-finished frames. | We have allowed for proprietary jamb protectors to pre finished walnut frames in high traffic areas
20 | BAM | 2019-11-18 | In reference to the panelling to stair 3 timber is to be Kebony as discussed in the post tender meeting. Can you please include for this in your revised bid | Please provide detail drawings, including timber section sizes, setting out etc and a specification for the Kebony panelling
21 | BAM | 2019-11-18 | With regards to the back painted glass to male WC's, can you please confirm that you have included for detail 4 within your lump sum return | The panelling may not be manufactured and fixed exactly as detail 4 but the appearance, performance and functionality will be the same.