## Sheet1
25 Cannon Street
Tender Query Schedule
WP15 Carpentry & Joinery - Raphael
Section A - to be completed by person requesting clarification |  |  |  | Section B - to be completed by person providing clarification
Item No. | Raised By | Date Raised | Clarification Description | Clarification Response
Prelims
1 | BAM | 2019-11-15 | Can you please confirm you have included for all site staff in order to complete the required works.
2 | BAM | 2019-11-15 | Can you please confirm if you have included for any access scaffold for the scope of works
3 | BAM | 2019-11-15 | Can you please confirm what protection you have allowed for? Can you please confirm what is included in the protection for all BAM projects.
Measured Works
4 | BAM | 2019-11-15 | Item 185 &186 Granite bench/ledge - These items are to be the same as the Reception bench seating already priced [excluding the upholstered cushion] (item 173). Please refer to the attached Reception bench seating mark up and specification N10 [FF-05] for details. Can you please include this within your bid.
5 | BAM | 2019-11-15 | Item 177 Internal cladding support system to Reception walls - We now require the cladding support system for the plaster wall panels to hang on. Please refer to attached cladding support system mark up and specification K13/135. Can you please price this as a stand alone item.
6 | BAM | 2019-11-15 | Can you please provide a stand alone price for the following internal glazed screen to the café area. Please refer to the attached WP16 glazed screen folder which contains the marked up scope of work drawings/specification and pricing schedule.
7 | BAM | 2019-11-15 | Can you please provide a install only cost for the metal mesh curtain. Can you please provide a cost for the drop rod and unistrut head fixing for the curtain track fixed to the concrete soffit. Please refer to mesh curtain folder which contains marked up scope drawings and specification.
8 | BAM | 2019-11-15 | Item 107 heavy duty hanging clothes/ garment rail - Can you please propose a product and clarify a solution for this item
9 | BAM | 2019-11-15 | In reference to the Benches in the EOT series drawings, the benches around the isolated column and 2nr peninsular benches in the female changing room are incorporated in the measure of 34m. Please note these items are to be included in your fully lump sum bid.
10 | BAM | 2019-11-15 | Item 117 & 118 - Can you please confirm if you have included for 2nr bespoke below sink units as per drawing EOT 04.
11 | BAM | 2019-11-15 | Item 163&164 - These fire rated doors to the lift lobby are under review. Can you please provide a price for the bronze SS finish. Is this the £6,213.71 sum provided in the post tender queries.
12 | BAM | 2019-11-15 | Item 169 SK-04 hardwood timber skirting to stairs - Can you please amend your quotation to 500m
13 | BAM | 2019-11-15 | Item 181 - Can you please propose a solution for fitting out the cleaners cupboard. The cupboard is to include a sink and adjustable shelving
14 | BAM | 2019-11-15 | Item 184 - In reference to the filtered water tap & chiller unit please refer to item no 25 SA-37 in the Sanitaryware schedule for details.
15 | BAM | 2019-11-15 | Can you please include a firm allowance for the bins and bin flaps to the male and female changing room towel units
16 | BAM | 2019-11-15 | Please refer to BGY drawing 1069_CO-31. Can you please confirm you have included for the Timber veneer panelling within your lump sum bid