## Sheet1
25 Cannon Street
Tender Query Schedule
WP15 Carpentry & Joinery - VE Schedule
Section A - to be completed by person requesting clarification |  |  |  | Section B - to be completed by person providing clarification
Item No. | Raised By | Date Raised | VE Description | VE Response
Value Engineering Opportunities
Timber Veneer Panels
1 | BAM | 2019-11-14 | You have currently allowed for all veneers to the WC, WC Cubicles and Shower doors to be Oberflex American Walnut, Brut D'Ober as per the specification. Can you please confirm if there is any potential VE saving for using a alternative veneer? | We are awaiting a reponse from our supply chain and will advise upon any savings once we receive feedback
2 | BAM | 2019-11-14 | Omit Class O (Euro Class B) performance specification from WC locations | Currently, because the Oberflex is specified as being unfinished, we have not allowed for WC locations to have Euro Class B performance, we would welcome the oppurtunity of discussing this further as part of the post bid meeting
3 | BAM | 2019-11-14 | Proprietary Veneered Cubicle system in lieu of Bespoke | We have allowed for a proprietary system that closely aligns to BGY's design information and utilises Oberflex veneers.
Fluted Timber Panels
4 | BAM | 2019-11-14 | Fluted timber panels are specified as timber veneer oberflex. Can you please provide a VE option for these to be flat timber veneer panels | Saving for the fluted panels to be unfinished, flat Oberflex veneer. Grd flr 2 nr @ approx £448.00 = £896.00. Levels 1 to 5 30 nr @ approx £165.00 = £4,950.00. Once again however we would need to discuss our concerns over using an unfinished product
Doorsets
5 | BAM | 2019-11-14 | Changing ironmongery supplier from 3V to a equal approved supplier | Alternative ironmongery supplier a saving of approx £30k.
6 | BAM | 2019-11-14 | Face fixed Ironmongery in lieu of flush | The saving for a face fixed closer in lieu of a concealed closer to a non fire rated door is £8.00 each. This increases to £27.00 each and £35.00 each respectively for FD30 & FD60 fire rated doors
7 | BAM | 2019-11-14 | Doors measuring 2700mm to be changed to 2300mm omitting over panel | Saving for omitting overpanels and leaving the door leafs the same height is approx £22k
8 | BAM | 2019-11-14 | Change the Shadmaster door core to a Shadcore core | Duplication of item 009 below
9 | BAM | 2019-11-14 | Particleboard door core in lieu of laminboard door core | Particleboard door core in lieu of laminboard a saving of approx £25k.
Sanitaryware
10 | BAM | 2019-11-14 | Can you please provide VE for an equal approved design of items such as toilet brush holders, toilet roll holders, grab rails etc but from a different supplier | Please see attached, the savings identified are each per fitting
11 | BAM | 2019-11-14 | Can you please provide Vee options for a Dolphin non - infra red option soap dispenser in lieu of a infra red one. | The saving for a dolphin non - infra red option is £222.47 each
Lockers and Benching
12 | BAM | 2019-11-14 | Can you please confirm what supplier and specification you have used for the double height lockers/benching. Can you please provide possible VE if these lockers were obtained from an equal alternative supplier. | We have based our quotation upon the specified supplier, Maxwood's Z lockers
Bespoke Mirror Units
13 | BAM | 2019-11-14 | Opaque illuminated facia in lieu of light with shade to Mirror cabinets
14 | BAM | 2019-11-14 | Powdercoated Bronze in lieu of anodised bronze to Mirror cabinets
15 | BAM | 2019-11-14 | Can you please provide an alternative bespoke mirror solution that provides the same visual intent.
Urinal Divider Units
16 | BAM | 2019-11-14 | Solid Grade Laminate dividers in lieu of profiled timber sub frame wrapped in metal sheeting with bronze finish | We can offer a saving of £708.00 each for Solid Grade Laminate dividers.
17 | BAM | 2019-11-14 | Laminated glass dividers with a bronze painted interlayer in lieu of a profiled timber sub frame wrapped in metal sheeting with bronze finish | We can offer a saving of £503.00 each for for laminated glass dividers with a bronze painted interlayer
Programme
18 | BAM | 2019-11-14 | Is there any opportunity to complete the works in a shorter programme then the 38 weeks in the programme (prelim saving)
Storage / Towel Units
19 | BAM | 2019-11-14 | Can you please provide an alternative bespoke Towel storage solution that provides the same visual intent.