## N D Queries
RAPHAEL CONTRACTING LTD
BAM - 25 Cannon Street
Schedule of Order Queries
Comment
Item | Document | Clause | Ref
1 | Interview meeting minutes | 4.04 & 4.05 | P I Insurance | As discussed at the meeting 05.02.20 P I Insurance is not applicable to this package
2 | Interview meeting minutes | 6.1 | S/Con T's & C's | This clause will only apply once this schedule of order queries has been closed out
3 | Interview meeting minutes | 6.16 & 6.17 | Fixed Price | These clauses require further discussion and may need to be qualified with regard to COVID_19
4 | Interview meeting minutes | 7.01 | Commencement date | This clause requires further discussion and may need to be qualified with regard to COVID_19
5 | Interview meeting minutes | 8.01 | Site working hours | RCL's working ours are Monday to Friday 8:00am to 5:30pm
6 | Interview meeting minutes | 10.01b) | Attendances | We do not appear to have received Sub-Contract Data Sheet item 47
7 | Interview meeting minutes | 10.04 | Office space | We will need space for minimum two desks
8 | Contract Sum Analysis | 169 | Stair 3 panelling | For the avoidance of doubt please amend this description to Kebony
9 | Programme and Restraints | 3.0 | S/Con programme | This clause requires further discussion and may need to be qualified with regard to COVID_19
10 | Programme and Restraints | 4.0(a) | Early site visits | This can only be accomodated where programme allows
11 | Programme and Restraints | 4.0(f)&(g) | Out of sequence working | We have not allowed for any return visits or out of sequence working
12 | Programme and Restraints | 5.0 | Working hours | RCL's working ours are Monday to Friday 8:00am to 5:30pm
13 | Programme and Restraints | 6.0(e) | Working hours | RCL's working ours are Monday to Friday 8:00am to 5:30pm
14 | Programme and Restraints | 9.0(z) | Scaffolding | Please re-word as being the joinery not the mechanical services package. Bam will need to provide a scaffold for the stair 3 panelling
15 | Programme and Restraints | 7 | Final paragraph | We have not allowed for any extra visits
16 | Package Scope | Page 1 | Ground floor Female WC | The full size mirror to the north wall is not on the pricing schedule
17 | Package Scope | Page 2 | Typical Floor Male WC | Bullet points 2 & 3 are a duplication please delete nr 2
18 | Package Scope | Page 3 | Basement EOT Male | Bullet points & 105. Please, for clarity, insert "WC" in front of "Cubicle" (to make it clear they are not shower cubicles)
19 | Package Scope | Page 3 | Basement EOT Female | Bullet points & 105. Please, for clarity, insert "WC" in front of "Cubicle" (to make it clear they are not shower cubicles)
20 | Package Scope | Page 4 | Reception/Lobby | Please add "stonework by others" to bullet point 1
21 | Package Scope | Page 5 | Divider unit | Bullet point 5. Please delete "LED insert" - by others
22 | Package Scope | Page 5 | High table | Please delete bullet point 4 - by others
23 | Package Scope | Page 5 | Bench seat | Bullet point 1. Please delete "on Granite tiles (M40:141)" - by others
24 | Package Scope | Page 5 | Reception desk | Please delete bullet point 6 - by others
25 | Package Scope | 2,3 ,4 & 8 | Compliance with standards and codes | We do not have design responsibility, it is the architects that need to ensure that their drawings and specifications comply with Building Regs, British & European Standards and BREEAM & DDA requirements requirements
26 | Package Scope | 7 | Support structures | Any within dry lined walls is by others (see item 30)
27 | Package Scope | 13 | Cavity closing | Cavity closing is by others, the only fire stopping we have allowed for is intumescent mastic around door frames
28 | Package Scope | 14 | Surveys | This can only be accomodated where programme allows
29 | Package Scope | 15 | Cleaning | "Sparkle" clean is by Bam
30 | Package Scope | 17 | Loadings | This clause would appear not to be applicable to the joinery package
31 | Package Scope | 19 | Drawings | We have not allowed to revise drawings that have been prepared based upon the architects details that are subsequently amended
32 | Package Scope | 20 | Setting out | This clause would appear not to be applicable to the joinery package
33 | Package Scope | 29 | Concrete plinths | This clause would appear not to be applicable to the joinery package
34 | Package Scope | 37 | Attendance | We have not allowed to provide attendance during the air leakage test
35 | Package Scope | Page 8 | Key specifications | Specification L20 should read Rev T2 dated 10/9/19 and N10 rev C1 dated 16/1/20 (as the drwing register - refer item 38 below)
36 | DRM |  |  | Agreed and closed out
37 | Supplementary Conditions |  |  | Please see attached an edited version of the SCC's. We have inserted a tab "Seb St" which contains the agreed SSc's for Bam's Sebastian Street project and have amended in, in blue, the 25 CS SSC's in line with this. We have made furthe project specific amendments in red
38 | Drawing register | All | Bam (CW) email 23.04.20 | Agreed provided a statement is included within the clarifications schedule that where discrpencies exist between the door schedule and other design information the door schedule takes precedence.
39 | Marked up drawings | RE-21 T1 | Reception bench | We appear to have received two versions of this drawing our tender is based upon "Option 1" albeit it contains a statement re joinery carcass in lieu of blockwork which is not allowed for.
40 | Marked up drawings | RE-40 T2 | Reception desk | All electrics, lighting etc by others
41 | Marked up drawings | RE-41 T1 | Divider unit | All electrics, lighting etc by others
42 | Marked up drawings | RE-46 T2 | Reception desk | All electrics, lighting etc by others
43 | Marked up drawings | WC-12 T2 | Grd floor female WC | Mirror to internal elevation AA is not in the pricing schedule
44 | Marked up drawings | WC-20 T1 | Mirror unit | All electrics, lighting etc by others
45 | Marked up drawings | WC-30 T2 | Mirror unit | All electrics, lighting etc by others
46 | RCL tender |  |  | Please see the schedule within the "RCL tender" tab which summarises the clarifications contained within our tender return which do not appear to have been addressed within the numbered documents, these will need to be referenced somewhere within the order

## RCL tender
Bam - 25 Cannon Street
Pricing Notes issued via email 12.11.19
| 1 | Please refer to our response, dated 11.11.19, to the tender query schedule for potential technical issues with regard to:-
d) The application of applied finishes to doors within the reception area
| 2 | Our ironmongery quotation is based upon 3v's schedule ref CT0819-01-T. Electrical items of ironmongery will be free issued to others for them to fix. We have not allowed for access control, FOB release, swipe card access or any other security hardware. The forming of mortices for any floor springs is to be by others.
| 3 | Where required we have allowed to use our door manufacturer’s certified intumescent products, we have not allowed for any specific acoustic ratings. We have allowed, only where necessary to achieve certification, intumescent sealant, we have not allowed for any other mastic. Mastic will not be fair faced.
| 4 | Timber doors may be sourced from a separate company to that which supplies the frames however the whole assembly will be fully compliant in respect of fire certification.
| 5 | We have not allowed to machine for or to supply or fix any air transfer grilles.
| 6 | We have allowed to fix doors and ironmongery once only, the filling of fixing holes to primed door frames is to be by others.
| 7 | We have allowed for overpanels to door types to be the same thickness as the door leafs without a transom, we have not allowed for detail 03 on drawing DD-03.
| 8 | Frames to doors with a painted finish have been priced as being supplied primed for on site decoration by others, we have assumed that the paint finish to the door leafs is RAL 9010.
| 9 | Primed skirtings and widow boards for on site decoration by others will be manufactured from mrmdf and will be fixed using a combination of adhesive, pins and screws, the filling of all fixing holes is to be by others.
| 10 | The plumbing in of sinks and electrical connections to the soap dispensers are by others, all other plumbing goods, electrical equipment and lighting are to be by others
| 11 | The specified manufacturer of the height adjustment equipment has expressed concerns as to whether it is suitable for its intended use
| 12 | We have included PC Sums of £1,660.00 and £2,490.00 respectively for bins and bin flaps to the male and female changing room towel units.
| 13 | We have allowed for the shower benches to have "off the shelf" brackets manufactured by Hegbo.
| 14 | The stonework to the reception benches and planters is to be by others
Tender letter dated 23.10.19
| 10 | All timber products provided by ourselves will be environmentally accredited. Usually this accreditation will be by the FSC, if not it will be by one of the other recognised bodies, e.g. PEFC or CSA.
| 13 | We have not allowed for testing
| 16 | We shall co-operate fully to try to ensure proper co-ordination between ourselves and other trades. However, ultimate responsibility for co-ordination must remain with yourselves.
| 18 | Our current daywork rates are:
Labour RICS = 140%
Materials Cost = 15%
Plant current market hire rate + 15%
Subcons Cost = 15%