## Sheet1
25 Cannon Street
Tender Query Schedule
WP15 Carpentry & Joinery - Raphael Contracting Ltd
Section A - to be completed by person requesting clarification |  |  |  | Section B - to be completed by person providing clarification
Item No. | Raised By | Date Raised | Clarification Description | Clarification Response
Covering Letter
1 | BAM |  | Item 2 - The documents that your tender is to be based on is as per the Data Enquiry Sheet which was appended to the tender documents. Within the drawing section, folder 48, we have included a mark-up set of drawings which provides clarity on the exact scope. The remaining drawings are there for you to review for any potential impact on your works.
2 | BAM |  | Item 4 - Please confirm the level of protection that you have included for. Please note that your works will remain the full responsibility of yourselves until fully handed over and signed off. In addition, we will require you to return at completion to remove and dispose of all of your protection.
3 | BAM |  | Item 5 - We will provide 110v power supply to central locations around the project. You will be required to provide any leads necessary to ensure power source adjacent to your works, bearing in mind the majority of your tools will be battery powered.
4 | BAM |  | Item 6 - Bam confirm that a hoist will be located within Watling St for the vertical distribution of your materials. Please refer to the durations included within the Appendix B for when the hoist is available. When the hoist is dismantled, please note that we will have a BBU arrangement for the Goods Lift; please refer to the Appendix B for dates. Also included within the Appendix B are the dimensions and capacity of both the hoist and the goods lift.
5 | BAM |  | Item 6 - In addition to the above, please note that BAM will provide an external scaffold and a birdcage within the double height reception only. All other internal access, irrespective of height, is to be by you.
6 | BAM |  | Item 7 - We confirm that Bam will provide an Easting, a Northing and a Datum per floor. All other setting out is to be by yourselves.
7 | BAM |  | Item 8 - Please note that site hours are 8.00am to 6.00pm, Monday to Friday. This is the site hours that your programme of works are to be based on.
8 | BAM |  | Item 8 - With regards to noisy works, please note that you will be restricted by the City of London Code of Practice for Construction site which is included within our standard tender documents. Please confirm you will work in accordance with this document where applicable to the scope of your works.
9 | BAM |  | Item 8 - With regards to return visits, please confirm that your prelims and programme of works is in accordance with the sequence and return visits as identified by the Appendix B included within the tender documents.
10 | BAM |  | Item 11 - Please note that retention will be held at 3%, with half being released at main contract PC and the remaining half upon completion of the making good defects period.
11 | BAM |  | Item 12 - Please refer to the Appendix B for the programme of works. Please confirm you are fully compliant with this document.
12 | BAM |  | Item 13 - Please note that your tender is to be fully lump sum and not subject to remeasurement based upon the tender documentation issued.
13 | BAM |  | Item 13 - In addition to the above, please provide details of the items you would wish to discuss further.
14 | BAM |  | Item 13 - With regards to mock-ups, please confirm that you have allowed for the provision of samples and mock-ups as detailed within the tender documents. As a minimum we would expect a toiler area to be fully constructed and completed to act as a benchmark for the remaining areas.
15 | BAM |  | Item 14 - Please confirm that your tender is based on the specified supplier for veneered toilet cubicles as detailed within the K32 specification.
16 | BAM |  | Item 15 - Bam will provide office accommodation for you during the works as part of a shared open plan office environment. You will however be required to supply your own furniture and equipment as required. With regards to a store, we will provide space for you to provide your own store for.
17 | BAM |  | Item 17 - With regards to VE, can you please provide us with a full schedule of proposals for VE together with firm cost allowances should the client choose to deviate from the original specification.
18 | BAM |  | Item 18 - Please note that the level of daywork rates isn't acceptable, and should your quotation be of interest we would wish to discuss firm rates with you.
19 | BAM |  | Item 19 - We confirm that any subcontract order will not be issued to you until circa March / April 2020, therefore please confirm that your tender will remain open for acceptance through until beyond this approximate duration.
20 | BAM |  | Item 19 - Please note that we require your quotation to be fixed priced through until December 2021. Please confirm acceptance of this.
Measured Works
21 | BAM |  | Can you please provide a breakdown of your preliminaries
22 | BAM |  | Can you please confirm if you have included for return visits for the ground floor window cill North elevation
23 | BAM |  | Item 21&24 - Can you please confirm if you have inlcuded for solid timber batten to back painted glass as dwg WC_40 detail 4
24 | BAM |  | Item 25&27 - In reference to the fluted timber panels to urinal walls can you please confirm what specification you have based your price on. The rate you have used seems to be high compared to your competitors. Please can you review your rates.
25 | BAM |  | Item 47,49,51,53,55 & 57 - In reference to the bespoke mirror unit can you please confirm what specification you have based your price on. The rate you have used seems to be high compared to your competitors. Please can you review your rates.
26 | BAM |  | Item 65,69,73&78 - Can you please confirm what specification you have based your price on.
27 | BAM |  | Item 100 - Can you please include for integrated solid timber bench to lockers in the EOT changing areas within your bid
28 | BAM |  | Item 105&106 - Can you please include for full height locker with intergrated fold down ironing board unit within your bid
29 | BAM |  | Item 107 - Can you please include for the heavy duty hanging clothes/garment rail to the EOT drying room within your bid
30 | BAM |  | Item 112&116 - Can you please confirm what specification you have based your price on.
31 | BAM |  | In reference to your total price for doors and ironmongery, the rates you have used seem to be higher then your competitors. Can you please review your rates.
32 | BAM |  | Item 162 - Can you please include the automatic opeining vent within your allowance for the smoke extract doors
33 | BAM |  | Item 163&164 - Can you please include the metal cladding bonded to door with bronze satin stainless finish within your allowance for the Reception lift lobby doors
34 | BAM |  | Item 165 - Can you please include the profile plaster wall panel, over panel, granite tiles and bronze reveals within your allowance for the concealed Recpetion door.
35 | BAM |  | Item 168 - Can you please provide an E.O for the timber clad access hatch adjacent to platform lift overrun within your bid
36 | BAM |  | Item 169 - Can you please confirm if you have included for all hardwood timber skirting to new build stair floors to all floors and to Café area
37 | BAM |  | Item 185&186 - Can you please include for the Granite bench and ledge to the Reception Area within your bid.
38 | BAM |  | Additonal Items - Can you please include for a full fit out including sink and adjustable shelving to the cleaners cupboard
39 | BAM |  | Additonal items - Can you please include an allowance for mock ups as per the BGY mock up schdule within your bid
40 | BAM |  | Additonal items - Can you please include an allowance for 2nr filtered water tap & chiller unit as per EOT_40
41 | BAM |  | Can you please include for fixed price for the duration of the contract works.
42 | BAM |  | Can you please confirm what protection strategy you have allowed for. Can you please confirm if you have included for in situ correx protection to all panelling, bespoke joinery and WC cubicles.
alinea Consulting Tender Queries
43 | alinea |  | Please confirm your tender sum is a fixed price for the duration of the works
44 | alinea |  | Please provide suggestions in respect of Veneer panels in respect reducing cost.
45 | alinea |  | Concealed paper towel dispenser- please provide VE suggestions in respect of this. Equal and approved.
46 | alinea |  | Dolphin inra red dispenser- please provide cost saving opps in respect of this. Equal and approved. Please also provide option for non- infra red
47 | alinea |  | Urinal dividing screens- Please provide VE suggestions in respect of this. Contractor suggestion appreciated.
48 | alinea |  | Hair dryer unit/ straighteners- should these be excluded?
47 | alinea |  | Toilet brushes, roll holders and spares- please provide contractor alternative for these works
50 | alinea |  | Timber cladding to External terrace stair- please confirm- this is aligned with design Spec? Please also provide suggestions for cost savings for Equal and approved products/ systems.