## Minutes
Project name: | 25 CANNON STREET | [5 empty] | Project number: | HLN.0280
Held with: | Raphael Contracting Limited | [5 empty] | Date: | 2020-02-05
Held at: | 25 Cannon Street, London, EC4M 5TA | [5 empty] | Time: | 2:00pm
Works package: | WP15 Carpentry & Joinery
Present |  |  |  |  | Additional circulation
Name |  |  | Company |  | Name |  |  | Company
Section | Summary
Pre-Qual | Pre-Qualification Status
1 | Introduction
2 | BAM Construction Limited Project Details & Correspondence Arrangements
3 | Sub-Contractor Details
4 | Sub-Contractor Insurance Details
5 | Sub-Contractor Organisation & Project Management Structure
6 | Summary of Sub-Contract
7 | Sub-Contract Programme
8 | Site Working Hours & Holidays
9 | Management of Sub-Contract Works
10 | Attendances
11 | Sub-Contract Design Element
12 | Information Management Procedures
13 | Site Dimensions and Tolerances
14 | Quality Procedures
15 | Health and Safety
16 | Environment and Sustainability
17 | Community Engagement
18 | BAM Construction Limited Company Policies & Procedures
19 | Anti-Bribery and Corruption Policy
20 | Any Other Business / Expand on Items Above
Item | Description | [6 empty] | Action by
Pre-Qual | Pre-Qualification Status
P.1 | Constructionline registration number: | [6 empty] | RCL
P.2 | Is the Sub-Contractor Constructionline Gold fully verified status? | [6 empty] | RCL
P.3 | If the response in P.2 is 'No', has the 'Exception Protocol' been followed | [6 empty] | RCL
and approval to use this Sub-Contractor been granted by the Regional
Commercial Director and Supply Chain Manager?
Note: copy of e-mail confirming exception protocol to be appended to the Order
Draft/Recommendation Form/Please Place Sub-Contract Form
P.4 | BAM Construction Limited require all Sub-Contractors to be Constructionline Gold
verified status and to ensure this status is maintained throughout the duration of the
Sub-Contract Works.
1. | Introduction
1.1 | Purpose of meeting
The meeting was held to introduce the Sub-Contractor to BAM's project team and
to review the agreed Sub-Contract documentation and the scope of works prior to the
commencement of works on site.
2. | BAM Construction Limited Project Details & Correspondence Arrangements
2.01 | Full name: | 25 CANNON STREET
2.02 | Address: | 25 Cannon Street, London
2.03 | Post code: | EC4M 5TA
2.04 | Telephone: | tba |  | email: | 25cannonst@bam.co.uk
2.05 | Single point of contact for project: |  |  | Graham Ridge
2.06 | Position: | Project Manager |  | email: | gridge@bam.co.uk
2.07 | QS for Sub-Contractor applications: |  |  | Danny Smith
| Position: | Snr Project Surveyor |  | email: | dsmith@bam.co.uk
2.08 | All correspondence to be sent to the person named in 2.05 with the exception of
2.10 and 2.11 below and notices given under Clause 19 of the Sub-Contract.
Note: Refer also to Section 12 Information Management Procedure.
2.09 | The Electronic Data Management System on this project is: |  |  |  |  | Livelink
2.1 | All design information e.g. drawings, specifications, reports and the like for BAM
Construction Limited to be uploaded and issued via Livelink or any other named
project specific Electronic Data Management System (EDMS) and marked for the
| attention of: | Richard Owen
2.11 | Applications for payment are to be sent via email to the person named in 2.07.
2.12 | In addition to the above all emails are to be copied to the following project email
| address: | 25cannonst@bam.co.uk
3. | Sub-Contractor Details
3.01 | Full name: | Raphael Contracting Limited
3.02 | Address: | Raphael House, 123 Roebuck road, Chessington, Surrey
3.03 | Post code: | KT9 1EU
3.04 | Telephone: |  |  | email: |  |  |  | RCL
3.05 | Company Registration number: |  |  | 03010267
3.06 | VAT Registration number: |  |  | 652792806
3.07 | Unique Tax Reference number: |  |  | 6930530920
3.08 | Date of formation: | [6 empty] | RCL
3.09 | Date of last published accounts: | [6 empty] | RCL
3.10 | Subsidiary of other company Y/N: | [6 empty] | RCL
3.11 | If yes to 3.10 then advise who: | [6 empty] | RCL
4. | Sub-Contractor Insurance Details
|  |  |  | Maximum liability limit |  | Expiry date
4.01 | Employers Liability Insurance: |  |  | 10000000 |  | 2020-03-06
4.02 | Third Party Liability Insurance: | [6 empty] | RCL
4.03 | Product Liability Insurance: |  |  | 5000000 |  | 2020-03-06
4.04 | Professional Indemnity Insurance: |  |  | 5000000 |  | 2020-03-05
4.05 | Confirmation that Professional Indemnity Insurance liability is in respect of each
| claim or series of claims arising out of the same event: |  |  |  |  | Yes
4.06 | If no to item 4.5 then the Sub-Contractor to provide below details of any current
unsettled claims in addition to any settled claims during the past 5 years:
n/a
5. | Sub-Contractor Organisation & Project Management Structure
The Sub-Contractor to list below the names of key organisation and project specific
personnel.
5.01 | Director with overall responsibility for project: | [6 empty] | RCL
5.02 | Frequency of site visits by person named in 5.01: | [6 empty] | RCL
5.03 | Supervisor with overall responsibility for project: | [6 empty] | RCL
5.04 | CV of supervisor named in 5.03: | [6 empty] | RCL
5.05 | Safety Advisor responsible for this project: | [6 empty] | RCL
5.06 | Quantity Surveyor: | [6 empty] | RCL
5.07 | Designer / Design Manager (if applicable): | [6 empty] | RCL
5.08 | Document Controller: | [6 empty] | RCL
5.09 | Planner: | [6 empty] | RCL
6. | Summary of Sub-Contract
6.01 | Brief description of the Main Contract Works:
Refurb of 6 storey plus basement office comprising structural alterations to cores, office floors, roof and basement; structural alterations to the facade including replacing glazing and forming roof terrace; internal fit-out to CAT A
6.02 | Brief description of the Sub-Contract Works:
To execute and complete the following which will form part of the Works to be
| executed under the Main Contract. |  |  | Package: | WP15 Carpentry & Joinery
6.03 | The basis of the Sub-Contract Works:
| Labour, plant and materials: |  |  | Yes
| Labour and plant: |  |  | n/a
| Labour only: |  |  | n/a
6.04 | Status of the Sub-Contract Works: |  |  | Additional Information:
| Design: |  | No
| Full design: |  | No
| Complete the design: |  | No
| Manufacture: |  | Yes | Refer to agreed design release programme
| Procurement: |  | Yes | Refer to agreed design release programme
| Supply: |  | Yes | Refer to agreed design release programme
| Delivery: |  | Yes | Refer to agreed design release programme
| Installation: |  | Yes | In accordnace with agreed method statement
| Testing: |  | Yes | In accordnace with agreed method statement
| Commissioning: |  | Yes | In accordnace with agreed method statement
6.05 | Form of Sub-Contract:
BAM Construction Limited Articles of Agreement and Conditions of Sub-Contract
| Form: 153:37 Revision: |  | 13
6.06 | The Contract Administrator is: Real PM
6.07 | The Contractor's Representative is: Frazer Wardhaugh - Head of Legal
6.08 | The Subcontractor Representative is: | [6 empty] | RCL
6.09 | Sub-Contract Numbered Documents
The 'Sub-Contract Agreement Document Index' was reviewed and both parties
agree that the documents listed and referred to therein, will form part of and be
read and construed as part of the Sub-Contract referred to in 6.05 above.
These minutes will also be added to the list of numbered documents.
6.1 | The Sub-Contractor's Terms and Conditions, qualifications, clarifications, attendances
and the like shall be deleted, being superseded by the agreements recorded within
these meeting minutes.
6.11 | Sub-Contract order value:
6.12 | Order value build up: |  | Refer to Appendix A - Contract Sum Analysis
6.13 | Subject to re-measurement: No, all works lump sum unless items within the Contract Sum Analysis are referred to as Provisional Quantity
6.14 | Discount: | nett
6.15 | Retention: | 3%
6.16 | Fixed price: | Yes
6.17 | Expiration of fixed price: |  | End of 2021
6.18 | Daywork rates have been agreed and are noted in the Sub-Contract Sum Analysis
and Clause 3.3 of the Articles of Agreement or the relevant clause from any other
| Form of Sub-Contract listed in item 6.5 Alternative 2 above. |  |  |  |  | Not Applicable
6.19 | Payment Schedule: |  | Refer to Appendix G
Bonds, Warranties, etc.
6.2 | A Parent Company Guarantee is required in the draft form annexed hereto or included
| within the Sub-Contract Documents: |  |  | Not Required
6.21 | A Performance Bond is required in the draft form annexed hereto or included
| within the Sub-Contract Documents: |  |  | Not Required
6.22 | A Retention Bond is required in the draft form annexed hereto or included
| within the Sub-Contract Documents: |  |  | Not Required
6.23 | The following Sub-Contractor Warranties where required are as follows and shall be in
the draft form annexed hereto or included within the Sub-Contract Documents:
| Purchaser / Tenant Warranty: |  |  | Yes
| Fund Warranty |  |  | n/a
| Employer Warranty |  |  | Yes
| Other Warranties (list below): |  |  | n/a
Please refer to Document ** with the Subcontract Data Sheet for standard wording of the Warranty
Valuations
6.24 | Period: Monthly
6.25 | Dates for applications: Refer to Subcontract Payment Schedule Appendix G
7. | Sub-Contract Programme
Note: durations given are working weeks.
The Sub-Contractor shall submit his proposed programme of the works no later than 2
weeks from receipt of BAM Sub-Contract Order, Letter of Intent or notice of
commencement (whichever is the earliest). The Sub-Contract programme shall be fully
labour resourced, identify periods for design, off site fabrication and critical deliveries
(if any) and incorporate the following:
7.01 | Anticipated commencement date: |  |  |  | 2020-09-21
7.02 | Period on site for carrying out works: |  |  |  | 35 | working week(s)
7.03 | Continuity of specific operation cannot be guaranteed. The Sub-Contractor is to allow
for an adequate number of visits to complete the works, taking into account interfaces
with other trades.
7.04 | State number of visits anticipated: |  |  | In accordance with the agreed and signed Appendix B
7.05 | Specific Lead in periods from receipt of Sub-Contract Agreement:
| Notice to commence works on site: |  |  |  |  | week(s) |  | RCL
| Preparation/production of information/drawings: |  |  |  |  | week(s) |  | RCL
| Information/drawing approval: |  |  |  |  | week(s) |  | RCL
| Materials procurement: |  |  |  |  | week(s) |  | RCL
| Manufacturing: |  |  |  |  | week(s) |  | RCL
| Delivery: |  |  |  |  | week(s) |  | RCL
Further notes:
RCL
7.06 | List samples to be provided:
In accordance with the BGY Mock-up Schdule and 1069_SA drawing series. Raphael to provide a schedule of sign off dates for each sample required.
7.07 | Samples to be provided by: | [6 empty] | RCL
7.08 | Key items of materials and/or plant on long deliveries:
RCL
7.09 | Any special early warning notes (e.g. factory shut downs):
RCL
7.1 | The Sub-Contractor to provide name, address and contact details of any proposed
off-site manufacturing/fabricating facilities.
RCL
8. | Site Working Hours & Holidays
8.01 | Normal site working hours.
|  |  | from | to
| Monday to Friday: |  | 8.00 | 18.00 | Please note that programme to be based on Mon-Fri working only with Saturdays by agreement only.
| Saturday: |  | 8.00 | 13.00
| Sunday: |  | n/a | n/a
8.02 | BAM Construction Limited reserves the right to vary these times without prior notice.
8.03 | Site holiday / shut down periods in addition to statutory bank holidays.
|  | year | from |  | to
| Christmas: | 2020 | 2020-12-24 |  | 2021-01-01 |  | Inclusive
| Easter | 2020 | 2020-04-11 |  | 2020-04-13 |  | Inclusive
| Easter | 2021 | 2021-04-02 |  | 2021-04-05 |  | Inclusive
8.04 | Any hours or days the Sub-Contractor may wish to work outside the above will be by
prior agreement with BAM Construction Limited. The Sub-Contractor may the be liable
for all associated costs arising from operating the site outside of the above times.
8.05 | Sub-Contractor's holiday / shut down periods in addition to statutory bank holidays.
|  | year | from |  | to
| Christmas: | 2020 |  |  |  |  | Inclusive | RCL
| Easter | 2021 |  |  |  |  | Inclusive | RCL
| Easter | 2021 |  |  |  |  | Inclusive | RCL
Working Restrictions
8.06 | Noise: Strictly in accordance with the City of London Code of Practice for Deconstruction and Construction Sites; 9th Edition dated January 2019.
8.07 | Traffic: Strictly in accordance with the City of London Code of Practice for Deconstruction and Construction Sites; 9th Edition dated January 2019.
8.08 | Weekend: Strictly in accordance with the City of London Code of Practice for Deconstruction and Construction Sites; 9th Edition dated January 2019.
8.09 | Nights: Strictly in accordance with the City of London Code of Practice for Deconstruction and Construction Sites; 9th Edition dated January 2019.
9. | Management of Sub-Contract Works
9.01 | Supervisor with overall responsibility for project: | [6 empty] | RCL
9.02 | Detailed Logistics Plans, Method Statements and Risk Assessments should be
| submitted a minimum of: |  | 21 days | prior to starting on site.
9.03 | Method Statements/Risk Assessments will be prepared by: | [6 empty] | RCL
9.04 | Name of person for issue of all instructions and notices: | [6 empty] | RCL
9.05 | Instructions / variations will be issued in writing by BAM Construction Ltd only. Please note that these instructions are only valid if issued on formal BAM Construction template referenced 310-11 rev 3 entitled ‘Instruction to Subcontractor’ and countersigned by either the Bam Project Manager (Graham Ridge) or a member of the Commerical Team. Instructions included on emails or issued verbally will not be valid. Instructions issued from any member of the Client / Design Team will not be valid unless confirmed in writing by BAM Construction Ltd. The Subcontractor is to comply with variations as dictated by the terms of the contract, including proceeding in cases where costs cannot be agreed beforehand.
9.06 | The Sub-Contractor must keep the same supervisor and operatives on site for the
duration of the Sub-Contract works. Any operatives arriving for work without the
appropriate supervision may be prevented from working and removed from site.
9.07 | It is the Sub-Contractor’s Supervisor's (as 9.1 above) responsibility to fully brief those
under their control and to ensure that they are fully aware of the requirements of the
Contract, specification, drawings, interfaces, etc. and are able to fully complete the
Sub-Contract works. Any costs resulting from BAM Construction Limited Management
fulfilling this role will be set-off against the Sub-Contractor.
9.08 | The person identified in 9.01 above together with other relevant and appropriate
Sub-Contractor personnel are required to attend regular progress/co-ordination
meetings as requested by BAM Construction Limited. The Sub-Contractor shall
prepare a progress report prior to these meetings, identifying both on and off-site
activities. The decision as to who accompanies the person named in 9.01 above shall
rest entirely with BAM Construction Limited.
9.09 | Is it intended to sub-let any portion of the Sub-Contract Works? | [6 empty] | RCL
If yes your attention is drawn to clause 14 of BAM Conditions of Sub-Contract.
9.1 | Sub-Contractor's anticipated workforce on the project:
| Own operatives: |  |  |  | nr |  |  | RCL
| Sub-Contractor operatives: |  |  |  | nr |  |  | RCL
| Apprentices: |  |  |  | nr |  |  | RCL
| Work placements: |  |  |  | nr |  |  | RCL
9.11 | No agency labour is to be employed by the Sub-Contractor without written prior consent
from BAM Construction Limited's Project Manager.
9.12 | Percentage of local labour:
| 0-10 mile radius of the project: | [6 empty] | RCL
| 10-25 mile radius of the project: | [6 empty] | RCL
| 25-50 mile radius of the project: | [6 empty] | RCL
| 50+ mile radius of the project: | [6 empty] | RCL
| Total: |  |  | 0%
9.13 | Where required, do you subscribe to, and apply, the terms of Construction Industry
| Joint Council National Working Rule Agreement? | [6 empty] | RCL
9.14 | Do you engage in the practice of 'blacklisting?' | [6 empty] | RCL
9.15 | What percentage of your workforce is paid via payroll? | [6 empty] | RCL
9.16 | Daily and weekly record of staff, labour and hours to be submitted by the
Sub-Contractor to BAM Construction Limited for record purposes.
9.17 | It is the responsibility of the Supervisor (identified in 9.01) to ensure that all relevant /
up-to-date information is made available to operatives at the workplace, including
subsequent amendments and revisions e.g. Drawings, Method Statements, etc.
10. | Attendances
10.01 | A full list of attendances provided by the Sub-Contractor is either:
a) Attached to these meeting minutes:
| b) Included within Sub-Contract Data Sheet item: |  |  |  |  | 47
Notwithstanding the above a summary of key attendances to be provided are detailed
below.
Offices/Storage
10.02 | Sub-Contractor's Office: |  |  | Space to be provided by Bam only - all furniture by Subcontractor
10.03 | Sub-Contractor's Storage: |  |  | Space to be provided by Bam only - any containers / boxes by Subcontractor
10.04 | Date office / storage space available / required: | [6 empty] | RCL
10.05 | Provision of maximum 1 bar pressure water supply: |  |  |  |  | By BAM
10.06 | Location of supply: |  | Water supply adjacent to hoist tower - any hoses from this supply to be by Raphael
Temporary Electrics
10.07 | Provision of safety lighting: |  |  | By BAM
10.08 | Provision of task lighting: |  |  | By Sub-Contractor
10.09 | 110v power for small tools only.
10.1 | All leads from power source to Sub-Contractor's tools: |  |  |  |  | By Sub-Contractor
10.11 | The provision and supply of power for Sub-Contractor offices / storage etc.:
By BAM
Unloading and distribution
10.12 | Mechanical handling: |  | By Sub-Contractor
10.13 | All unloading and distribution will be undertaken by the subcontractor from the point of deliver to the point of storage / installation - please refer to BAMs Construciton and Logistic Plan for details of what BAM will provide to assist.
(except for agreed usage of any BAM Construction Ltd cranes or hoists)
10.14 | Traffic Management: All traffic management for the Sub-Contract works to be provided by Sub-Contractor. Any road/pavement closures required for the Sub-Contact works are included by the Sub-Contractor.
Scaffold
10.15 | Use of BAM Construction Ltd standing scaffold if and when erected:
Bam will be providing scaffold to the faced, a birdcage to the double height reception and a birdcage to the top of stairs. All internal scaffold, access and crash decks to be provided by Sub-Contractor.
10.16 | Details of special scaffolding to be provided by Sub-Contractor:
Any scaffolding requirements outside of items described above deemed included by Sub-Contractor irrespective of height.
Plant
10.17 | Barriers & Segregation: All barriers and segregation required for the Sub-Contract works deemed included by the Sub-Contractor
10.18 | Provision of all Sub-Contractor's plant: |  |  |  | By Sub-Contractor
10.19 | Provision of all Sub-Contractor's small tools: |  |  |  | By Sub-Contractor
10.2 | Security of Sub-Contractor's plant and materials: |  |  |  | By Sub-Contractor
10.21 | Cranage: All crangeage required for the Sub-Contract works deemed included by the Sub-Contractor
10.22 | Additional plant requirments: BAM will provide a goods lift/hoist any other movement that that provided by the hoist is included by the Sub-Contractor. All traffic management included by the Sub-Contractor.
Supervisor of Sub-Contract Works
10.23 | Supervision: Sub-Contractor is deemed to have included for the supervision of their works including attendnace on other trades as required where their own works is directly affected by other Sub-Contractors.
Waste Management
10.24 | Waste Management: Sub-Contractor to remove waste to a central point located on each floor provided by BAM. Any bulk items items of packaging, such as cable drums, pallets, stillages etc, are to be cleared by the subcontractor.
Engineering
10.25 | Main grid lines and datum provided by: |  |  |  | By BAM
10.26 | Setting out from main grid lines and datum's by: |  |  |  | By Sub-Contractor
Builders work requirement
10.27 | Sub-Contractor to specify:
RCL
Protection
10.28 | Supply of protection to Sub-Contractor's own work: |  |  |  |  | By Sub-Contractor
10.29 | Removal of protection from Sub-Contractor's own work: |  |  |  |  | By Sub-Contractor
10.3 | All protective covering provided must be fire retardant to LPS1207.
Any other specialist requirements
(BAM / Sub-Contractor to list below)
10.31 | [7 empty] | RCL
11. | Sub-Contract Design Element
11.01 | Sub-Contract element applicable:
11.02 | The Principal Designer for this project is: |  |  |  | Bam Construction Ltd
11.03 | On this project and in the context of the Construction (Design & Management)
Regulations you are carrying out design for the:
RCL
11.04 | As a Designer under these regulations, the Sub-Contractor must:-
a) Provide a Design Competency brief before commencement of any works
b) Give adequate consideration to the risks to health and safety of those carrying out
construction, cleaning and maintenance work at any time, and to those who may
be affected by the work of such persons at work.
c) Include, within your design, adequate information about any aspect of the design
which may affect the health and safety of those carrying out construction,
cleaning and maintenance work at any time, and those who may be affected by
the work of such persons at work.
d) Promptly provide the Principal Contractor with information which the Principal
Contractor would provide for the Health and Safety File.
e) Accordingly, please provide the following, together with any other information you
may consider being relevant for inclusion in the Health and Safety File.
i) A schedule of the materials originally used in manufacture/construction/
installation
ii) General details of the methods originally used in manufacture/construction/
installation
iii) The design criteria
iv) The recommended methods and materials to be used to clean
v) The recommended methods and materials to be used to repair/replace/maintain
vi) Copies of the As-Constructed drawings/schedules
11.05 | As a designer the Sub-Contractor must consider environmental matters including
designing out waste.
11.06 | The Project Design Responsibilities Matrix is either:
| a) Attached to these meeting minutes: |  |  |  | No
b) Included within Sub-Contract Data Sheet item: Please refer to Appendix F
Development of Design
11.07 | The Sub-Contractor should ensure compliance with the design team specification.
If a deviation from the ‘original’ specification has been agreed as ‘equal and
approved’ then the design team specification shall be updated.
11.08 | The Sub-Contractor is required to ensure that the design is in accordance with the
manufacturer’s recommendations.
11.09 | The Sub-Contractor is required to ensure that interface details with other trades are
co-ordinated, buildable and approved by all relevant parties.
11.1 | The Sub-Contractor is required to ensure clarity and consistency across all
Sub-Contractor interface drawing details.
11.11 | The Sub-Contractor is required to update design drawings following review by the
design team.
12. | Information Management Procedures
12.01 | Sub-Contractor to provide an Information Required Schedule to BAM. It is the
Sub-Contractor’s responsibility to ensure that this is comprehensive. Any further
requests for information are to be submitted on an agreed form (one request per
form). No claims will be considered in cases where requests are not submitted in
accordance with the procedure, or where the request is made unreasonably close to
or distant from when the information is required to suit the agreed programme.
12.02 | Name of person preparing Information Required Schedule: | [6 empty] | RCL
12.03 | Person responsible for Information Management: | [6 empty] | RCL
12.04 | The person named in 12.02 should attend the project mobilisation meeting and any
training identified as required. The production of information shall commence only
after the Project Information Manager is satisfied that the project procedures will be
adhered to with reference to the BIM Execution Plan. Information will not be
accepted as complete unless the supplier can demonstrate this has been
undertaken satisfactorily.
Note: Where applicable Sub-Contractors will be expected to complete Part A Supply
Chain Assessment form BIM (350-20) pre contract and provide completed Part B
post contract.
12.05 | Details of Sub-Contract drawing programme and schedule:
RCL
Note: This document may be referred to as the Task Information Delivery Plan
(TIDP) and must detail all information deliverables to meet the requirement of the
Employers Information Requirements (EIR) and contract programme.
12.06 | Prior to issue all information must be checked for compliance against the
requirements of the project BIM Execution Plan. In addition the information must be
validated for completeness, accuracy, spatial co-ordination and relevance.
12.07 | All information must be in accordance with the procedures described in the project
BIM Execution Plan.
12.08 | Number of Sub-Contractor's hard copy drawings to be provided:
| For approval: |  | All drawings are to be issued direct to Bam via the EDMS Livelink system in pdf. and dwg. Format.
For construction:
For completion:
All correspondence for BAM Construction Limited to be uploaded and issued via Live
Link or any other Project Specific Electronic Data Management System (EDMS) and
sent to site for the attention of the person identified in 2.7 with the exception of
applications for payment which are to be sent to the person identified in 2.8.
Note: Refer also to Section 2 Project Details & Correspondence Arrangements
13. | Site Dimensions and Tolerances
The Sub-Contractor shall:
13.01 | Satisfy themselves before commencement of the Sub-Contract Works as to the work
previously carried out by others and shall immediately notify the Contractor in writing
of any difficulties with the same.
13.02 | Confirm that the specified tolerances of preceding works are compatible with the
Sub-Contract Works.
13.03 | Confirm that tolerances in the Sub-Contract Works comply with those in the
specification for the Sub-Contract Works.
13.04 | Before Practical Completion of the Sub-Contract Works demonstrate that the
Sub-Contract Works comply with the specified tolerances.
13.05 | As constructed records including any deviations from planned works shall be
submitted in accordance with verification procedures set out in the BIM Execution
Plan at the end of the contract.
14. | Quality Procedures
14.01 | BAM Construction Ltd is certificated to BS EN ISO 9001. The Sub-Contractor is
required to comply with all procedures relevant to their scope of work.
14.02 | The Sub-Contractor is required to issue to site all of the relevant manufacturer’s
technical and installation literature associated with their works.
14.03 | The Sub-Contractor to provide compliance certificates for all workmanship, materials,
plant and equipment provided for the contract.
14.04 | BAM operate Mobile Site Management Systems (MSMS) to support the management
of quality procedures. The Sub-Contractor shall comply with any instruction raised
through these systems within period stated in terms.
14.05 | Mobile Site Management Systems (MSMS) to be utilised on this project: | [5 empty] | BIM 360
Quality Assurance Checklists
14.06 | Develop and agree QA checklists for the Sub-Contractor’s site activities ensuring that
they are bespoke to the project and cover all aspects of the work. Append QA
checklists to the minutes.
The QA checklists are required to be compiled in the actual build sequence and
approved prior to the site start.
14.07 | The QA checklists are required to be reviewed and updated as the project develops
and where the changes are made to the design including adjacent/interfacing trades)
14.08 | Identify and agree ‘hold’ points within QA checklists.
Advance Build
14.09 | Identify and agree works that require site mock up or ‘advance’ build prior to
progressing of other similar areas on site.
Development of Design
14.1 | The QA checklists are required to be reviewed and updated as CDP designs are
developed; (including adjacent / interfacing trades).
14.11 | Ensure QA checklists identify key elements of specification: (e.g. material
thicknesses, fixings, fixing centres, etc.)
Installation
14.12 | The Sub-Contractor is required to carry out ‘Quality’ toolbox talks with the workforce
prior to works commencing.
14.13 | The Sub-Contractor is required to provide advice from the manufacturer/material
supplier on the level of workforce training/qualifications required to install the works.
14.14 | The Sub-Contractor is required to ensure that the installation is in the correct and
agreed sequence.
14.15 | The Sub-Contractor is required to ensure that the installation is in compliance with the
specification requirements.
14.16 | The Sub-Contractor is required to ensure that the installation is in accordance with
manufacturer’s recommendations.
14.17 | The Sub-Contractor is required to ensure that drawings are updated where deviations
from the intended design on site are necessary and agreed with interested parties.
14.18 | QA checklists are to be ‘signed off’ in stages as the work progresses by the
Sub-Contractor and issued to BAM.
Inspection and Testing
14.19 | Inspection and Test Plan(s) for the Sub-Contractor's works to be established prior to
commencement.
Operating & Maintenance Manuals
14.2 | The Sub-Contractor is to submit draft O&M manuals during the construction phase at
dates to be confirmed by BAM.
14.21 | The Sub-Contractor shall submit the final version of the O&M manual by no later than:
2 weeks prior to completion of subcontract works
14.22 | The Sub-Contractor shall submit their O&M manual in accordance with the Employers
Information Requirements (EIR) contained within the BIM Execution Plan.
14.23 | The Sub-Contractor is to include a simple ‘user’ friendly guide and calendar of the
maintenance requirements within the O&M manual.
14.24 | The Sub-Contractor is required to identify all elements of the installation/equipment that
requires a maintenance contract to maintain the warranty, identify any components
that are excluded by the warranty and advise material life span in accordance with the
Execution Plan.
14.25 | Practical Completion certificate for the Sub-Contract works will not be issued and
retention monies will not be released until all necessary warranties, record drawings
and maintenance manuals are completed and handed over.
15. | Health and Safety
Note: Skip to section 15.02 if the Sub-Contractor is Constructionline Gold Verified
Status.
15.01 | The Sub-Contractor has previously returned BAM's Sub-Contractor Health and Safety
| Questionnaire - See Sub-Contract Document Number: | [6 empty] | RCL
15.02 | The Sub-Contractor has previously returned BAM's Temporary Works Questionnaire
| - See Sub-Contract Document Number: | [6 empty] | RCL
15.03 | The Sub-Contractor has previously returned BAM's Designer's Health and Safety
| Questionnaire - See Sub-Contract Document Number: | [6 empty] | RCL
15.04 | The Sub-Contractor has provided an organisation chart showing responsibilities for
| Health & Safety. | [6 empty] | RCL
15.05 | Explain how you brief your workforce before commencing work each day or when an
activity changes.
RCL
15.06 | Provide details of how the organisation manages occupational health for its workers,
namely compliance with BAM safety critical worker requirements.
RCL
15.07 | How does your organisation ensure Health and safety training is given to the
organisation's employees at all levels such as Directors, Senior Managers, Supervisors
and Operatives. Please refer to the BuildUK website for further guidance.
RCL
15.08 | Pre-Start Health & Safety Meeting arranged for:
| Date: |  | TBA |  |  |  |  | BAM
| Time: |  | TBA |  |  |  |  | BAM
| Location: |  | 25 Cannon Street, London, EC4M 5TA
| BAM Chair: |  | Mick Fahy - Project Manager
16. | Employment of Labour
Note: Skip to section 17 if the Sub-Contractor is Constructionline Gold Verified
Status.
16.01 | The Sub-Contractor has previously returned BAM's Sub-Contractor Labour
| Questionnaire - See Sub-Contract Document Number: | [6 empty] | RCL
17. | Environment and Sustainability
Note: Skip to section 17.02 if the Sub-Contractor is Constructionline Gold Verified Status.
Status.
17.01 | The Sub-Contractor has previously returned BAM's Sub-Contractor Environment
| Questionnaire - see Sub-Contract Document Number: | [6 empty] | RCL
17.02 | Overall commitment
The Sub-Contractor confirms that they are able to provide evidence that shows they
| support BAM’s Environmental Policy and Responsible Sourcing Policy. | [6 empty] | RCL
Note: e.g. method statements, procurement practices or on site activities
17.03 | The Sub-Contractor confirms that they have read, understood and agree to BAM's
| Supplier Sustainability Requirements. | [6 empty] | RCL
Note: These agreements require documents to be submitted before work starts,
and timescales for the supply of documents during the contract relating to waste,
timber and fuel. Cause for financial penalties are also stated.
17.04 | The Sub-Contractor is to comply with the following key project specific requirements:
(example may include: FSC/PEFC project certification, BREEAM requirements,
| Carbon assessments, Recycled content, Planning requirements) | [6 empty] | RCL
18. | Community Engagement
18.01 | The Community Benefits / Requirements for this project are detailed in Sub-Contract
Document Number:
19. | BAM Construction Limited Company Policies & Procedures
19.01 | In addition to the specific policies and questionnaires referred to herein the
Sub-Contractor has observed, performed and complied with BAM's all other policies
and procedures, insofar as they relate and apply to the Sub-Contract, details of which
| can be found at: |  | www.bam.co.uk
20. | Anti-Bribery and Corruption Policy
20.01 | The Sub-Contractor must comply in every respect with the BAM Construct UK Ltd
Anti-Bribery and Corruption Policy and procedures copies of which are available from
any Regional Office or the following website:
www.bam.co.uk/docs/default-source/policies/antibriberyandcorruptionpolicy.pdf
21. | Any Other Business / Expand on Items Above
Signed: |  |  |  |  | Signed:
Name: |  |  |  |  | Name:
Company: | BAM Construction Limited |  |  |  | Company: | Raphael Contracting Limited