## Sheet1
WP15 Carpentry & Joinery Schedule of Clarifications
1 | The contract sum includes for a VE saving of £98,610.00 for a change from Oberflex timber veneer to an alternative matt finish high pressure laminate from Formica. The VE sum is based upon a 'Matte 58' product. In the event that a natural timber American walnut is chosen the saving would reduce to £37,949.00 an add-back of £60,611.00. In the event the Egger laminate option is chosen the saving would reduce to X, an add back of X. If a change back to the orginal alternative is instructed then it will be for the values stated above.
2 | The contract sum includes for a VE saving of £13,770.00 for changing ironmongery suppliers from 3V to Elite Ironmongery. If a change back to the orginal alternative is instructed then it will be for the values stated above.
3 | The contract sum includes a VE saving of £34,764.00 for changing from the Shadmaster door core to a Shadcore core for all timber doors. If a change back to the orginal alternative is instructed then it will be for the values stated above.
4 | The contract sum includes a VE saving of £12,444.00 for reducing walnut door frames from 44mm to 32mm.
5 | The contract sum includes a VE saving of £622.00 for reducing hardwood door frames from 44mm to 32mm. If a change back to the orginal alternative is instructed then it will be for the values stated above.
6 | The contract sum includes a VE saving of £24,640.00 for the option of having a manually operated version of the current infrared operated soap dispencer or a manual dispencer hidden behind the mirror unit. If a change back to the orginal alternative is instructed then it will be for the values stated above.
7 | The contract sum includes a VE saving of £10,160.00 for the urinal divider units to be laminated glass dividers with a grey painted interlayer in lieu of a profiled timber sub frame wrapped in metal sheeting. If a change back to the orginal alternative is instructed then it will be for the values stated above.
8 | The contract sum includes a VE saving of £2,489.00 for the oak/timber veneer internal shelves to be omitted and replaced with Oak MFC, solid timber bench omitted and replaced with oak effect laminate. If a change back to the orginal alternative is instructed then it will be for the values stated above.