## Sheet1
|  | Design Responsibilities Matrix (DRM) | [19 empty] | Revision B 03/12/19
Key
1 = Primary Responsibility
2 = Supporting Role
Project Title: 25 Cannon Street
Contract No: HLN 0280
Note:- This schedule is provided for guidance as to primary responsibility for design. The party identified with primary responsibility shall obtain input from any other party as is necessary to ensure a fully co-ordinated interface is achieved
PRIMARY DESIGN RESPONSIBILITY
| RESOURCE | Buckley Grey Yeoman | Waterman Structures | MTT | MTT (Hann Tucker) | MTT | MTT | BGY (Architect / Lead Designer) | Tom Stuart Smith | MLM | Gerald Eve (Retained by Client) | Waterman Infrastructure & Environment | MTT | FMDC (Retained by Client) | Buckley Grey Yeoman | Tom Stuart Smith (Irritech) | MTT (Gravity Design Associates) | Waterman Infrastructure & Environment | Design Consultant Responsibility and Deliverables | SUBCONTRACTOR | Contractor Design Portion | Subcontractor Deliverables
| ROLE | Architect and Lead Designer | Structural/Civil Engineer | MEPH Engineer | Acoustic Consultant | Fire Engineering | Lift Consultant | Inclusive Access | Landscape | Approved Inspector | Planning Consultant | Transport | BREEAM | Façade Engineering | Cleaning & Access | Landscape Irrigation | Reception Lighting | Ecologist
1 | Lead Designer
| Lead designer as defined in RIBA Services | 1
| Provide coordinated design programme for coordinated design to be produced to BAM construction programme. Agree Design Information Release Programme to BAM / Project Information Required Schedule | 1 | 2 | 2 |  |  |  |  | 2
| Co-ordination / preparation of the Overall Site Plan | 1 | [6 empty] | 2
| Co-ordination of all interfaces /elements / materials | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  |  |  | 2 | 2 | 2 | 2 | 2
| Integrate Specialist Consultants and design subcontractors designs into the overall design | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  |  |  | 2 | 2 | 2 | 2 | 2
2 | Building Performance and Strategies
| Co-ordination of all performance strategies to meet the client's brief. | 1 | 2 | 2 | 2 | 2 | 2 | 2 | [5 empty] | 2 | 2 | 2 | 2 | 2 | Lead the design team to a coordinated building solution
| Co-ordinating general arrangement drawings | 1 | 2 | 2 |  | 2 |  | 2 | [10 empty] | Fully coordinated plans, elevations and sections
| Establish and develop the Architectural Overall Design strategy | 1 | 2 | 2 |  | 2 |  |  | 2 | [9 empty] | Provide drawings/specification
| Establish and develop the Building Service Design strategy | 2 | 2 | 1 |  |  |  |  | 2 |  |  |  |  | 2 |  | 2 | 2 |  | Provide drawings/specification
| Establish and develop the Structural Design Philosophy for all areas/elements | 2 | 1 | 2 |  |  |  |  | 2 | [9 empty] | Provide drawings/specification
| Establish and develop the Landscape design for the project | 2 | 2 | 2 |  |  |  |  | 1 |  |  |  | 2 |  |  |  |  | 2 | Provide drawings/specification
| Establish and develop the Acoustic Design Strategy | 2 |  | 2 | 1 | [13 empty] | Provide Report
| Establish and develop the Fire Design Strategy | 2 |  | 2 |  | 1 | [7 empty] | 2 |  |  |  |  | Provide Report
| Prepare BREEAM Assessemnts for Sustainability Criteria | 2 | 2 | 2 |  |  | 2 |  | 2 |  |  | 2 | 1 |  |  |  |  | 2 | Provide Report
| Establish and develop Base Build ICT Infrastructure Design | 2 |  | 1 | [9 empty] | 2 |  |  |  |  | Provide drawings & specification. Base build provisions for plant space and risers
| Establish and develop Horizontal and Vertical Access / Circulation Strategy | 1 |  |  |  | 2 | 2 | 2 | [10 empty] | Provide drawings/specification
| Establish and develop Air tightness Principles | 1 |  | 2 | [9 empty] | 2 |  |  |  |  | Develop airtightness principles . Design criteria by M&E consultant
| Establish and develop Thermal Principles | 2 |  | 1 | [9 empty] | 2 |  |  |  |  | Develop thermal requirements and model. Provide drawings/ specification coordinated with model
| Establish and develop lifts strategy | 2 |  | 2 |  | 2 | 1 | 2 | [10 empty] | Technical performance specification
| Establish and develop Ventilation strategy | 2 |  | 1 | 2 | 2 | [12 empty] | Provide design, general arrangement drawings; performance specification.
| Prepare Thermal performance analysis | 2 |  | 1 | [9 empty] | 2 |  |  |  |  | Carry out thermal modelling of the buildings to show compliance with Part L, Provide EPC rating and energy sustainability report
| Prepare building cleaning and maintenance strategy | 2 | 2 | 2 | [10 empty] | 1 |  |  |  | Provide coordinated building cleaning and maintenance document for client use.
| Prepare plant access and maintenance strategy | 2 | 2 | 1 | [10 empty] | 2 |  |  |  | Provide coordinated plant access and maintenance strategy for client use. To be developed further with subcontractor input. | 2 |  | Develop design in line with plant access & maintenance strategy. Provide maintenance information for plant selections.
| Prepare Interstitial condensation calculations | 2 |  | 2 | [9 empty] | 2 | [5 empty] | 1 | X | Detailed design of the cladding systems and necessary calculations to provide compliance with the design parameters and specification given by the façade eng.
| Prepare wind effect on building structure - Analysis | 2 | 1 | [10 empty] | 2 |  |  |  |  | Design of building structure to resist wind sway
| Assit PQS Prepare Area schedules | 2 | [18 empty] | .
| Establish and develop Lighting / daylight strategy | 2 |  | 1 | [9 empty] | 2 |  |  | 2
3 | Surveys and Assessment The Site and Surrounding
| Traffic analysis and surveys - including impact assessment As required by project for Planning | 2 | [9 empty] | 1 | [6 empty] | Carry out surveys and produce reports
| Ecology surveys - As required by project for Planning / BREEAM | 2 | [6 empty] | 2 | [8 empty] | 1 | Instigate surveys and produce reports
| Site investigation / Existing Structure |  | 1 | [15 empty] | Existing structure design, origional Site Investigation | 1
| Asbestos survey | [17 empty] | Carry out site survey and prepare report for asbestos removal | 1 |  | Strip out contractotor scope
| Prepare Demolotion Scope Drawings - Plans / Elevations | 1 | 2 | 2 | [14 empty] | Provide demolition scope drawings, structural cut lines by structural engineer
| Prepare Structural Demolition plans / cut lines | 2 | 1 | 2 | [14 empty] | Provide structural demolition scope drawings, structural cut lines by structural engineer
| Prepare demolition temporary Works |  | 2 | [15 empty] | provide outline temp works requirements based on design parameters of existing structures. | 1 | X | Method statement / Risk Assessment / drawings / calculations / environmental plan / noise / dust monitoring
4 | Survey & Assessments - Drainage and Services
| Identifying the need for and designing Services Diversions | 2 |  | 1 | [14 empty] | Provide scope. And specifications
| Existing services, non-intrusive survey | 2 |  | 1 | [14 empty] | Provide scope. Drawings showing existing services
| Establish existing utility services capacity |  |  | 1 | [14 empty] | Details of existing utilities capacity
| Establish existing underground drainage (capacity, connections, levels etc.) | 2 | 1 | 2 | [14 empty] | Provide drawing showing location and size
5 | Surveys and Assessments - The Building
| Inclusive access Assessment | 2 |  | 2 |  |  |  | 1 | [10 empty] | Provide report & integrate into the design
| Flood Risk Assessment |  | 1 | [15 empty] | Provide Flood Risk Assessment
| BREEAM Assessment | [11 empty] | 1
| Daylight Analysis | 2 |  | 1 | [14 empty] | Provide report & integrate into the design
| Carry out Thermal Modelling, calculations and prepare report to ensure compliance with outline specifications and Employers Requirements | 2 |  | 1 | [14 empty] | Provide calculations / report & integrate into the design
| Existing structure assessment (Where existing structure is altered) | 2 | 1 | 2 | [14 empty] | Provide report from site surveys - integrate findings into the design
6 | Specifications
| Architectural NBS | 1 | 2 | 2 | 2 | 2 | 2 | 2 | [10 empty] | Provide NBS specs for the works
| Structural including below ground drainage | 2 | 1 | 2 | [14 empty] | Provide specs for the works
| MEPH, ICT, Fire Protection (services), specifications inc. materials and workmanship | 2 |  | 1 | 2 | 2 | 2 | [11 empty] | Detailed specifications, including performance specification
| Reception lighting - specifications, materials and workmanship |  |  | 2 | [12 empty] | 1 |  | Detailed specifications, including performance specification
| Lighting control | 2 |  | 1 | [12 empty] | 2 |  | Coordinated lighting control specification for the project
| Underground Services Specification (Except below ground drainage as above ) |  | 2 | 1 | [14 empty] | Specification and location
| Landscape Specification - non-CDP | 2 | 2 | 2 |  |  |  |  | 1 |  |  |  | 2 | [5 empty] | Detailed materials, planting and workmanship spec
| Water Feature, Irrigation | [7 empty] | 2 | [6 empty] | 2 |  |  | Performance Specification, drawings showing scope | 1 | X | Product specificatipon, system design
| Building Log Book | 2 | 2 | 2 |  | 2 | 2 | [11 empty] | Provide relevant information for the preparation of the Building Log Book | 1 | X | Coordinate and produce log book.
| Building User Guide & O&M's | 2 | 2 | 2 |  | 2 | 2 |  | 2 | [9 empty] | Design Narratives, record information | 1 |  | Production of O&M's / BUG.
| Lift Performance Specification (Including Platform Lift) | 2 |  | 2 |  |  | 1 | [11 empty] | Lift shaft sizing / performance specifications | 2 | X | Installation drawings/ manufactures details & specifications. Record drawings.
| Above ground drainage | 2 |  | 1 |  |  |  |  | 2
7 | Local Authority Approvals
| Planning submission : discharge of reserved matters | 2 | 2 | 2 | 2 | 2 |  | 2 | 2 | 2 | 1 | 2 | 2 |  |  |  | 2 |  | Planning submission document; Obtaining consents & discharge of conditions | 2
| Submit Building Control Application and approval | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 |  |  |  | 2 |  |  |  |  | Submissions for Building Regulation compliance and approval. | 2 |  | BAM / specialist contractors to obtain approvals for relevant CDP design & site works
| Prepare Structural Calculations for Building Control Approval |  | 1 | [15 empty] | Design & provide structural information & calculations for Building Regulation approval.
| Underground drainage details for building Control Approval |  | 1 | [15 empty] | Design & provide UG drainage system for building control approval |  |  | BAM to obtain approvals for on site installations
| New Drainage Connections into existing sewers | 2 | 1 | 2 | [14 empty] | Provide design and prepare calculation for approvals of sewer connections with relevant authority |  |  | BAM to obtain approvals on site installations
| Environment Agency | 2 | 1 | 2 | [14 empty] | Provide flood risk report and submit for approval
| Fire Authority | 2 |  | 2 |  | 2 |  |  |  | 1 | [8 empty] | Fire Authority approval of Fire Strategy / Fire Plans
| Adjoining Owners - Open Space Agreement with CoL | 2 |  | 2 |  |  |  |  | 2 |  | 1 | [7 empty] | Provide information required by CoL
| Public Consultation for scheme | 2 | [8 empty] | 1 | [7 empty] | Provide information, attend meetings.
| Police [secure by design] Implement Security Consultant (Instrom) Recommendations for BREEAM Hea 06 Security of Site & Building | 1 |  | 2 |  |  |  |  | 2 | [5 empty] | 2 |  |  |  | Liaise and Develop design to meet Secure by design.
| Public Highways and Traffic | 2 | 2 | [8 empty] | 1 | [6 empty] | Liaise with Highway and develop design
| Section 106 Agreement - Discharge Conditions | 2 | 2 | 2 | [6 empty] | 1 | 2
| Any Section 38 and 278 Highway Works / External pavement Works | 1 | 2 | 2 | [14 empty] | Works to existing highways
| Utility Suppliers (into site and on-site distribution) | 2 | 2 | 1 | [14 empty] | MEP Engineer responsible for the design / capacities and obtaining quotations | 2 |  | BAM responsible for delivery of supplies
8 | BREEAM
| Pre Assessment to advise design team and allocate ownership for achieving credits | 2 | 2 | 2 | 2 |  | 2 |  | 2 |  |  | 2 | 1 | [5 empty] | Provide BREEAM pre-assessment schedule
| Provide information to BREEAM assessor as required - all stages | 2 | 2 | 2 | 2 |  | 2 |  | 2 |  |  | 2 | 1 | [5 empty] | Provide evidence and implement actions | 2 |  | Provide evidence
| Collate information from design team and liaise with BRE - all stages | [11 empty] | 1
| Produce BREEAM assessment and issue to BRE | [11 empty] | 1
| Complete post construction assessment / review | [11 empty] | 1
| Obtain BREEAM certificate from BRE - for building for 'design' and 'As Built' | [11 empty] | 1 | [5 empty] | Certificates
9 | Part L Requirements
| Advise design team on compliance requirements | 2 |  | 1 | [9 empty] | 2 |  |  |  |  | Provide brief to team - set performance standards
| Complete calculations as necessary to inform the design team and allow option appraisal |  |  | 1 | [14 empty] | Calculation and brief
| Issue calculations - Approved Inspector to approval |  |  | 1 | [14 empty] | Calculation and brief - confirm compliance
| Complete design and tender information in accordance with Part L | 2 |  | 1 | [9 empty] | 2 |  |  |  |  | Provide drawings and specifications - supported by the thermal model
| Provide thermal parameters / calculations of building envelope/fabric in accordance with Part L assessment | 2 | 2 | 2 | [9 empty] | 2 | [5 empty] | 1 | X | Provision of thermal parameters / calculations.
| Design of building services in accordance with Part L input data and to allow compliance with Part L | 2 |  | 1 | [14 empty] | Drawings / specifications & calculations
| Complete BRUKL report demonstrate Part L compliance |  |  | 1 | [14 empty] | Issue BRUKL Report | 2 |  | Provision of as built data
| Carry out calculations as necessary to produce the final building "Energy Performance Certificates" EPC |  |  | 1 | [14 empty] | Issue Energy Performance Certificate | 2 |  | Provision of as built data
10 | Acoustics
| Report on existing site noise levels [prior to construction] |  |  |  | 1 | [13 empty] | Carry out site surveys and produce report
| Develop Acoustic performance requirements | 2 |  | 2 | 1 | [8 empty] | 2 |  |  |  |  | Develop building fabric and Mechanical acoustic performance requirements. Comment on contractor submissions. | 2 |  | Acoustic data submissions
| Incorporate M&E acoustics performance requirements | 2 |  | 1 | 2 | [13 empty] | Coordinated design principles and performance specifications. Acoustic Consultant comment on submissions. | 2 |  | Acoustic data submissions
| Design advice on meeting regulations and employer requirements | 2 |  |  | 1 | [13 empty] | Provide advice and comments on contractors drawings.
| Compliance with employers requirements | 2 |  |  | 1 | [13 empty] | Report conforming compliance
| Provide acoustic product specification | 2 |  | 2 | 1 | [8 empty] | 2 |  |  |  |  | Review and comment on contractors proposals
| GA plans showing acoustic performance requirements | 1 |  |  | 2 | [13 empty] | Architectural acoustic requirements are to be defined within building element NBS specification. Mark up GA's.
| Acoustic inspections, testing and reports |  |  |  | 1 | [13 empty] | Site testing on completion and report on findings. | 2 |  | Carry out site testing to requirements.
| Contractor acoustic testing mock-ups and reports |  |  |  | 1 | [13 empty] | Provide comments to test mock up drawings and test mock up acoustic reports | 2 |  | Acoustic test data
11 | Fire
| Fire strategy - design | 2 | 2 | 2 |  | 1 | 2 |  |  | 2 |  |  |  | 2 |  |  |  |  | Provide design to ADB .Define fire compartmentation. Determine cavity barrier requirements details and locations; signage, refuge locations Drawings: layout, sections & details to describe requirements. BC issue to obtain approval.
| Fire protection to structure and fire stopping | 2 | 2 |  |  | 1 | [12 empty] | Paint and RC design protection specs [Performance specification] | 2 |  | Fire protection proposals based on proprietary systems to meet performance criteria with test data / certification
| Fire alarm & detection performance requirements | 2 |  | 1 |  | 2 |  |  |  | 2 | [8 empty] | Provide design principles of fire alarm & detection, electrical and alarm interface design with other elements. Drawings: layout, details to describe requirements.BC issue to obtain approval.
| Fire extinguishers, dry & wet risers and other fire fighting equipment | 2 |  | 2 |  | 1 |  |  |  | 2 | [8 empty] | Specification / location of fire-fighting equipment.
| Smoke ventilation strategy and natural vent performance requirements | 2 |  | 2 |  | 1 | [12 empty] | Design performance solution ,strategy, and drawings, fire-fighting shaft & Basement
| Operable smoke vent detailed design | 2 |  | 2 |  | 2 | [12 empty] | Fire Fighting Shaft - 'Colt' smoke extract | 1 | X | Design drawings and specifications
| Sprinklers - outline design | 2 |  | 1 | [14 empty] | Design drawings and performance specification - BC approval.
| Sprinkler - specialist design | 2 |  | 2 | [14 empty] | detail design | 1 | X | installation drawings and calculations
12 | Access/Part M Equality Act
| Design to comply with Part M / access. | 2 |  |  |  |  | 2 | 1
| Co-ordination of building fabric and services elements to meet all inclusive design requirements | 1 | 2 | 2 |  |  | 2 | 2 | 2
13 | Substructure
| Co-ordinating foundations with underground drainage & services |  | 1 | 2 | [14 empty] | Coordinated drawings showing foundations related to drawings / services with setting out dimensions.
| Loads to new foundations and foundation design |  | 1 | [15 empty] | Existing Foundations
| Below basement slab Foul & Surface Water Drainage and sewer outfalls to sewer | 2 | 1 | 2 | [14 empty] | Layout drawings specifications and details, with setting out dimensions pipework sizes, falls, manhole schedules, drainage layouts, inverts, and details including adaptions and connections to existing sewers.
| Sump pump design and specification |  | 1 | 2 | [14 empty] | Provide Sump Pump Design and specifications. Setting out drawings and details. | 2 |  | Working drawings
| Location and detailing of Incoming Services - existing and new |  |  | 1 | [14 empty] | Main service routes & connections. Liaison with Stat Services providers.
| Basement & Ground Floor Waterproofing; grade - system and specification / scope for new waterproofing | 1 | 2 | [15 empty] | Layout drawings, sections, details and full specification. |  |  | Junction drawings
| Basement slab, walls and ground slab design | 2 | 1 | 2 | [14 empty] | Full design, and detailed specifications for ground bearing and suspended slabs
| Reinforcement Design |  | 1 | [15 empty] | Provide full design
| Reinforcement detailing / schedules |  | 1 | [15 empty] | Provide drawings and schedules
14 | Above Ground Drainage and Plumbing
| Co-ordinate with below ground drainage | 2 | 2 | 1 | [14 empty] | Provide coordinated plans
| Roof drainage - levels, roof system any falls, cordinating outlet locations | 2 | 2 | 1 | [14 empty] | Roof layout drawings showing outlet positions - rainwater design / calculations
| Landscape drainage - levels, falls, cordinating outlet locations | 2 | 2 | 2 |  |  |  |  | 1 | [9 empty] | Coordinate with existing landscape drainage
| Roof drainage outlets with connections to internal downpipes | 2 | 2 | 1 | [14 empty] | Outlet specification and connection detail drawings
| Internal rainwater goods | 2 | 2 | 1 | [14 empty] | Specifications and drawings coordinated with other services
| Office and Residential Toilet layouts | 1 | 2 | 2 | [14 empty] | Layout and detail drawings. Full specification of fittings and finishes. |  |  | Fabrication drawings - Cubicles, vanity units
| Sanitary ware schedule and sanitary fittings specification | 1 |  | 2 | [14 empty] | full schedule of fittings and spec. Sanitaryware schedule to be issued by architect. All specified items to comply with WRAS
| Plumbing system | 2 |  | 1 | [14 empty] | Specifications, coordinated drawings and schematic drawings |  |  | Installation drawings
15 | Superstructure
| Concrete Frame, beams, columns, slabs and walls design | 2 | 1 | 2 | [14 empty] | Dimensioned drawings, sections, openings sizes, details & datum levels
| In situ concrete staircase | 2 | 1 | [15 empty] | Layout by Architect, full design by Structural Engineer
| Metal stairs | 2 | 2 | 2 | [14 empty] | Layout by Architect, 'loadings, interface with structure by Structural Engineer | 1 | X | Fabrication design and provide detail Drawings
| Primary builders work holes through structural elements above 250mm dia/square, including setting out for riser floors and holes through walls | 2 | 1 | 2 | [14 empty] | Provide dimensional lay out drawings, spatial sizing by services designer |  |  | Setting out of holes through walls below 250mm diameter by contractor
| Detail of cast in services incl. conduits, pipes, sleeves etc. | 2 | 2 | 1 | [14 empty] | Provide drawing and details | 2 |  | shown on working drawings
| Reinforcement design |  | 1 | [15 empty] | Provide full design
| All reinforcement Detailing / schedules |  | 1 | [15 empty] | Provide schedules
| Composite slab design including shear stud performance design / specification |  | 1 | [15 empty] | Layout drawings, loading and performance Specification
| Metal decking design |  | 2 | [15 empty] | Structural Engineer provide design intent, spans layout drawings and specification | 1 | X | Drawings, product data sheets, calculations
| Structural steelwork frame design | 2 | 1 | 2 | [14 empty] | Layout drawings with full setting out, section sizes, details, specification, connection loadings, steel finishes, service holes through beams & junction details | 2 |  | Fabrication Drawings, connection design
| Structural steelwork - temporary bracing scheme |  | 2 | [15 empty] | WSL checking Role only | 1 | X | Fabrication drawings and connection design
| Structural steel trimmers to holes, openings. | 2 | 1 | 2 | [14 empty] | Coordinated layout drawings with full setting out, details, specification, Indicative connection & junction details | 2 |  | Fabrication Drawings
| Steelwork to concrete connection design |  | 1 | [15 empty] | Layout drawings with full setting out, details, specification, connection & junction details | 2 |  | Fabrication Drawings
| Structural steelwork to steelwork connections design | 2 | 2 | [15 empty] | WSL to provide connection forces, layout drawings, setting out, details, junction details, finishes & specification | 1 | X | Steel to steel connections, Column splices Fixings and base plates Fabrication drawings and calculations
| Concrete performance spec |  | 1 | [15 empty] | Performance specifications |  |  | Find mix design for approval, including lytag concrete
| Secondary steelwork design Inc. cold rolled set-out/co-ordination | 2 | 2 | [15 empty] | WSL to review drawings for impact on primary structure only | 1 | X | Fabrication drawings and connection design
| Primary plant plinths, primary steelwork etc. for plant and plant screens | 2 | 1 | 2 | [14 empty] | RC and steelwork design where structurally required by WSL, layout drawings by Services Engineer | 2 |  | Final coordination by contractor. Secondary steel / plant support frames.
| Expansion & other structural joints | 2 | 1 | [10 empty] | 2 |  |  |  |  | Specifications and layout of structural joints
| Non-structural floor screed | 1 |  | 2 | [14 empty] | Specifications
| Temporary works design |  | 2 | [15 empty] | Review of proposals only | 1 | X | Drawings sizes, details, calculations
16 | Envelope
| Prepare Interface design and co-ordination of all materials | 1 | 2 | 2 | [9 empty] | 2 |  |  |  |  | Coordinated design concept and detail drawings. Setting out dimensioned drawings
| Roof finish & build up and rainwater outlet locations | 2 |  | 2 | [14 empty] | Performance specification, coordination of details and interfaces. Detailed design drawings and setting out, layout drawings, sections, details, colours / finish, interfaces with adjacent structures. | 1 | X | Roof system design drawings. Application of propriety roofing system in accordance with manufactures requirements Product Guarantee.
| Waterproofing details to plinths, up stands, abutments etc. | 2 | 2 | 2 | [14 empty] | Design drawings specifications based on specified syustem | 1 | X | Roof system design drawings. Application of propriety roofing system in accordance with manufactures requirements Product Guarantee.
| Curtain walling, windows, glazed doors, plant screening, external louvers | 2 | 2 | 2 | 2 |  |  | 2 | [5 empty] | 2 |  |  |  |  | Concept design drawings and performance specification including testing criteria and interface requirements including junctions between systems; typical details based on proprietary system and U Values with input from Service engineer. Dimensioned plans ,sections, and typical 1:5 details. Define overall structural openings coordinate with safety requirements & ventilation strategy | 1 | X | Contractor to complete design including fixings & structure & calcs; fab drawings; resolution of interface details with other CDP contractors, detailed construction sequence & method statement; temporary works (support/ bracing); O+M manuals; detailed design of any secondary steel work. . Calcs and docs to support approved inspectors application
| Limestone Cladding | 2 | 2 | [10 empty] | 2 |  |  |  |  | Concept design drawings and performance specification including testing criteria and interface requirements including junctions between systems; typical details based on proprietary system and U Values with input from Service engineer. Dimensioned plans ,sections, and typical 1:5 details. Define overall structural openings coordinate with safety requirements. | 1 | X | Contractor to complete design including fixings & structure & calcs; fab drawings; resolution of interface details with other CDP contractors, detailed construction sequence & method statement; temporary works (support/ bracing); O+M manuals; detailed design of any secondary steel work.. Calcs and docs to support approved inspectors application
| Roof Light Design | 2 | 2 | [5 empty] | 2 | [9 empty] | Concept design drawings and performance specification including testing criteria and interface requirements including junctions between systems; typical details based on proprietary system. Dimensioned plans ,sections, and typical 1:5 details. Define overall structural openings coordinate with safety requirements. | 1 | X | Contractor to complete design including fixings & structure & calcs; fab drawings; resolution of interface details with other CDP contractors, detailed construction sequence & method statement; O+M manuals; Calcs and docs.
| Fall restraint, Cleaning and access equipment | 2 | 2 | 2 | [10 empty] | 2 |  |  |  | Architects concept design, performance specification and access and cleaning report., setting out, and interface coordinated drawings | 1 |  | Working Drawings, Product warranty
17 | Internal Finishes
| Internal setting out of all finishes, stairs, WC`s, Lift Lobbies, corridors, entrances, apartment and office finishes, inc co-ordination with services - sockets, lighting, etc | 1 |  | 2 |  |  | 2 | 2 |  | 2 | [6 empty] | 2 |  | Elevation drawings with setting out of M&E equipment.
Joinery Items
| Special joinery items - Reception desk, café bench seating, prep area etc | 1 |  | 2 | [14 empty] | Concept layout drawings with setting out, sections, details and specification, coordination with MEPH | 2 |  | Fabrication and installation drawings including sub frame and fixing details. Samples, Record drawings
| Timber doors | 1 |  | 2 | 2 | 2 |  | 2 |  | 2 | [8 empty] | GA`s and detail drawings, interface drawings specifications, coordination with design team | 2 |  | Manufacturers and installation drawings including fixing details. Samples, Record drawings
| Riser metal doors | 1 |  | 2 | 2 | 2 |  | 2 |  | 2 | [8 empty] | GA`s and detail drawings, interface drawings specifications, coordination with design team | 2 |  | Manufacturers schedule
| Door schedules & details | 1 |  | 2 | 2 | 2 | [12 empty] | Layout drawings with setting out, sections, threshold details, interface details. Door schedule Provide Structural Openings & width and wall type information, Based on fire strategy and acoustics, including transfer grills. | 2 |  | Manufactures schedule, samples
| Ironmongery schedule | 1 |  | 2 |  | 2 |  | 2 | [10 empty] | Ironmongery schedule with setting out requirements, power requirements. Layout drawings, finishes & colour schedule, specification. Schedule to be provided by agreed supplier. | 2 |  | Manufactures sschedule, samples
| Timber wall panelling / timber screens | 1 |  | 2 | 2 | 2 |  | 2 |  | 2 | [8 empty] | GA`s and detail drawings, interface drawings specifications, coordination with design team | 2 |  | Manufacturers and installation drawings including fixing details. Samples, Record drawings
| Polished plaster wall panelling | 1 |  | 2 | 2 | 2 |  | 2 |  | 2 | [8 empty] | GA`s and detail drawings, interface drawings specifications, coordination with design team | 2 |  | Manufacturers and installation drawings including fixing details. Samples, Record drawings
| Timber flooring | 1 |  | 2 | 2 | 2 |  | 2 |  | 2 | [8 empty] | GA`s and detail drawings, interface drawings specifications, coordination with design team | 2 |  | Manufacturers and installation drawings including fixing details. Samples, Record drawings
| Skirtings | 1 | [16 empty] | GA`s and detail drawings, interface drawings specifications, coordination with design team
| Internal block walls [non load bearing] inc proprietry lintel | 1 | 2 | 2 |  | 2 | [12 empty] | Provide layouts, specifications | 2 |  | Builders work drawings to be produced by subcontractors.
| Internal block walls [non load bearing] post design and head restraint | 2 | 1 | 2 | [14 empty] | Provide drawings / specifications for restraint posts / head restraint for incorporation into drawings by others. | 2 |  | Relevant product details
| Dry lining/plastering/rendering | 1 |  | 2 | 2 | 2 | [12 empty] | Detail design internal wall package, based on fire strategy and acoustic requirements and any other performance criteria Inc. movement joints, setting out drawings, sections, details and specification. coordination with M&E consultant, based on proprietary system details. | 2 |  | Application of Architects details
| Floor screed and smoothing compound | 1 | 2 | 2 | [14 empty] | Provide layout drawings, details, specifications |  |  | product warranty
| Raised access flooring. | 1 | 2 | 2 | [14 empty] | Provide layout drawings, details, specifications | 2 |  | product warranty plus provision of bespoke detail and setting out of floor layouts
| Suspended ceilings | 1 |  | 2 | 2 | 2 | [12 empty] | Specification and coordinated layout drawings with full setting out, sections, details, co-ordinated reflected ceiling plans including setting out of lights, grills, FA sounders/detectors, access panels; | 2 |  | manufacturing and installation drawings, including interface details with other elements
| Fire curtains | 2 | 2 | 2 |  | 1 | [12 empty] | Layout drawings with full setting out, sections, details, threshold details, interface details, colours, door schedule Provide Structural Openings & width and wall type information, Based on fire strategy | 2 |  | Fabrication and installation drawings showing interface details including Manufactures details.
Floor finishes
| Stone (Granite), Tiling | 1 |  | 2 | 2 |  | 2 | 2 | [10 empty] | Layout drawings with joint setting out, sections, details, threshold and joint details, interface details, floor build up details, Specification, | 2 |  | installation drawings, including interface details with the elements, Samples
| Soft floor finishes (carpet & rubber florring) | 1 |  | 2 | 2 | 2 | [12 empty] | Detailed layout drawings. Full Specification and schedule.
| Lifts | 2 |  | 2 |  |  | 2 | [11 empty] | Design drawings, setting out performance specifications | 1 | X | Detailed design drawings, manufacture and installation.
| Lift car finishes | 1 |  |  |  |  | 2 | [11 empty] | Design concept and detailed design information | 2 | X | Detailed design drawings, manufacture and installation.
Architectural metalwork
| Roof and basement plant rooms access ladders, walkways, stepovers, raised platforms, riser grillage floors, collapsible balustrade | 2 | 2 | 2 |  |  |  |  | 2 | [9 empty] | Coordinated design intent drawings. | 1 | X | Fabrication drawings; structural calculations, Record drawings
| Bike Storage | 1 | [5 empty] | 2 |  |  |  | 2 | [6 empty] | Concept and specification anddimensioned setting out plan. |  |  | Fabrication drawings, Product warranty
| Stair handrails and balustrades, glass balustrades, | 2 | 2 | 2 |  |  |  | 2 | 2 | 2 | [8 empty] | Concept layout drawings with setting out, sections, details, colours/finishes and specification provide dimensioned plans, elevations and design interface details with adjacent elements. and specification. Structure Engineer's to assist in finalising the structural aspects and performance specification for the architectural metalwork elements. Ensure compliance with statutory requirements | 1 | X | Fabrication drawings; structural calculations, Record drawings
| Architectural louvres, | 2 | 2 | 2 | [14 empty] | layout drawings with joint setting out, sections, details, , interface details, Specification, | 1 | X | Fabrication drawings; structural calculations, Record drawings
| Reception glazed screens | 2 | 2 | 2 | 2 | 2 | [12 empty] | Layout drawings with joint setting out, sections, details, , interface details, Specification, | 1 | X | Fabrication drawings; structural calculations, Record drawings
| Metal planters named supplier | [7 empty] | 2 | [9 empty] | Concept and specification to suit statutory requirements and provide dimensioned setting out plan. | 1 |  | Product warranty
| Wall Finishes | [17 empty] | Coordinated design intent drawings.
| Tiling | 1 |  | 2 | 2 |  | 2 | 2 | [10 empty] | Layout drawings with joint setting out, sections, details, threshold and joint details, interface details, floor build up details, Specification, |  |  | installation drawings, including interface details with the elements, Samples
| Painting & Decorating | 1 | [16 empty] | Wall finishes plans, Specification & Colour Schedules
18 | Fixtures, Fittings and Equipment
| Room layouts & final co-ordination (fixed FF&E) - Café, Reception | 1 |  | 2 | [14 empty] | 1:50 layout drawings and wall elevations showing locations of furniture, equipment and MEPH elements | 2 |  | Manufacturers drawings where applicable
| Signs & graphics - Wayfinding | 1 |  | 2 | [14 empty] | Provide layouts and specification of signage from proprietary range. Drawings to show principles of setting out (Location, levels etc.) provide detail for illuminated signage layout drawings with full setting out, details, colours/finishes and specification | 2 |  | Fabrication drawings for bespoke signage
| Statutory signage | 1 |  | 2 |  | 2 |  |  |  | 2 | [8 empty] | Provide layouts and specification of signage from proprietary range. Drawings to show principles of setting out (Location, levels etc.) provide detail for illuminated signage layout drawings with full setting out, details, colours/finishes and specification.
| Blinds | 1 |  | 2 | [14 empty] | Provide 1:5 details for coordination with structure and finishes for fixing locations. |  |  | tenant fit out
19 | External Works including roof gardens
| Hard Landscaping inc finishes, stone benches, planters, covers, grilles, levels, falls & setting out | 2 | 2 | 2 |  |  |  | 2 | 1 | 2 | [8 empty] | Fully coordinated setting out and detailed drawings and specifications, coordinated with Civil engineers structure and Services Engineers drainage design, surface finishes by Landscape Architects |  | 2 | Fabrication and manufacturers installation drawings
| External signage | 1 | [16 empty] | Drawing, schedule and specification . |  | 2 | fabrication and manufacturers drawings
| External and street lighting | 2 |  | 1 |  |  |  |  | 2 | [9 empty] | Fully coordinated drawings, specifications, setting out |  | 2 | fabrication and manufacturers drawings
| External CCTV/security systems | 2 |  | 2 | [14 empty] | Services engineer concept design, performance specification | 1 | X | installation drawings/specifications coordination with metalworker housing
| Plant selection and soil build-up specification | 2 | 2 | 2 |  |  |  |  | 1 | [9 empty] | Indicative planting plan and planting schedule |  | 2
21 | External Highway Works
| Perimeter Pavement reinstatement | 1 | 2 | 2 |  |  |  |  | 2 | [9 empty] | Ground Floor Perimeter Pavement Reinstatement scope
22 | Building Services Design
| Air conditioning & mechanical ventilation heating and cooling systems | 2 | 2 | 1 | 2 | 2 | [12 empty] | Stage 4 detail design and specification | 2 |  | Detailed co-ordinated working drawings
| Heating plant & auxiliaries | 2 |  | 1 | [14 empty] | Stage 4 detail design and specification | 2 |  | Detailed co-ordinated working drawings
| Water treatment and Filtration system | 2 |  | 1 | [14 empty] | Stage 4 detail design and specification | 2 |  | Detailed co-ordinated working drawings
| Cooling water services - incoming supplies and distribution | 2 |  | 1 | [14 empty] | Stage 4 detail design and specification | 2 |  | Detailed co-ordinated working drawings
| Domestic hot water generation plant | 2 |  | 1 | [14 empty] | Stage 4 detail design and specification | 2 |  | Detailed co-ordinated working drawings
| External louver concept design, sizing | 2 |  | 1 | 2 | [13 empty] | Stage 4 detail design and specification | 2 |  | Detailed co-ordinated working drawings
| Heating installations including underfloor | 2 |  | 1 | [14 empty] | Stage 4 detail design and specification | 2 |  | Detailed co-ordinated working drawings
| Public health and plumbing services | 2 |  | 1 | [14 empty] | Stage 4 detail design and specification | 2 |  | Detailed co-ordinated working drawings
| Calorifier plant | 2 |  | 1 | [14 empty] | Stage 4 detail design and specification | 2 |  | Detailed co-ordinated working drawings
| Generator Exhaust flue & supply air | 2 |  | 1 | [14 empty] | Stage 4 detail design and specification | 2 |  | Detailed co-ordinated working drawings
| Gas supply manifold and outlets | 2 |  | 1 | [14 empty] | Stage 4 detail design and specification | 2 |  | Detailed co-ordinated working drawings
| Thermal insulation to plant, equipment and systems | 2 |  | 1 | [14 empty] | Stage 4 detail design and specification | 2
| Trace heating systems | 2 |  | 1 | [14 empty] | Stage 4 detail design and specification | 2 |  | Detailed co-ordinated working drawings
| Electric lighting including emergency lighting to internal and external areas | 2 |  | 1 |  |  | 2 | [9 empty] | 2 |  | Stage 4 detail design and specification | 2 |  | Detailed co-ordinated working drawings
| Electric lighting including emergency lighting to reception | 2 |  | 2 |  |  | 2 | [9 empty] | 1 |  | Stage 4 detail design and specification | 2 |  | Detailed co-ordinated working drawings
| Electrical general & small power systems | 2 |  | 1 |  |  | 2 | [11 empty] | Stage 4 detail design and specification | 2 |  | Detailed co-ordinated working drawings
| LV discrimination study and cable sizing |  |  | 1 | [14 empty] | Stage 4 detail design and specification | 2 |  | Detailed co-ordinated working drawings
| Fire detection and alarm systems | 2 |  | 2 |  | 2 | [12 empty] | Concept design and performance specification | 1 | X | Detailed co-ordinated working drawings
| Induction loops | 2 |  | 1 | [14 empty] | F1 detail design and specification | 2 |  | product warranty
| Disabled Refuge & WC Alarm Systems | 2 |  | 2 | [14 empty] | Concept design | 1 | X | Detailed co-ordinated working drawings
| Security, CCTV, intruder alarm & access control systems | 2 |  | 2 | [14 empty] | Concept design | 1 | X | Detailed co-ordinated working drawings
| Lightning protection | 2 | 2 | 2 | [14 empty] | Concept design and performance specification | 1 | X | Detailed co-ordinated working drawings
| Generating Plant & fuel tank | 2 |  | 1 | [14 empty] | Stage 4 detail design and specification | 2 |  | Detailed co-ordinated working drawings
| Generating plant enclosure | 2 |  | 2 | 1 | [13 empty] | Acoustic and material specification , setting out Stage 4 design information | 2 |  | Detailed co-ordinated working drawings
| IT and AV systems infrastructure for future provision | 2 |  | 1 | [14 empty] | Stage 4 detail design and specification | 2 |  | Detailed co-ordinated working drawings
| Electrical HV/MV/LV substations and switchrooms | 2 | 2 | 1 | [14 empty] | Provide load requirements and agree solution with Utilities. Provide evidence all electric scheme neets MD | 2
| Vibration Control - Engineering Systems | 2 | 2 | 1 | 2 | [13 empty] | Concept design and performance specification | 2 |  | Product warranty
| Building management systems and automatic controls | 2 |  | 2 | [14 empty] | Concept design and performance specification | 1 | X | Detailed specifications, co-ordinated working drawings
| Above slab drainage (Foul and RW) | 2 |  | 1 | [14 empty] | Stage 4 detail design and specification | 2 |  | Detailed co-ordinated working drawings
| Incoming electrical, gas, water, telecom & other services | 2 | 2 | 1 | [14 empty] | Stage 4 detail design and specification | 2 |  | Detailed co-ordinated working drawings
| Plant sizing, locations & sketch layouts, including weights | 2 | 2 | 1 | [14 empty] | Stage 4 detail design / coordination | 2 |  | Detailed co-ordinated working drawings
| Plant rooms spatially co-ordinated with fabric, plant & services | 2 | 2 | 1 | [14 empty] | Stage 4 detail design / coordination | 2 |  | Detailed co-ordinated working drawings
| Plant room access requirements, space for maintenance | 2 |  | 1 | [14 empty] | Stage 4 detail design / coordination | 2 |  | Detailed co-ordinated working drawings
| Service void spatial sizing (ceilings, floors) | 1 | 2 | 2 | [14 empty] | Stage 4 detail design / coordination | 2 |  | Detailed co-ordinated working drawings
| Services within risers, spatially co-ordinated with structure & fabric | 2 | 2 | 1 | [14 empty] | Stage 4 detail design / coordination | 2 |  | Detailed co-ordinated working drawings
| Services within voids to be spatially co-ordinated with structure & fabric to Stage 4 | 2 |  | 1 | [14 empty] | Stage 4 detail design / coordination | 2 |  | Detailed co-ordinated working drawings
| Service void & riser access arrangements. | 1 |  | 2 | [14 empty] | Stage 4 detail design / coordination | 2 |  | Detailed co-ordinated working drawings
| Identify primary holes within structural elements of the building | 2 | 2 | 1 | [14 empty] | Stage 4 Drawing showing size and setting out | 2
| Incorporate primary holes and plant plinth/ support into structural design | 2 | 1 | 2 | [12 empty] | 2 |  | Drawing showing size, details and setting out
| Provide details of all holes/chases etc. required for services installation through non structural building elements | 2 | 2 | 2 | [14 empty] | Drawing showing size and setting out | 1 |  | Shown on co-ordinated drawings
| Plant support where typical roof plinths are not appropriate | 2 | 2 | 2 | [14 empty] | Roof spatial layouts showing all plant | 1 |  | Detailed plant support details