## New Pro-Forma
|  |  |  | Sub-Contractor Payment Schedule |  | Form : 330-08
Rev : 3
| Retention Release Date* |  | First half retention release date: |  | n/a
| *Only to be completed for use with 153-37-1 |  |  | (Clause 8.10.1(ii))
| Sub-contractor Application For Payment (AFP) date | Main Contract Valuation Date | Due Date | Last date for issue of payment (payer) notice | Last date for issue of pay less notice | Final Date for payment | :
1 | 2020-02-17 | 2020-02-20 | 2020-02-27 | 2020-03-03 | 2020-03-24 | 2020-03-27
2 | 2020-03-17 | 2020-03-20 | 2020-03-27 | 2020-04-01 | 2020-04-21 | 2020-04-24
3 | 2020-04-17 | 2020-04-20 | 2020-04-27 | 2020-05-01 | 2020-05-22 | 2020-05-25
4 | 2020-05-18 | 2020-05-20 | 2020-05-27 | 2020-06-01 | 2020-06-23 | 2020-06-26
5 | 2020-06-16 | 2020-06-19 | 2020-06-26 | 2020-06-29 | 2020-07-21 | 2020-07-24
6 | 2020-07-17 | 2020-07-20 | 2020-07-27 | 2020-07-31 | 2020-08-21 | 2020-08-26
7 | 2020-08-17 | 2020-08-20 | 2020-08-27 | 2020-08-28 | 2020-09-22 | 2020-09-25
8 | 2020-09-15 | 2020-09-18 | 2020-09-25 | 2020-09-30 | 2020-10-20 | 2020-10-23
9 | 2020-10-16 | 2020-10-20 | 2020-10-27 | 2020-10-30 | 2020-11-23 | 2020-11-26
10 | 2020-11-17 | 2020-11-20 | 2020-11-27 | 2020-12-02 | 2020-12-22 | 2020-12-25
11 | 2020-12-15 | 2020-12-18 | 2020-12-25 | 2020-12-30 | 2021-01-19 | 2021-01-22
12 | 2021-01-15 | 2021-01-20 | 2021-01-27 | 2021-02-01 | 2021-02-23 | 2021-02-26
13 | 2021-02-16 | 2021-02-19 | 2021-02-26 | 2021-03-03 | 2021-03-23 | 2021-03-26
14 | 2021-03-16 | 2021-03-19 | 2021-03-26 | 2021-03-31 | 2021-04-20 | 2021-04-23
15 | 2021-04-16 | 2021-04-20 | 2021-04-27 | 2021-04-30 | 2021-05-24 | 2021-05-27
16 | 2021-05-17 | 2021-05-20 | 2021-05-27 | 2021-06-01 | 2021-06-22 | 2021-06-25
17 | 2021-06-15 | 2021-06-18 | 2021-06-25 | 2021-06-30 | 2021-07-20 | 2021-07-23
18 | 2021-07-16 | 2021-07-20 | 2021-07-27 | 2021-07-30 | 2021-08-23 | 2021-08-26
19 | 2021-07-30 | 2021-08-02 | 2021-08-09 | 2021-08-13 | 2021-09-03 | 2021-09-06
| 0 | +3 | +7 | +5 | -3 from final date | 30 from due date
NB: For all future valuations beyond the above dates the payment cycle will be as currently detailed based on the date of the Main Contract Valuation.