## Table 1
BAM - 25 Cannon Street
| Clarification/Comment | Bam Comment 21.05.20 | RCL Comment 21.05.20
1 | The contract sum includes for a VE saving of £98,610.00 for a change from Oberflex timber veneer to an alternative matt finish high pressure laminate from Formica. The VE sum is based upon a 'Matte 58' product. In the event that a natural timber American walnut is chosen the saving would reduce to £37,949.00 an add-back of £60,611.00. In the event the Egger laminate option is chosen the saving would reduce to £76,888.00, an add back of £21,722.00. In the event a Shadbolt Crown Cut veneer is chosen there would be an additonal cost of £6,930.48 over the natural American walnut straight grain option. If a change back to the orginal alternative is instructed then it will be for the values stated above.
2 | The contract sum includes for a VE saving of £13,770.00 for changing ironmongery suppliers from 3V to Elite Ironmongery. If a change back to the orginal alternative is instructed then it will be for the values stated above. |  | Agreed and closed out
3 | The contract sum includes a VE saving of £34,764.00 for changing from the Shadmaster door core to a Shadcore core for all timber doors. If a change back to the orginal alternative is instructed then it will be for the values stated above. |  | Agreed and closed out
4 | The contract sum includes a VE saving of £12,444.00 for reducing walnut door frames from 44mm to 32mm. |  | Agreed and closed out
5 | The contract sum includes a VE saving of £622.00 for reducing hardwood door frames from 44mm to 32mm. If a change back to the orginal alternative is instructed then it will be for the values stated above. |  | Agreed and closed out
6 | The contract sum includes a VE saving of £24,640.00 for the option of having a manually operated version of the current infrared operated soap dispencer or a manual dispencer hidden behind the mirror unit. If a change back to the orginal alternative is instructed then it will be for the values stated above.
7 | The contract sum includes a VE saving of £10,160.00 for the urinal divider units to be laminated glass dividers with a grey painted interlayer in lieu of a profiled timber sub frame wrapped in metal sheeting. If a change back to the orginal alternative is instructed then it will be for the values stated above. |  | Agreed and closed out
8 | The contract sum includes a VE saving of £2,489.00 for the oak/timber veneer internal shelves to be omitted and replaced with Oak MFC, solid timber bench omitted and replaced with oak effect laminate. If a change back to the orginal alternative is instructed then it will be for the values stated above. |  | Agreed and closed out
9 | Please refer to our response, dated 11.11.19, to the tender query schedule for potential technical issues with regard to:-
| d) The application of applied finishes to doors within the reception area |  | Agreed and closed out
10 | Our ironmongery quotation is based upon 3v's schedule ref CT0819-01-T. Electrical items of ironmongery will be free issued to others for them to fix. We have not allowed for access control, FOB release, swipe card access or any other security hardware. The forming of mortices for any floor springs is to be by others. |  | Agreed and closed out
11 | Where required we have allowed to use our door manufacturer’s certified intumescent products, we have not allowed for any specific acoustic ratings. We have allowed, only where necessary to achieve certification, intumescent sealant, we have not allowed for any other mastic. Mastic will not be fair faced. |  | Agreed and closed out
12 | Timber doors may be sourced from a separate company to that which supplies the frames however the whole assembly will be fully compliant in respect of fire certification. |  | Agreed and closed out
13 | We have not allowed to machine for or to supply or fix any air transfer grilles. |  | Agreed and closed out
14 | We have allowed to fix doors and ironmongery once only, the filling of fixing holes to primed door frames is to be by others. | RCL have included for the removal of ironmongery prior to decoration and reinstate once decorations are complete.
15 | We have allowed for overpanels to door types to be the same thickness as the door leafs without a transom, we have not allowed for detail 03 on drawing DD-03. |  | Agreed and closed out
16 | Frames to doors with a painted finish have been priced as being supplied primed for on site decoration by others, we have assumed that the paint finish to the door leafs is RAL 9010. |  | Agreed and closed out
17 | Primed skirtings and widow boards for on site decoration by others will be manufactured from mrmdf and will be fixed using a combination of adhesive, pins and screws, the filling of all fixing holes is to be by others. |  | Agreed and closed out
18 | The plumbing in of sinks and electrical connections to the soap dispensers are by others, all other plumbing goods, electrical equipment and lighting are to be by others | There was no clarification issued in your orignal bid which excluded the electrical equipemnt and therefore were deemed included. A clarification was added on a revised bid, however the price for the items including electrical equipemnt did not change. Electrical Items and LED lighting deemed included by RCL. | Our tender was issued under cover of our letter dated 23.10.19, item 13 of this letter stated that there were various assumptions that we had made in the preperation of our tender that we would need to discuss further. On 29.10.20 Bam issued their Tender Query Schedule, item 13 asked what items we wished to discuss further. On 11.11.19 we responded to this query stating that we would forward our project Specific Pricing notes. On 12.11.19 we issued these Pricing Notes, item 10 stated that all electrical equipment and lighting was by others.
19 | The specified manufacturer of the height adjustment equipment has expressed concerns as to whether it is suitable for its intended use |  | Agreed and closed out
20 | We have included PC Sums of £1,660.00 and £2,490.00 respectively for bins and bin flaps to the male and female changing room towel units. | RCL deemed to have allowed for firm fixed price in lump sum bid with no provisonal sums. | We had to accept our competitors prices which had no qualifications
21 | We have allowed for the shower benches to have "off the shelf" brackets manufactured by Hegbo. |  | Agreed and closed out
22 | The stonework to the reception benches and planters is to be by others |  | Agreed and closed out
23 | All timber products provided by ourselves will be environmentally accredited. Usually this accreditation will be by the FSC, if not it will be by one of the other recognised bodies, e.g. PEFC or CSA. |  | Agreed and closed out
24 | We have not allowed for testing |  | Agreed and closed out
25 | We shall co-operate fully to try to ensure proper co-ordination between ourselves and other trades. However, ultimate responsibility for co-ordination must remain with yourselves. |  | Agreed and closed out
26 | Where discrpencies exist between the door schedule and other design information the door schedule takes precedence. |  | Agreed and closed out
name :
company :
date :