## Sheet1
RAPHAEL CONTRACTING LIMITED
PRELIMS BREAKDOWN
CONTRACT: | 25 Cannon Street
PROGRAMME - | START: | Sept 20
FINISH:
| DURATION: | 38 weeks
Avg 4 men
NOT GB OR JW
M.O'B: | [9 empty] | -
SUPERVISOR- PRE-TENDER: |  |  | 4 | wks | @ | 1950 | X | 100% | = | 7800
NON WORKING: |  |  | 38 | wks | @ | 1900 | X | 50% | = | 36100
FOREMAN- PRE-TENDER: |  |  |  | wks | @ | 1100 | X | 0% | = | 0
NON WORKING: |  |  | 38 | wks | @ | 1100 | X | 100% | = | 41800
WORKING: |  |  |  | wks | @ | 1100 | X | 0% | = | 0
ENHANCEMENT |  |  |  | wks | @ | 290 | X | 0% | = | 0
UNLOAD & DISTRIBUTE/ CLEAN & CLEAR | [9 empty] | 10000
OFFICE/TELEPHONE/COPYING: | [9 empty] | 10000
PLANT: | [9 empty] | 5000
INCREASED COSTS: | LABOUR | [7 empty] | }
[9 empty] | } | Separate
| MATERIALS | [7 empty] | }
RUBBISH REMOVAL | [9 empty] | 0
PROTECTION/RISK/FRENCH POLISHER: | [9 empty] | 20000
HEALTH & SAFETY | [9 empty] | 5000
135700
OH & P | [5 empty] | 12% |  |  |  | 16284
151984
Discount | [9 empty] | 16887.1111
6000
174871.1111
PEPS | [9 empty] | 1766.3749
176637.486
CONTINGENCY | [9 empty] | 0
[6 empty] | TOTAL |  |  |  | 176637.486