## Title
Appendix C
SUPPLEMENTARY SUBCONTRACT CONDITIONS
FIXED PRICE LUMP SUM
for
WP15 Carpentry & Joinery
at
25 Cannon Street, London, EC4M 5TA
for
25 Cannon Street Limited c/o Pembroke
package works to be undertaken by
Raphael Contracting Limited
signed:
name:
on behalf of:
date:
25 Cannon Street / Supplementary Conditions
Ref: HLN.0280/WP15

## Contractual Compliance
25 Cannon Street
Supplementary Conditions
Contractual Conditions
Item
Description
Subcontract Quotations & Financial Management
1 | Any subcontract entered into will be a fixed (subject to clauses 7 & 27 below), lump sum all encompassing price for the design (in accordance with the scope of works, specifications and Appendix E & F), supply of all labour, plant, materials, preliminary items etc. necessary to complete the works in accordance with the documents listed in Sub-Contract Data Sheet ref: 153-06 Rev 5.
2 | Any quantities produced by the subcontractor or provided by the Main Contractor whether specifically mentioned / described or not are the sole risk of the subcontractor.
3 | Any Bills of Quantities or Preliminary items used in the compilation of the lump sum tender will have no contractual status whatsoever [other than in assisting in the pricing of variations at the main contractors discretion] and are to be non remeasurable.
4 | Adjustments will only be made to the measured works where there is a fundamental change to the design / scope resulting in an addition / omission to the subcontract works assuming the sub-contractor has issued the appropriate notice.
5 | The subcontractor is to provide a full priced breakdown of all the preliminary items included within his quotation that he deems necessary to successfully execute his works. No claims for additional costs will be entertained by the Main Contractor for additional preliminaries not priced but that are required to complete the subcontract works. The subcontract final account figure will be adjusted to reflect preliminary items priced but subsequently not provided.
6 | The subcontractor is deemed to have made due allowance and included within his quotation for all works [including preliminaries] whether described specifically or not, but which could be reasonably assumed necessary to facilitate the successful execution of the subcontract package.
7 | With the exception of any unexpected price rises as a result of Covid-19 and or the final resolution of Brexit the subcontractor's quotation is a fixed price and not subject to fluctuation of any kind.
8 | The subcontractor shall make all due allowance for winter working and indeed the climate conditions at the time the works are undertaken with due consideration being made but not limited to protection screens / tents, heaters, dehumidifiers & cooling equipment to ensure the works are progressed
9 | The subcontractor shall make all due allowance for compliance with the Working Rule Agreement.
10 | The subcontractor shall ensure that all documents, specifications, reports, etc. that are named or referred to in the subcontract enquiry have been considered when submitting his quotation irrespective of whether they are included within the tender enquiry pack. The Main Contractor will not entertain any claims for additional costs as a result of the subcontractors failure to comply with this requirement.
11 | Specifications are included in the enquiry document and are considered to be part of and incorporated in the item descriptions. Subcontract quotations will be deemed to have included with complying with the requirements of the Specifications, whether or not specific requirements are mentioned in any individual or collective item descriptions.
12 | The subcontractor shall, with his quotation, submit a fully priced copy of his quantified schedule of rates that equates to his quotation sum and these will be only included in the subcontract order for the valuation of variations (at the main contractors discretion). They may also be used for assistance in the preparation of interim valuations.
13 | Within 7 days of his appointment, the sub-contractor should provide a cash flow forecast showing the gross valuation of the works at the date of each interim application throughout the sub-contract period, and based upon the programme of works.
14 | Interim applications for payment together with all necessary supporting information should be sent to site marked for the attention of the Project Surveyor at least five working days before the established Main Contract valuation dates. .
15 | Interim applications for payment should be accompanied by forecast of the final sub-contract value, together with a schedule of both proposed and authorised variations.
16 | Sub-contractors will be required to attend regular financial review meetings on site to facilitate accurate reporting.
17 | The sub-contractor shall identify all variations when directions are issued and obtain the Main Contractor's approval in advance of the works being put in hand.
18 | The subcontractor shall ensure that all variations from whatever source are approved by the Main Contractor in advance of the works being put in hand.
19 | Only variations that have been approved by the Main Contractor in advance of the work being put in hand will be included in a final adjustment of the contract sum.
20 | Upon receipt of a request for a quotation and/or programme advice, the sub-contractor shall submit an estimate without delay and in any case within 5 days & shall include:
• A detailed breakdown of the cost including any allowance for direct loss and expense.
• Details of any additional resources which may be required.
• Details of any adjustments which may have to be made to the programme for the Works.
• Any other information as is reasonably necessary for the Project Manager to fully assess the implications of issuing such an instruction.
21 | All measurement for the purpose of valuing variations and provisional sums, shall be in accordance with the RICS NRM2
22 | The tenderer shall advise of any reservations and concerns he has in regard to the enquiry and highlight any gaps. Failure by the subcontractor to identify any ambiguities, inconsistencies, gaps or omissions during the tender period will result in it being deemed that the subcontractor has priced the most suitable solution as dictated by the Main Contractor.
23 | Provisional sums within sub-contract tenders will only be permitted on prior agreement with the Main Contractor. Any provisional sums that are permitted will be deemed "defined" provisional sums and the sub-contract sum will be deemed to include for all programming and preliminary costs associated with the expenditure of these sums. Work items included as a provisional sum are not to be undertaken until you are in receipt of a written instruction confirming the expenditure of the sum; such requests for instruction are to be raised by you in a timely manner to suit the progress of the works.
24 | The tenderer shall identify any additional items that are not described in the enquiry but are required for the proper execution of the works - all as indicated or inferred in the drawings listed in the form of tender. No request for additional reimbursement will be allowed in respect of lack of knowledge of the site.
25 | The subcontractor shall where necessary check on site figured dimensions on consultant’s drawings, and ascertain the actual dimensions of existing structures or features affecting the new works. Where a discrepancy is apparent the subcontractor should report the fact to the Main Contractor and ask for further instructions. The Main Contractor's subsequent instruction to correct any discrepancies will not constitute a change to the subcontract. The Main Contractor will not accept any claims for delay or standing time where this requirement has not been performed in a timely manner.
26 | Value of materials claimed off site will only be paid if allowable under the main contract - It will be the responsibility of the subcontractor to furnish the main contractor with an indemnity form (obtained from the Main Contractor's QS) transferring title or ownership to the Main Contractor. This form will include insurance policy no., photographs and a list of all materials applied for. Furthermore the subcontractor is to provide reasonable proof that the title of ownership has transferred to the Main Contractor in respect of any claimed 'unfixed materials on site' and that no sub-subcontractor or supplier (of any tier) has validly retained title to these goods.
27 | With the exception of any unexpected price rises as a result of Covid-19 and/or the final resolution of Brexit appropriate provision should be made to allow for or fix any exchange rate fluctuations which may have an affect on the costs associated with the project up until completion. All applicable tender rates should be returned inclusive of any premiums associated with fixing the rates against currency fluctuations except of any that arise as a result of Covid-19 and/or the final resolution of Brexit.
Key Dates & Working Hours
28 | The subcontractor is to be aware of the sensitivity & quiet times of the surrounding areas and make due allowance within his tender for compliance with instructions to cease work due to such restrictions. Noisy working can only completed on a 2 hours on and 2 hours off basis.
29 | Normal working hours are 8am to 6pm Mondays to Fridays. The subcontractors programme is to include for a working 5 day week. The site will be open 8am to 1pm Saturdays for certain activities, subcontractor cost for working Saturdays are deemed included. Anytime worked outside these hours will be by prior agreement with the Main Contractor. RCL's working hours are 7:30am to 5pm.
30 | All subcontractors are to take full advantage of the hours available on site in order to satisfy the programming requirements. BAM Construction Ltd will not entertain any non-productive overtime claims due to any programming shortfalls if the above hours have not been worked.
31 | BAM Construction Limited reserve the right to vary these times without notice. Any hours the subcontractor may wish to work outside the above will be by prior agreement with the Project Manager and will be subject to reimbursement to BAM of costs for BAM supervision and/or attendance [First Aider, Fire Officer, Site Manager etc.] and all associated compound, site set up, company tied and overhead costs.
32 | The Main Contractor's Overtime Charges:
The following allows for the extended opening of the site with BAM security and management present on site. Written application will be made for such requests and will be at the discretion of BAM.
Monday - Friday = £90/Hr
Saturday = £135/Hr
Sunday = £180/Hr (Minimum 5 Hours duration)
Additional crane time will be charged at the following rates per crane and will include a Driver and Banksman. Written application will be made for such requests and will be at the discretion of BAM.
Monday - Friday = £97/Hr
Saturday = £114/Hr
Sunday = £131/Hr (Minimum 5 Hours duration)
Additional hoist time will be charged at the following rates per hoist and will include a Driver. Written application will be made for such requests and will be at the discretion of BAM.
Monday - Friday = £51/Hr
Saturday = £68/Hr
Sunday = £84/Hr (Minimum 5 Hours duration)
Access & Deliveries
33 | The sub-contractor is deemed to have inspected and satisfied himself with respect to adequacy of access to the site. All deliveries and sub-contractors personnel must report to BAM Construction site office prior to entering the site to sign in and be issued a visitor's pass.
34 | Access is permitted for off-loading, only if:
a] By prior arrangement with our Construction Manager
b] Provided 7 working days notice for deliveries is given to our Construction Manager.
35 | Freight vehicle safety requirements:
a] Ensure that all freight vehicles have the following:
a1] Audible alert to other road users to the planned movement of the vehicle when the vehicle's indicators are in operation.
a2] Prominent signage at the rear of the vehicle to warn cyclists of the dangers of passing the vehicle on the inside.
a3] Properly adjusted class VI mirror's of Fresnel lens to eliminate the near side blind spot.
a4] Side under run guards.
b] Driver training:
b1] Drivers must be trained on vulnerable road users safety through an approved course and hold a current valid Certificate of Competence.
b2] Drivers must hold a valid driving licence and be legally able to dive the vehicle.
c] All freight operators must be registered with the Freight Operator Registration Scheme and accredited to FORS Gold accreditation. Evidence of FORS Gold accreditation must be submitted at least 7 days prior to a delivery.
36 | The Subcontractor must book all deliveries of plant and materials via the M-Site delivery management system and co-ordinate these with our site logistics manager. If the subcontractor or supplier fails to meet the delivery slot they may be turned away from site. No costs will be accepted by BAM for failure to make deliveries. If the unloading takes longer and the next delivery is waiting to gain entry to the site, the unloading may be stopped and the vehicle asked to leave site. It will be the subcontractors responsibility to pay all costs and reschedule the delivery of the remainder of the materials.
37 | Materials are to be delivered to site to suit the installation programme on a 'just in time' basis, but allow for working in loaded out areas. Storage of materials will be strictly by agreement with BAM and be in clearly designated locations.
38 | Sub-contractors are to provide experienced and competent personnel for all their deliveries and unloading activities. This is to include but not be limited to traffic marshals, slinger/signaller, banksman/reversing banksman, general operatives etc.
39 | Deliveries and packages will not be signed for by BAM, subcontractors and suppliers must ensure that labour will be on site to unload and sign for any deliveries.
40 | Adaptions to site hoardings and gates to suit sub-contractor deliveries are to be allowed within the tender return.
41 | The sub-contractor or supplier is responsible for all costs associated with out of hours deliveries and must give 7 working days notice to BAM Site Management of these deliveries. No costs will be accepted should these deliveries be cancelled for any reason.
42 | The sub-contractor or supplier is to allow for any road closures required for plant deliveries etc and accept timing of this procedure. Include management of traffic / pedestrians for all plant / materials deliveries.
43 | Prior to commencing fabrication, checks are to be made on site as to the means of access as no claims will be considered for any lack of knowledge of any restrictions on transporting the materials or equipment into the area of the works.
Site Visit
44 | The sub-contractor is advised to visit site and acquaint himself with the conditions affecting the execution of the works, including local conditions, accessibility of works and site, the nature of the ground, and the supply of and conditions affecting labour and materials. The sub-contractor shall make due allowance for the incomplete nature of the building, including humidity levels, lack of heating etc., that may affect unfixed or fixed materials. The sub-contractor is deemed to have included for all costs arising from the foregoing as no claim for extra payment or extension of time will be admissible due to want of knowledge or inadequate allowance.
Programme
45 | BAM’s programme is issued for information only and identifies the indicative programme requirements for the sub-contractor works and the anticipated start and completion dates of each section. The exact dates will be confirmed by our Project Manager within the agreed periods. The sub-contractor is not to deviate from these dates without the written permission of our Project Manager.
46 | The Main Contractor will require from the sub-contractor a detailed breakdown of the programme period for the purpose of regular progress assessment. Details of anticipated resource involvement will also be required.
47 | On a weekly basis, on a date to be agreed, a progress report including revised programme will be required to be submitted to our Project Manager recording not only the progress of works on site, but the progress of design, placing orders and manufacturing to meet future dates. Key dates should be highlighted for specific events and the capability of meeting these dates stated in these reports. The exact content of these progress reports will be discussed with the sub-contractor prior to their works commencing but should also include a section specifically on the quality of the sub-contractors work and the compliance (or otherwise) with the subcontract requirements. Failure to deliver these reports by 5pm on the business day when the report is required a sum of £500.00 will be withheld until the report is issued to the BAM Project Manager. Due allowance to be made within bid for necessary planning resources to accommodate this requirement and should be clearly identified with subcontract contract sum analysis.
Information Required Schedule
48 | Immediately an order or instruction has been issued, the sub-contractor must produce a schedule of the information required to enable the necessary ordering, manufacture, delivery and installation of his works. This schedule is to itemise the information required, and the date by which that information needs to be issued. It is the responsibility of the sub-contractor to ensure that this is lodged with Site Management at the earliest possible time to ensure compliance with the programme of works on site.
Site Instructions
49 | Site instructions varying the scope or content of the works will be given in writing via a site Instruction to Subcontractor (Form 310-11) from BAM Site Management only. The sub-contractor shall confirm in writing any financial or programme effect resulting from this instruction within 5 days. Under no circumstances are any instructions to be taken from any representative of the client or design team unless the same has been authorised with BAM Project Management. Issue of an instruction does not necessarily result in additional cost or programme implications.
Damage to Sub-Contractors Work
50 | Protection of the sub-contractor's work is the sole responsibility of the sub-contractor until the work is fully and finally completed and handed over to BAM.
51 | Damage caused to the sub-contractor's works is to be reported immediately to the Construction Manager. If damage is witnessed, BAM will act on the sub-contractors behalf against any third party, or arrange for reimbursement as applicable.
52 | Descriptions such as "damage by others" will not be accepted for payment.
Inclement/Adverse/ Exceptionally Adverse Weather
53 | Where the sub-contractor's operations are liable to be affected by weather conditions, they are to ensure that all reasonable efforts are made to maintain progress prior to the works being suspended. Payment for standing time or disruption as a result of inclement/adverse/exceptionally adverse weather will not be made. Any hours lost as a result of adverse weather conditions must be reported to and agreed with our Construction Manager on a weekly basis stating the days on which these delays occurred, together with the hours lost and proposals to mitigate any such delays.
Interfaces
54 | The sub-contractor is responsible for the provision of all interface's with other trades work which will include but not be limited to:
a] Coordinating design with adjacent, preceding and follow on trades
b] Coordinating site activities e.g. deliveries, storage, access to working areas etc with adjacent, preceding and follow on trades
c] Attending meetings as necessary to discuss and review design and site coordination.
d] All costs associated with meeting the interface requirements
Correspondence Procedures
55 | The subcontractor is required to direct all correspondence to our site office, for the attention of the Project Manager unless it is of a financial nature whereby it should be addressed to The Project Surveyor.
Industrial Relations
56 | The sub-contractor is deemed to have employed his labour in a bona fide manner, have all holiday stamps fully paid and only employed labour eligible to work within the UK.
57 | The sub-contractor is responsible for maintaining good industrial relations at all times and shall confirm to the following principles in order to maintain a uniform standard of industrial relations on site:
a] All working rule arrangements to be rigidly adhered to.
b] Any site procedure agreement to be adhered to.
c] Sub-contractors shall be responsible for ensuring that their employees comply with such site regulations as may be introduced from time to time.
58 | The sub-contractor shall employ on the works such persons as are skilled and experienced in the performance of their duties. Each subcontractor, where possible, is to employ local labour. The Main Contractor reserves the right to have any person employed by the sub-contractor, removed from site, if in the opinion of the Main Contractor that person misconduct himself, is incompetent or negligent in the performance of his duties or fails to conform with site requirements or regulations as may have been advised to him.
59 | The sub-contractor is required to take such care as to ensure that the sub-contract work integrate with that of other sub-contractors and for ensuring that full co-operation is maintained with the main contractor.
Record Drawings, O&M Manuals and Health & Safety Files
60 | The subcontract will not be awarded practical completion until all record drawings, operation and maintenance files and health and safety files have been issued on the project EDMS Systems and are signed off by BAM. The first draft of such documents are to be submitted to BAM 6 weeks prior to completion of the subcontractor's agreed programme of works. BAM will take 1 week to check and advise of any errors and amendments that need to be made to these documents and then the subcontractor shall rectify these and reissue within 1 week which will be 4 weeks prior to completion of the subcontractor's agreed programme of works. Any costs levied at BAM for failure to obtain practical completion due to non submission of the foregoing will be deducted from the subcontractor's account.
61 | The subcontractor shall record the 'as-built' position of all works etc., where they differ from the working drawings. 'As-Built' shall mean incorporating all requirements of the BAM Instructions together with further variations and minor alterations the Subcontractor may make by agreement with BAM to overcome site and erection problems including changes arising from site setting out.
62 | The subcontractor shall co-ordinate the preparation of his 'as-fitted' or 'as-built' record drawings for the submission of such drawings to BAM and the Employer's Agent or Consulting Engineers in accordance with item 60 above.
63 | The subcontractor shall assemble in conjunction with BAM, the Employer's Agent and the Consulting Engineers operating and maintenance manuals including test certificates and commissioning results materials supplied giving such information on materials and equipment including installation diagrams, operating and maintenance instructions, and names and addresses of suppliers as is necessary to enable the Employer's personnel to operate and maintain the building.
64 | The subcontractor shall provide four fully co-ordinated copies of such manuals and drawings to be submitted to BAM for submission to the Employer's Agent or Consulting Engineers in accordance with item 62 above and relevant subcontract documentation. Allow for making arrangements for and any necessary practical instruction of the Employer's personnel as detailed in the subcontract documents prior to practical completion.
65 | The subcontractors method statement will also include a description of the final cleaning procedure prior to Practical Completion. BAM expects that the completed buildings will be offered for Practical Completion in an exceptionally high standard of cleanliness and the Practical Completion will be refused unless the subcontract works reach this standard.
Access for Off Site Material Inspections
66 | The subcontractor shall facilitate access of all off site materials as and when required by BAM, Employer and/or the Design Team including access to any sub-subcontractor or suppliers workshop/premises.
67 | Provision should be made for costs associated with inspection of off-site materials including transport and accommodation.
Meeting Attendance
68 | The subcontractor will attend all necessary design, progress, quality, financial and health and safety meetings deemed necessary by BAM Project Management and his representative shall be a person relative to the discipline of which the meeting is concerned.
Ordering Materials
69 | The subcontractor should note that the ordering of materials or other resources using quantities stated in the enquiry document is at the subcontractor’s own risk.
Production Information
70 | Production Information / Shop Drawings must be provided by the subcontractor where required by the Design Team Specification, Employer’s Requirements and the enquiry document. The subcontractor is to be responsible for the final design.
71 | When preparing a master programme the subcontractor shall make reasonable allowance for completing production / shop drawings, builder's work drawings, inspection by the Employer's Agent and any subsequent amendment[s], resubmission[s] and reinspection[s].
72 | If submitted production information differs from the Employer's Requirements architects drawings, specifications or schedules, each such difference must be subject to a request for substitution or variation, supported by all relevant information.
73 | BAM will issue all drawings, specifications and reports either by the project EDMS Systems, email or compact disk and the subcontractor will ensure he has the facility to read these files which will be PDF or DWG and is able to print them off for his own distribution. BAM will not entertain any additional costs associated with the foregoing.
74 | The issue of a comment on a subcontract drawing or document by the employers agent shall not be treated as having cost or programme implications without being instructed in writing by BAM. It is the subcontractor’s responsibility to identify these changes, in writing, prior to the incorporation where such would have a cost or programme affect. Failure to do so will result in any change being treated as design development at the cost of the subcontract package.
75 | Subcontractor is to allow for connection, to use and operation of the electronic data management systems including licenses.
76 | The Subcontractor will and shall procure that all of his Sub-Subcontractors and suppliers will, use the project electronic data management systems including licenses.
Copyright
77 | The subcontractor shall be responsible for acting upon and resolving or avoiding all issues of copyright which emanate from them or their suppliers works that are under the subcontractors control. This will include:
a] All information cross issue matters, including responsibility for ensuring that BAM and the Employer's rights are where reasonably possible maintained on all subcontract or other prepared documentation for this project.
b] Ensuring wherever possible it is under the subcontractor's control and that BAM, the Employer and the Professional Team are not liable for copyright infringement.
78 | The subcontractor shall ensure that no copyright obligations which may effect the execution of the works on cost and programme should lie with BAM, the Employer or the Professional Team where these could have reasonably been foreseen and resolved or avoided by the subcontractor without such effect.
Security / Safety / Protection / Fire
79 | The subcontractor shall take all necessary action to prevent personal injury, death and damage to the works or other property from fire. Comply with the Joint Code of Practice 'Fire Prevention on Construction Sites' published by the Building Employers Confederation and the Loss Prevention Council. Where work necessitates the use of naked flames in enclosed spaces, a portable fire extinguisher is to be provided in all areas where work is taking place. Fire escape routes are to be kept unobstructed at all times. The subcontractor is deemed to include for all costs involved in complying with these requirements.
Nuisance Generally
80 | The subcontractor shall prevent smoke, dust, fumes, spillage, pollution of waterways and other harmful activities. No bonfires will be allowed. Dispose of waste foodstuffs [e.g. from mess rooms] in a manner that does not encourage flies and other pests. Comply with any reasonable requests from the public and adjoining owners.
Noise
81 | The subcontractor shall keep noise to as low a level as can be practicably attained. Avoid the use of noisy tools [e.g. percussion tools] or restrict their use to agreed times. Fit compressors, percussion tools and vehicles with effective silencers of a type recommended by the manufacturers of the compressors, tools or vehicles. Use mufflers and acoustic enclosures when necessary. The use of radios, CD players and the like will be prohibited. Comply with BS 5228 'Noise control on construction sites'. No noise will be permitted at weekends unless specifically approved by the Employers Agent. The subcontractor will comply with statutory and local authorities with regard to noise control (reference City of London Code of Practice for Deconstruction and Construction Sites; 9th Edition).
82 | The subcontractor's attention is also drawn to the 'Control of Pollution Act 1974 - Sections 60 and 61'. The Local Authority may impose a maximum noise level for the site and also lay down restrictions on the types of plant to be used and the methods of working to be adopted. It is the subcontractor's responsibility to ascertain if any impositions or restrictions will apply to the site for his works and to submit or at very least assist in the application to the Local Authority for prior consent. All costs associated with noise and vibration assessments and compliance with the above will be deemed to have been included.
Electrical Interference
83 | The subcontractor shall not cause any interference to radio and TV receivers, computers or other instruments in adjoining properties.
Electromagnetic Interferences
84 | The subcontractor shall take all necessary precautions to avoid excessive electromagnetic disturbance of apparatus outside the site.
Laser Equipment
85 | The subcontractor is to install, use and store construction laser equipment in accordance with BS EN 60825
Vibration
86 | The subcontractor shall prevent any form of shock or vibration being transmitted into the retained structure, cladding or surrounding buildings.
Water
87 | The subcontractor shall prevent damage from storm and surface water as a direct result and consequence of his works.
Keep Highways Clean
88 | The subcontractor shall prevent soils and debris resulting from their works being deposited on the public highway and immediately remove any unavoidable deposits and pay any Local Authority charges for repairs etc. Any roads / paths with soils or debris arising from the subcontract works shall be swept and kept clean throughout the day as required.
Trespass by Plant
89 | The subcontractor shall not permit [unless permission has been previously obtained in writing] plant to encroach over or upon adjacent property; trespass by crane jibs into airspace is a particular consideration. Full details of mobile crane siting, height, jib length and agreements reached with adjacent property to be submitted before work commences.
Site and Adjacent Property
90 | The subcontractor shall protect site and any existing buildings or property on or adjacent to the site and not forming part of the works that may possibly be damaged or affected by the subcontract works. Should damage occur the subcontractor will be required to cover any repairs costs. Equally the subcontractor will be required to clean off any construction waste from the existing boundaries & structures and offer back to the main contractor in the same condition as provided at contract commencement. Additionally if the subcontractor requires any existing hoardings and or barriers to be moved for working space requirements the subcontractor will be required to pay all associated costs equally should same be damaged as a consequence of site works the subcontractor will be required to meet all repair costs.
91 | Compliance with all Principal Designer requirements, planning authority restrictions, and party wall agreements.
Planted Areas
92 | The subcontractor shall protect all plants and cultivated areas including associated hard landscaping and features that may possibly be damaged or affected by the subcontract works.
Existing Planted Areas
93 | Any plants damaged by the subcontractor's works shall be replaced with healthy stock from approved nurseries at the subcontractors cost. Established trees, if disfigured or permanently damaged by the subcontractors works, shall be replaced at the subcontractors cost. Any such tree shall be the responsibility of the subcontractor until healthy new growth is assured.
Paved Areas
94 | The subcontractor shall protect all site roads, paths, paved areas and access routes that may possibly be damaged or affected by the subcontract works. Should any of these areas including existing buildings be damaged the subcontractor will be expected to pay the full repair and or replacement cost to the same specification or better
Stability
95 | The subcontractor shall accept responsibility for the stability and structural integrity of the works during the subcontract works and support as necessary. Details of design loads may be obtained from the Structural Engineer.
Publicity
96 | No advertisement of any kind will be permitted on site except with the written permission of the Employers Agent which can only be obtained through BAM.
97 | The subcontractor shall not at any time take any photographs or video recordings of the works or part thereof for purposes other than to demonstrate progress, unless the subcontractor has obtained the prior written permission of the Employers Agent which can only be obtained through BAM.
98 | The subcontractor shall give no statement, photographs or information of any kind or no such information shall be communicated to the press, radio/TV companies, company magazines, etc., unless the subcontractor has obtained the prior written permission of the Employers Agent which can only be obtained through BAM.
Pedestrian Access and Use of Site
99 | Upon arrival to the development, all personnel must report to the BAM Security Hut. All new comers to site must be inducted before stepping onto site. See Health & Safety Compliance Item 1 for notes on site induction.
100 | Other persons visiting the site in connection with the works must report in the first instance to the BAM Security Hut and sign in with reception upon entering and leaving the site. Whilst on site, visitors must be accompanied at all times by a member of the sub-contractors staff who have undergone the site induction systems and have escort authority. All visitors must wear the required Personal Protective Equipment. Work people or visitors who arrive at the site and whose name does not appear on the sub-contractors list may be delayed or refused access to the site.
101 | The subcontractor is to ensure that all operatives sign in & out each day using the biometric hand scanning security system. Failure to scan in and out will result in the operative being removed from site. Additionally any operative found scanning in and out for anybody other than themselves will automatically be removed from site on a permanent basis
102 | Operatives must adhere to the designated pedestrian routes and security procedures on site.
Maintenance of Existing Services
103 | Before commencing site operations the sub-contractor shall ascertain the location of all services, drains or sewers and inform our Project Manager. The sub-contractor shall also uphold, maintain and protect all pipes, ducts, drains, sewers, overhead cables etc during the execution of the works and make good any damage or pay any costs or charges in connection of same. Immediately any damage is caused the sub-contractor shall notify our Project Manager.
104 | All existing services shall be maintained in good working order. Any break in the service, howsoever caused, shall be made good at the sub-contractors expense.
Archaeological Investigation
105 | Any items found on site of archaeological interest must be immediately handed to BAM's Site Management for transmission to the Local Archaeological Trust.
Bonds / Guarantees
106 | BAM Performance bond - subcontractor to agree to wording unamended
107 | BAM Parent Company Guarantee - subcontractor to agree wording unamended
108 | Subcontractor warranties - subcontractor to agree wording unamended
109 | All bonds guarantees & warranties to be executed & returned to main contractor within 14 days of issue
110 | Acceptance of Liquidated & Ascertained Damages as laid down in the contract documents
General Items
111 | Acceptance of cost or lost time due to instruction to cease specific operations due to noise, dust or other pollution.
112 | The subcontractor will be responsible to retrieve all works information from the relevant EDMS system including other subcontractors information which may interface and or co-ordinate with your works. BAM will not instruct the subcontractor to retrieve "other" subcontractors information or to implement same within their design, manufacture or construction works on site.
113 | The subcontractors work is to comply with all relevant British Standard latest regulation and codes of good practice. Subcontractor to comply with the design teams specifications and drawings, it is the Design Team's responsibility to ensure that these comply with British Standards. Subcontractor (as the specialist) is to advise Bam if they notice anything that they believe may not be compliant
114 | Samples and mock ups to be provided in accordance with the specification.
115 | The Subcontractor has included for obtaining approval from the Design team etc. prior to manufacturing materials in accordance with the programme requirements and in order to prevent any delays to the construction programme i.e. if extra tests, additional works, further samples etc. are required to satisfy them of their scheme then the Subcontractor is deemed to have included for these at no additional cost. No such approval, comment or otherwise shall relieve the Subcontractor of their responsibility for adhering to the programme. Subcontractor has allowed for all costs associated with the design, shop drawings, mock ups etc. Along with design work to any associated interfaces.
116 | The subcontractor is responsible for any design errors affecting the works, or its impact on other trades, by way of failing or by those of other interface with subcontractor design packages
117 | Subcontractor has made due allowance with regard the quality control of workmanship and materials including regular inspections in conjunction with BAM Site Management
118 | The Subcontractor is to allow for any necessary labours, notching, trimmings, scribing, packing, supports, openings, chases, builderswork and the like, as is required, to overcome construction tolerances, or to comply with the new / existing structure. All setting out and marking out of builders works to be completed by the subcontractor.
119 | The Subcontractor has allowed for all holes, sinkings, plugging and screwing and similar as necessary into backgrounds of concrete, reinforced concrete, brick, block, steel, stonework, and the like so as to provide suitable fixings etc
120 | Subcontract design must be performed and comply within the construction tolerances of all other elements, including the existing structure.
121 | Where the consultants drawings, specifications and schedules refer to the "contractor" the subcontractor is to assume in each and every instance that "contractor" means "subcontractor" and that their tender should comply accordingly.
122 | The subcontractor is to identify any discrepancy in the tender documentation and refer this matter to BAM for direction. In the event a discrepancy is not identified to the contractor in the tender period, the Subcontractor will be deemed to have made due allowance for the most appropriate solution determined solely by BAM.
Non Compliance
123 | Failure to comply with any of the above may result in BAM carrying out the works / facility on behalf of the subcontractor and deducting all direct and indirect cost of that service from the subcontractor's account.

## Health & Safety Compliance
25 Cannon Street
Supplementary Conditions
Health and Safety Conditions
Item | Description
Health & Safety
1 | The Sub-Contractor will comply at all times with all current Statutory Provisions relevant to their operations, including but not limited to:- • Health and Safety at Work, etc. Act. • The Consumer Protection Act. • Management of Health and Safety at Work Regulations. • Personal Protective Equipment at Work Regulations. • Provision and Use of Work Equipment Regulations. • Manual Handling Operations Regulations. • Control of Substances Hazardous to Health Regulations. • The Construction (Health, Safety & Welfare) Regulations. • Consultation with Employee Regulations. • Working Time Regulations and all other current relevant statutory provisions.
2 | The sub-contractor shall have a fully competent and suitably experienced Foreman / Supervisor on site at all times in charge of operations on site at all times, who will act as the site point of contact for all matters relating to health, safety and welfare. This person is to be identified prior to commencement; supervisors must have received a minimum of two days’ Health and Safety training provided by Construction Skills or an affiliated training provider. Evidence of the occupational health monitoring undertaken by the employer must be provided. All instructions will be directed through the Supervisor. The Supervisor plus one other nominated person will be required to act as Fire/Liaison Officer on behalf of the sub-contractor’s employees and attend the regular site meetings as required. The sub-contractor will be deemed to have included for the foregoing within the tender.
3 | Safety helmets and all other 5 point P.P.E. must be provided by the sub-contractor for all their operatives and visiting personnel to site and be worn at all times on site. The sub-contractor is reminded that all operatives are to wear the appropriate clothing for their works including gloves, protective safety footwear, high-visibility jackets, vests, face-fit respiratory equipment and fitted harnesses. All P.P.E. must be suitable and fit for purpose with operative trained in its use and maintained and fitted correctly. Trainers are not allowed to be worn on site. Note: Safety helmets are to be a consistent colour.
4 | NO P.P.E, NO CSCS CARD OF CORRECT COMPETENCE FOR TASK AND NO HEALTH AND SAFETY TRAINING = NO WORK
5 | As well as holding the right CSCS competency card for the task, the sub-contractor must have the following standards of health and safety training: • Operatives - CITB Health and Safety Awareness: One Day • Supervisors - CITB Site Supervisors Safety Training Scheme: Two Days • Managers - CITB Site Manager Safety Training Scheme: Five Days • Directors - CITB Directors Role for Health and Safety or IOSH Directing Safely: One Day
6 | Should any delivery vehicles be required to drive onto site, the drivers must wear the all necessary P.P.E. required before leaving the vehicle.
7 | All operatives operating disc cutting, grinding, burning, welding or other noisy equipment must wear the appropriate eye and ear protectors. Failure to comply with the above instruction will result in either a removal of the operative from site or ultimately determination of the sub-contract for non-compliance.
8 | In the event of any disputes arising, BAM Construction Ltd's Safety Officers decision will be binding on all parties.
9 | All electrical equipment must have been ‘PAT’ tested and a copy of the electrical certificate issued to BAM. All mechanical equipment must be delivered to site with a certificate of worthiness and be suitable for purpose to which it is to be used. All diesel drums must be stored within a bunded area.
10 | Certificates of thorough examination for lifting equipment must be issued to BAM prior to any operations taking place.
11 | Operators of mobile work equipment must hold as a minimum a recognised certificate of training achievement (CTA) for the category for which they have been trained and tested. All trainers must be CITB accredited.
12 | Only trained signallers are to give instructions to any crane operator and only trained slingers are to attach loads to any crane.
13 | Drivers of any vehicle or machine being loaded by excavator must vacate the vehicle/machine during loading.
14 | All contractors are to hold weekly toolbox talks, wherever possible these should be relevant to site operations. BAM may on occasions request certain subjects to be addressed. Records of toolbox talks must be forwarded to BAM, which must include at least a monthly environmental tool box talk. In addition all Health and Safety statutory paperwork must be completed and placed into the project live files prior to starting on site and updated on a weekly basis (before 12pm on a Monday).
15 | BAM will hold regular site safety review meetings and safety committee meetings, all contractors must ensure they are represented at these meetings.
16 | Any persons/contractor committing a misdemeanour relative to health & safety, will be issued with a health & safety improvement notice. The details of which must be rectified and actioned immediately.
17 | All accidents, near misses and dangerous occurrences must be reported to BAM Construction.
18 | Smoking will NOT be allowed on site.
19 | Operatives working in an unsafe manner may be permanently excluded from site for the safety of themselves and others.
20 | All subcontractors must carry out daily briefings / 'safe to start' briefings at the beginning of each working day. Records of these briefings must be retained for BAM inspection on a monthly basis.
Control of Substances Hazardous to Health [C.O.S.H.H.]
21 | In addition to the Control of Substances Hazardous to Health Regulations [issued under the Health and Safety at Work, etc. Act] the subcontractor shall give advance notice in writing to BAM warning of any "substances hazardous to health", provide BAM with a copy of the "assessment of health risks" as defined in the Regulation, specify the hazardous substances, their location and the dates when they could be encountered. Provide a similar notice to BAM about any hazardous substances to be used in works carried out after practical completion of any part of the works [such as maintenance, cleaning, etc]. Provide copies of notices given under this clause to BAM.
22 | In order to comply with the C.O.S.H.H. Regulations [1988], the sub-contractor must provide detailed information on the safe use, storage and handling of all goods and materials supplied to the site, irrespective of whether the goods and materials are manufactured directly by the sub-contractor or a third party.
23 | The information must be provided to our Construction Manager on site in writing before deliveries are made, if special precautions/storage facilities are required at the time of delivery. No work liable to expose persons to substances hazardous to health shall be undertaken without proper precautions having first been taken.
24 | Any product, which has flammable or toxic properties and is to be incorporated into the works, either for temporary or permanent operations is to be advised to the site management prior to its delivery to site.
25 | The sub-contractors attention is drawn to the requirements of the Consumer Protection Act 1987 in respect of providing information on the safe use, storage and handling of materials on site.
Permits to Work
26 | “Permits to Work” must be obtained before commencement for all maintenance, repair or installation works to elements of fabric, plant and equipment. They will be issued under the signature of, and controlled by, the site designated authority. If the sub-contractor identifies a potentially hazardous situation, he shall notify the site designated authority and subject to a separate “HOT WORK PERMIT”.
27 | The sub-contractor is to be aware of arrangements concerning fire precautions on site and include for cold cutting techniques in the first instance. When using and storing gas on site, Subcontractors are to supply separate locked cages for full and empty gas cylinders which are to be stored in separate locations.
28 | Welding trolleys must have appropriate fire extinguishers affixed and ready for use and all hot work applications must also have suitable extinguishers adjacent to the workplace.
29 | Due to the control exercised by the Electricity at Work Regulations Act 1989 in no circumstances shall the sub-contractor work on live systems without such written consent. Before any work is commenced which requires the isolation of electrical equipment under site control, approval must be granted by the site designated authority.
Safety Risk Management
30 | The sub-contractor will be required to provide a project specific method statement and risk assessment for their works package prior to site commencement. All RAMS are to be issued as a pack including all necessary paperwork, this is to include but not be limited to risk assessments, method statements, HAVS, COSHH and manual handling.
31 | The main objectives are to identify the responsible person, consider the hazards of all work operations, including those to any other parties, devise alternative strategies for the controlling of these risks and to relate these alternative strategies to the general decision making framework. The objective of risk management involves the following strategy:-
a] Risk identification, e.g. experience, inspection etc.
b] Risk evaluation and assessment, e.g. risk to others.
c] Risk control, e.g. visual checks, instruction, training, immediate remedial action where necessary, implementation of emergency procedure plan, i.e. safe shutdown of plant and equipment, procedures for notifying and directing emergency services on site.
Site Induction
32 | All personnel must complete an M-site pre-induction prior to undertaking BAM's induction training for the development and collecting their security pass. Please note all personnel must take with them their national insurance number and CSCS card to receive their induction training. Inductions will be carried out every Monday, Tuesday & Thursday. All personnel must be present at the induction room at 8.00am to commence their induction training at 8.30am. All operatives must have been inducted by their employing company and have received a RAMS briefing prior to attending BAM's induction. A member of the personnel's management team must attend site inductions with a signed copy of the Initial Health & Safety meeting minutes for the project.
33 | A charge of £5.00 will be incurred against the sub-contractor for each security pass issued (this will be required if the operative does not have a CSCS card with a chip) & £15 should a replacement be required
34 | The sub-contractors attention is drawn to BAM Construction's Company Safety Policy and BAM Construction's Health and Safety Standards for sub-contractors.
35 | A copy of the sub-contractors current safety policy is to be submitted prior to commencement on site which is to be lodged with BAM Construction Ltd's Safety Department for reference purposes, with a copy on site.
36 | All subcontractors will be required to complete other prequalification questionnaires for approval by BAM before work commences.
37 | Operatives discovered failing to comply with the requirements set out in the site induction, this document or generally acting in an unsafe manner may be required to be re-inducted at a charge of £30 per man.
C.D.M. Regulations
38 | The sub-contractor shall comply with The Construction Design & Management Regulations 2015 in respect of the duties and powers required under those regulations.
39 | The sub-contractor shall allow for allocating adequate resources to ensure compliance with and the implementation of the Regulations under the supervision of a competent person experienced in the requirements of all matters related to Health & Safety at Work.
40 | The subcontractor shall allow and afford his assistance to BAM in developing and implementing the Health and Safety Plan in relation to the works on site ensuring it always reflects the current situation.
41 | The sub-contractor shall ensure that all site operatives and other persons authorised to be on site are aware of and comply with the requirements of the Health and Safety Plan.
42 | The sub-contractor shall ensure all information which should be included in the Health and Safety File is provided to BAM.
43 | In accordance with the current Construction Design and Management Regulations 2015, the sub-contractor will be required to produce technical literature, CV's of staff and details of similar projects to prove their competence as a "contractor", prior to the placing of an order.
44 | The sub-contractor will also be required to produce method statements, risk assessments, drawing and maintenance manuals [where applicable] throughout the progress of the works as well as any considerations and information relevant to the Health & Safety File.
45 | All sub-contractors will be required to complete a Health & Safety pre-qualification assessment, to prove their competency, before an order is placed.
Environmental
46 | The sub-contractor will comply with all current Statutory Provisions relevant to their operations:-
· Environmental Protection Act (Waste Control).
· Water Resources Act
· Control of Pollution (Oil Storage) (England) Regulations
· Hazardous Waste Regulations and all other current waste legislation.
47 | The sub‑contractor shall acquaint himself with the current Control of Pollution Act and any amendment or notices, and with any Local Authority or Statutory requirements relating to the control of the emission of noise from this project.
48 | The sub-contractor is to ensure that all materials emanate from legal and sustainable sources.
49 | The subcontract is to issue to BAM all relevant documentation in order to achieve the targeted credits to achieve BREEAM
50 | All sub-contractor BREEAM information to be issued on a progressive basis and at least 3 months prior to completion of the sub-contract works.
51 | The subcontractor must comply with all measures implemented on site to achieve a Considerate Constructors Scheme score of 40 or over.
52 | All Non Road Mobile machinery (NRMM) above 37kW power rating should meet a minimum EU Stage IIIB emission criteria of Directive 97/68/EC. Subcontractor to provide engine plate details for all NRMM to enable the site register to be completed.

## General Site Set Up Compliance
25 Cannon Street
Supplementary Conditions
General Site Set-up Conditions
Item | Description
Accommodation / Hutting / Storage / Welfare
1 | The subcontractor shall allow for providing all his own site offices, containers, storage facilities, tool boxes, etc. necessary to supervise and manage the works. The security of these facilities will be the responsibility of the subcontractor. The location is to be agreed with BAM. There will be limited office space for subcontractors within the BAM set-up, however this is to be designated by BAM and not guaranteed.
2 | A connection of power to the subcontractors site offices will be undertaken by BAM and the subcontractor is to include within his quotation a cost of £500.00 per connection for this service.
3 | Should the subcontractor require power to any other container, hut, storage facility, etc. then BAM will provide this at a cost of £500.00 per connection plus any builderswork necessary to install this supply e.g. trenches, ducting, etc.
4 | The subcontractor is then responsible for the electrical installation from the metered supply provided by BAM.
5 | BAM will monitor the metered supply on a monthly basis and deduct the cost of supplied power from the subcontractor's account. The subcontractor shall make due allowance within his quotation for this charge.
6 | The subcontractor shall make all his own provisions for any necessary telecom, power, water and drainage supply required to his site accommodation. The subcontractor shall not use BAM phones, fax or photocopying facilities and will be charged for doing so.
7 | BAM will provide and maintain Drying Rooms, Mess Rooms and WC facilities for male & female subcontract personnel. The subcontractors will be responsible to provide their own secure storage within the Drying Rooms. Padlocks are to be provided by operatives and any items will be stored at the operatives own risk.
8 | BAM will ensure that the welfare areas are kept in a clean and tidy state by cleaning at least once a day. This facility is provided for the benefit of all site personnel, however historically this has been abused by a minority of personnel to the detriment of the rest of the site and the welfare person in charge of maintaining a clean environment. If abuse occurs and graffiti of any nature appears on any surfaces within the welfare facilities the cost of BAM remedying such abuse will be charged to the relevant subcontractor. This will not be open for discussion or debate and although BAM will endeavour wherever possible to identify the culprit[s] behind such antisocial behaviour, where proof cannot be obtained, then equal contribution will be sort from the subcontractors.
9 | Notwithstanding the above any person[s] found mistreating the welfare facilities will be removed from site immediately.
10 | Eating or drinking anywhere other than in the mess room / canteen facility is strictly forbidden.
11 | The subcontractor accepts any liability for, and costs in association with, the relocation on site or removal from site of the subcontractor's site offices, containers, storage facilities, wheeled tool boxes, etc. deemed essential by BAM to progress the works.
12 | Full compliance with BAM logistics details including maintaining fire escape routes and pedestrian routes including working out of hours to maintain routes and re-routing where necessary.
Car Parking
13 | There will be no vehicle parking permitted on site, all subcontractors parking costs to be included within their tender
Electricity
14 | BAM will provide a temporary 110V electrical supply to locations to be advised by BAM.
15 | The subcontractor shall provide any specialist power supplies that he requires over and above 110V and include the cost of this plus advise of the nature of this requirement within the quotation return. The subcontractor must include for cable management of all leads and supplies provided by the subcontractor, this is to include but not be limited to tie wraps, cable hooks and ramps as required.
16 | BAM will provide safety lighting to the main core & circulation areas.
17 | The subcontractor shall provide any special lighting or task lighting that he requires to execute his works. Any special or task lighting installed by the subcontractor shall be capable of adaptation if required to permit the progress of the subcontractor and other trades work.
18 | The subcontractor shall not seek reimbursement from BAM for down time due to any loss of power supply irrespective of the cause of that loss.
Water
19 | BAM will provide a maximum of 25mm diameter mains pressure water supply to a location to be advised by BAM. The subcontractor is deemed to have satisfied himself in respect of the adequacy of this supply.
20 | The subcontractor shall provide any specialist water supplies that he requires over and above item 19 and include the cost of this plus advise of the nature of his requirement with his quotation return.
21 | The subcontractor shall allow for all transportation and storage of water required for his use on site from the supply provided by BAM in item 19 above.
22 | The subcontractor shall not seek reimbursement from BAM for down time due to any loss of water supply irrespective of the cause of that loss.
Materials Storage
23 | The subcontractor shall be responsible for the safe storage of his own materials whether temporary or for permanent inclusion into his works. The storage of these materials should be in accordance with the manufacturers recommendations and BAM Site Management may reject any such material that they believe has been detrimentally affected by non-conformance with the manufacturers recommended storage requirements.

## General Site Attend Compliance
25 Cannon Street
Supplementary Conditions
General Site Attendance Conditions
Item | Description
Waste Management
1 | A third of all accidents on a building site are as a result of slips, trips and falls which is why BAM is determined to instil into subcontractors the absolute necessity to maintain a safe, clean and tidy site. Historically subcontractors have generally failed to comply with this and it is unfortunate that they are only galvanised into taking action when they feel the direct financial impact of their failure to comply with the foregoing. BAM believe that the safety of all site operatives and personnel takes priority over anything else on a construction site and will not hesitate to take whatever action is required to maintain that appropriate environment.
2 | BAM maintain that by reducing lost time as a result of accidents and keeping a safe, clean and tidy working environment actually improves subcontractor productivity a consequence of which is improved subcontractor profit.
3 | The following are measures that the subcontractor must take 'as a minimum' to eliminate the above statistic together with the penalties for non-conformance:
4 | The subcontractor shall dispose of all rubbish, debris, surplus material, spoil and all other waste resulting from their works into bins provided by BAM at central locations in order to keep the site and works in a safe, clean and tidy state.
5 | The subcontractor shall remove all hazardous waste from site on a daily basis.
6 | The subcontractor shall remove all packaging including pallets, stillages, cable drums and excessive surplus material from their works from site on a daily basis to keep the site and works in a safe, clean and tidy state.
7 | All subcontract related waste, rubbish, dirt and residues is to be removed from voids and cavities in the construction before closing in.
8 | BAM may decide to employ a waste management company to control waste and will seek a financial contribution from the subcontractor to finance this if the subcontractor does not comply with the above.
9 | The Subcontractors allowance for works in connection with waste removal must be a realistic one as any additional costs for labour and management time provided by BAM over and above the subcontractors quoted allowance will be deducted from the subcontractor's account. The minimum deduction for waste in skips provided by BAM that either:
a] exceeds the subcontractors skip allowance, or
b] should not be in that skip
will be:
● 4 hours Site Management @ £75.00 per hour
● 2 hours Project Surveyor @ £75.00 per hour
● Minimum of half of one skip @ £350.00 per 7 yard skip
● Any Sundry Cost [photographs, consumables, etc.]
● All Company Tied Costs
● Overhead Recovery
10 | If the subcontractor fails to remove all his own generated rubbish, debris, surplus material, packaging, spoil and all other waste in accordance with item 4 on a daily basis, then BAM will employ labour to do so. In such circumstances the procedure will be as follows:
a] BAM site management to photograph all waste not cleared to skips from subcontract works undertaken the previous day.
b] These photographs will be issued under cover of a form entitled 'Subcontract Request Notice' to the subcontractor's foreman by 12 noon of the following day on which the waste, rubbish, etc was generated.
c] The subcontractor shall then without question ensure that that waste, rubbish, etc is cleared by the end of the day of issue of the 'Subcontract Request Notice'. If it is not, BAM will remove and all costs arising will be charged to the subcontractor in accordance with item 6 above.
d] Failure to comply with this Subcontract Request Notice will result in BAM employing all labour and procuring the necessary plant and materials required to safely remove this waste, rubbish, etc. the cost of which will be deducted from the subcontractor's account.
e] The minimum deduction from the subcontractor's account for failure to comply with items a to d above will be:
● 4 hours Site Management @ £75.00 per hour [2 hours deducted irrespective of whether subcontractor attends to Subcontract Request]
● 2 hours Project Surveyor @ £75.00 per hour
● 4 hours Labour @ £25.50 per hour
● 2 hours Forklift & Driver @ £65.00 per hour
● Sundry Plant [cranage, wheelie bins, etc.]
● Minimum of half of one skip @ £350.00 per 7 yard skip
● Any Sundry Cost [photographs, consumables, etc.]
● All Company Tied Costs
● Overhead Recovery
11 | Ensure that non-hazardous material is disposed of at a tip approved by the Waste Regulation Authority. Remove all surplus hazardous materials and their containers regularly for disposal off site in a safe and competent manner as approved by the Waste Regulation Authority and in accordance with the relevant regulations. All waste transfer documentation to be retained on site. Any costs levied at BAM by the skip / tip companies for disposing of hazardous material in skips provided for non-hazardous waste will be deducted from the account of the subcontractor disposing such waste.
Site Deliveries
12 | The subcontractor must have the means and resource on site to safely unload his materials. If this resource is not available and BAM has to procure a labour and plant resource to undertake this operation so as not to cause congestion to delay to other deliveries then all direct and indirect costs associated with this will be deducted from the subcontractors account.
13 | The subcontractor will liaise with BAM's gateman / traffic controller and allow within their tender for all necessary traffic management to manoeuvre vehicles on, off & around the site. As a minimum the subcontractor should have trained traffic marshals with labour / banksman in attendance as necessary to manage the vehicle on, around & off the site. The subcontractor will need to consider the use of barriers, traffic cones, signage & suitable lighting to ensure the activity is undertaken in a safe manor
14 | The subcontractor shall ensure that all their vehicles leaving site whether operatives or deliveries do not in anyway cause damage or release anything that may result in damage, dirt or staining to surrounding roads and footpaths. If this occurs and the subcontractor fails to attend within a reasonable time period then BAM will undertake the necessary works and deduct the cost of same from the subcontractor's account.
15 | The subcontractor is to consider the availability of the turning space into the site access routes. The subcontractor should consider this & price the appropriate delivery vehicles to ensure the neighbours buildings and services are not damaged. Any damage will be chargeable to the subcontractor.
16 | Delay costs will be the subcontractors responsibility if deliveries are affected by local authority bodies statutory restrictions or road closure
17 | Due to the restrictive nature of the site, materials should be where possible delivered premixed to site
Unloading & Distribution
18 | BAM will not be erecting a tower crane on the project. Any specific craneage requirements are to be discussed and agreed with BAM direct. BAM will be providing vertical lifting by either the existing passenger lifts (lifts 3&4), the goods lift, the car lift and an external goods hoist. The periods each of the aforementioned will be available for are specified on Programme Restraints Statement Appendix B , however priority will be given to critical programme activities as decided by BAM.
19 | Additional cranage, hoisting and lifting requirements required before or after the above dates will be provided by the subcontractors including all manual distribution.
20 | Any cranage, hoisting or lifting requirements that are beyond the capacity of the tower crane are to be provided by the subcontractors
21 | Where BAM are providing the craneage, we will provide 1 number driver & banksman, the subcontractors will be responsible for providing banksman & slingers from delivery to place of work. Each lift which is unsighted from unloading to place of distribution will require a minimum of 2 banksman / slingers. Radio's to be provided by the subcontractor to communicate with BAM crane drivers.
22 | The subcontractor is to provide crane equipment compatible with BAM crane block to include but not to be limited to chains, slings, straps, skips, forks, lifting frames, boat skips, man cage. In addition the subcontractor must provide all other lifting accessories such as whistle, chin straps, segregation and any other lifting specific PPE required for their lifting operations.
23 | Loading platforms in or around the building to be provided by the subcontractor
24 | Use of craneage (where provided by BAM) outside the agreed site working hours must be agreed first with BAM site management. The subcontractor will be charged for all costs associated with operating the cranes outside the agreed site hours.
25 | BAM will provide 1 hoist for goods use only booked on a "first come first served" basis for material distribution. Note BAM reserve the right to allocate the hoist for key works at our discretion. BAM will not be held responsible for any subcontractor delays for labour, material, plant or equipment distribution should the hoist be in use. This will be available on as detailed in the appendix B
26 | Access to & from the work place before or after the hoist erection / dismantle dates will be via the staircases
27 | Any adaptions to the hoist for special deliveries will be charged to the subcontractor
28 | BAM will provide 1 number driver per good hoist
29 | Any hoisting or vertical distribution requirements that are beyond the capacity of the hoists are to be provided by the subcontractor. Distribution across or to areas with changes in level of slabs or areas not serviced by the hoist is to be allowed for by the subcontractor.
30 | Use or the hoists outside the agreed site working hours must be agreed first with BAM site management. The subcontractor will be charged for all costs associated with operating the hoists outside the agreed site hours.
31 | The subcontractor is responsible for unloading materials to agreed storage areas as defined by BAM Site Management. Protection of stored materials is by the subcontractor.
32 | The subcontractor is to satisfy himself that he is aware of the size and restriction of the hoist including cage sizes, etc.
33 | The subcontractor is responsible for loading out and distributing materials to the face of his works both horizontally and vertically. The subcontractor is to include for electric pallet trucks and positive lifting techniques suitable for the subcontract works.
34 | Deliveries should be made on a “just in time” basis to meet the progress of the works the subcontractor is to make allowance for delivery via the most appropriate type of vehicle ie. Hiab lorry, rear unloader, side unloader, ridged back lorry. Your bid should allow for materials to be moved to suit site progress & sequence of other activities. Materials should not be stored next to the work face or other contractor’s works, on or against final or part completed works nor should materials be located in or around fire escape, access / egress routes. Materials should always be stored in a tidy manor clearly marked up the property of the contractor with labels identifying what the material is & installation location.
Setting Out
35 | BAM Construction will provide 1 no. master datum and 1 no. gridline in both N-S and E-W directions on each floor.
36 | The subcontractor will be responsible for all subsequent setting out of their works and are to make adequate provisions within their contract sum analysis for a competent site engineer.
37 | The Subcontractor has allowed for a post completion survey on immediate completion of the package works and shall issue same to BAM within 5 working days of completion.
38 | The subcontractor shall attend site as and when required to survey all previous trades works that they will interface with and satisfy themselves that construction design criteria in particular tolerances are correct. Should this not be the case the subcontractor is to notify BAM without delay and agree a process for rectification. BAM will not accept any costs from the subcontractor for commencing design, manufacture or construction on site that may incur additional cost over and above their tender allowance for not having first carried out the appropriate level of survey work
Scaffold
39 | BAM Construction will provide all external access scaffold [safety, access and working], handrail, edge protection, etc only as detailed within the BAM Scaffold Schedule. A copy of which can be obtained upon request.
40 | The subcontractor shall allow for any adaptions and / or alterations to the external scaffold which are over and above the scaffold allowed within the BAM Scaffold Schedule to allow access / egress of personnel and to facilitate and progress the works. A copy of which can be obtained upon request.
41 | Scaffold must not under any circumstances be erected, altered or adjusted by anyone other than a qualified scaffolder.
42 | Any access scaffold required for works up to 3.5m (working platform height) to be provided by the subcontractor. Scaffold towers and special scaffolding that is to be provided by the subcontractor is only to be erected by qualified personnel and must comply with NASC guidance. There will be no trafficking of these towers while operatives are on board. BAM will provide a working platform for the panelling to stair 3
43 | Ladders / steps of any description will not be permitted for use on site unless it can be demonstrated that there is no other means of accessing the works irrespective of the cost of providing alternative measures. In any case ladders or steps shall only be used for access and not as a working platform to carry out works.
Protection
44 | The subcontractor shall allow for the protection of all his own materials while on site prior to inclusion into his works, during installation and until handed over and accepted by BAM's Site Management.
45 | The subcontractor shall make due allowance within his tender and / or fully advise of the protection required to surrounding trades works to ensure that damage does not occur to said works as a result of the subcontractor's works.
46 | Should the subcontractor choose to not adequately protect surrounding trades works or fails to advise of the protection required to prevent damage from his works and consequently damage occurs, the subcontractor will be liable for either:
a] The repair of damaged works to an equal or better standard prior to damage, or
47 | b] The direct and indirect cost of BAM instructing others to undertake this repair work on behalf of the subcontractor.
48 | The subcontractor shall allow for all adaptions required to the above protection to facilitate the works, to access / egress the works and to open up for inspection (a maximum limit of 1m2) as and when required by BAM Site management.
49 | The subcontractor shall allow for separate visit[s] to remove all his own protection and that he may have provided for the surrounding works.
50 | Allowance should be made for out of sequence working and making good where any opening up or leaving down for inspections or testing may be required. (a maximum limit of 1m2)
51 | The subcontractor shall allow for any protection necessary to holes, edges, steps, etc. formed as part of the subcontract works including any necessary warning signs.
52 | Where flexible protective covering materials are provided by the subcontractor, these must conform to the requirements of the LPCB's Loss Prevention Standard LPS 1207: Fire requirements for protective covering materials (ref. 13) or equivalent standard (for example, ref. 14). The materials shall be manufactured in accordance with a quality assurance and certification programme, and the manufacturer shall be certified by a third-party approval body accredited by the United Kingdom Accreditation Service. The relevant approval mark shall be printed on the material. All solid/timber protection must conform with class '0' flame spread.
Demarcation / Warning Signs
53 | The subcontractor shall ensure that all necessary demarcation and / or warning signs are provided to safely facilitate the execution of his works and to ensure other trades are aware of the hazards and restrictions being imposed by the subcontract works.
Circulation and Common Areas
54 | The subcontractor shall include within his cost and programme for ensuring that all works in both common and circulation areas e.g. staircases, reception, corridors, etc. are undertaken outside of normal site hours. This cost will also include direct and indirect costs incurred by BAM for supervision and / or attendance [First Aider, Fire Officer, Site Manager etc.] and all associated compound, site set up, company tied and overhead costs.
Plant
55 | The subcontractor shall provide all necessary plant required to safely execute the subcontract works. BAM accept no liability in the event of mechanical breakdown or power failure.
56 | All plant should be maintained in good working order, with all test certificates available for BAM inspection 'on demand'.
57 | The subcontractor is responsible for the security of any plant, material [permanent or temporary], small tools, etc brought to site for use or incorporation into his works. BAM accept no liability for loss or damage to any of the foregoing. Subcontractor is to include all consumables required for the operation of plant.
Inspection of Work faces
58 | It is the responsibility of the subcontractor to inspect the tolerances of the workface at least 5 - 10 working days prior to start on site in order to establish the suitability of the structure / substrate. The subcontractor shall inform BAM Site Management in writing of any discrepancies in order for any remedial works to be carried out, 5 working days prior to the subcontractor's start on site date.
59 | BAM will not be held responsible for any cost incurred by the subcontractor building on or to substrate that is not within the recommended tolerance
60 | It is the subcontractor's responsibility to inspect the access provisions to the work face within reasonable time prior to work commencement.
61 | BAM will not entertain any claims for additional cost or time if these inspections have not been carried out.
Temporary Works
62 | The subcontractor is responsible for all temporary works applicable to his package and cost and programme implications of same.
Cleaning / Dust control
63 | The subcontractor shall allow for cleaning their works prior to offering them to BAM for snagging, once snagging is completed the subcontractor is required to re clean & offer the works to BAM.
64 | The subcontractor is to ensure that all interface, junctions & abutments with following trades are to be cleaned before the preceding trade commences their works.
65 | The subcontractor shall carry out a final clean of their works prior to receipt of PC for the subcontract works by BAM. "Sparkle" clean is by Bam
66 | The subcontractor is to allow whatever measures necessary to control dust, vibration and noise pollution created by the subcontractors works.
67 | Upon completion clear all materials, debris, plant and equipment leaving site in a safe and suitable condition for the following trades, including any filling as necessary.

## Seb St
Appendix C
SUPPLEMENTARY SUBCONTRACT CONDITIONS
FIXED PRICE LUMP SUM
for
WP22 Carpentry
at
The City Law School, Sebastian Street Development
for
City, University of London
package works to be undertaken by
dated 30/01/2019
signed:
name:
on behalf of:
date:
The City Law School / Supplementary Conditions
Ref: HLN.0272/WP22/SSC/002
Page 1 of 25
The City Law School, Sebastian Street Development
Supplementary Conditions
Contractual Conditions
Description
Item
Subcontract Quotations & Financial Management
1 | Any subcontract entered into will be a fixed, lump sum all encompassing price for the design (in accordance with the scope of works, specifications and Appendix D & E), supply of all labour, plant, materials, preliminary items etc. necessary to complete the works in accordance with the documents listed in Sub-Contract Enquiry Data Sheet ref: 153-06 Rev 4 and all subsequent documents issued during the tender period.
2 | Any quantities produced by the subcontractor or provided by the Main Contractor whether specifically mentioned / described or not are the sole risk of the subcontractor.
3 | Any Bills of Quantities or Preliminary items used in the compilation of the lump sum tender will have no contractual status whatsoever [other than in assisting in the pricing of variations at the main contractors discretion] and are to be non remeasurable.
4 | Adjustments will only be made to the measured works where there is a fundamental change to the design / scope resulting in an addition / omission to the subcontract works assuming the sub-contractor has issued the appropriate notice.
5 | The subcontractor is to provide a full priced breakdown of all the preliminary items included within his quotation that he deems necessary to successfully execute his works. No claims for additional costs will be entertained by the Main Contractor for additional preliminaries not priced but that are required to complete the subcontract works. The subcontract final account figure will be adjusted to reflect preliminary items priced but subsequently not provided.
6 | The subcontractor is deemed to have made due allowance and included within his quotation for all works [including preliminaries] whether described specifically or not, but which could be reasonably assumed necessary to facilitate the successful execution of the subcontract package.
7 | The subcontractor's quotation is a fixed price and not subject to fluctuation of any kind.
8 | The subcontractor shall make all due allowance for winter working and indeed the climate conditions at the time the works are undertaken with due consideration being made but not limited to protection screens / tents, heaters, dehumidifiers & cooling equipment to ensure the works are progressed
9 | The subcontractor shall make all due allowance for compliance with the Working Rule Agreement.
10 | The subcontractor shall ensure that all documents, specifications, reports, etc. that are named or referred to in the subcontract enquiry have been considered when submitting his quotation irrespective of whether they are included within the tender enquiry pack. The Main Contractor will not entertain any claims for additional costs as a result of the subcontractors failure to comply with this requirement.
The City Law School, Sebastian Street Development
Supplementary Conditions
Contractual Conditions
Description
Item
11 | Specifications are included in the enquiry document and are considered to be part of and incorporated in the item descriptions. Subcontract quotations will be deemed to have included with complying with the requirements of the Specifications, whether or not specific requirements are mentioned in any individual or collective item descriptions.
12 | The subcontractor shall, with his quotation, submit a fully priced copy of his quantified schedule of rates that equates to his quotation sum and these will be only included in the subcontract order for the valuation of variations (at the main contractors discretion). They may also be used for assistance in the preparation of interim valuations.
13 | Within 7 days of his appointment, the sub-contractor should provide a cash flow forecast showing the gross valuation of the works at the date of each interim application throughout the sub-contract period, and based upon the programme of works.
14 | Interim applications for payment together with all necessary supporting information should be sent to site marked for the attention of the Project Surveyor at least five working days before the established Main Contract valuation dates. .
15 | Interim applications for payment should be accompanied by forecast of the final sub-contract value, together with a schedule of both proposed and authorised variations.
16 | Sub-contractors will be required to attend regular financial review meetings on site to facilitate accurate reporting.
17 | The sub-contractor shall identify all variations when directions are issued and obtain the Main Contractor's approval in advance of the works being put in hand.
18 | The subcontractor shall ensure that all variations from whatever source are approved by the Main Contractor in advance of the works being put in hand.
19 | Only variations that have been approved by the Main Contractor in advance of the work being put in hand will be included in a final adjustment of the contract sum.
20 | Upon receipt of a request for a quotation and/or programme advice, the sub-contractor shall submit an estimate without delay and in any case within 5 days & shall include:
• A detailed breakdown of the cost including any allowance for direct loss and expense.
• Details of any additional resources which may be required.
• Details of any adjustments which may have to be made to the programme for the Works.
• Any other information as is reasonably necessary for the Project Manager to fully assess the implications of issuing such an instruction.
21 | All measurement for the purpose of valuing variations and provisional sums, shall be in accordance with the standard method of measurement 7th edition.
22 | The tenderer shall advise of any reservations and concerns he has in regard to the enquiry and highlight any gaps. Failure by the subcontractor to identify any ambiguities, inconsistencies, gaps or omissions during the tender period will result in it being deemed that the subcontractor has priced the most suitable solution as dictated by the Main Contractor.
The City Law School, Sebastian Street Development
Supplementary Conditions
Contractual Conditions
Description
Item
23 | Provisional sums within sub-contract tenders will only be permitted on prior agreement with the Main Contractor. Any provisional sums that are permitted will be deemed "defined" provisional sums as described in the Standard Method of Measurement 7th edition and the sub-contract sum will be deemed to include for all programming and preliminary costs.
24 | The tenderer shall identify any additional items that are not described in the enquiry but are required for the proper execution of the works - all as indicated or inferred in the drawings listed in the form of tender. No request for additional reimbursement will be allowed in respect of lack of knowledge of the site.
25 | The subcontractor shall where necessary check on site figured dimensions on consultant’s drawings, and ascertain the actual dimensions of existing structures or features affecting the new works. Where a discrepancy is apparent the subcontractor should report the fact to the Main Contractor and ask for further instructions. The Main Contractor's subsequent instruction to correct any discrepancies will not constitute a change to the subcontract. The Main Contractor will not accept any claims for delay or standing time where this requirement has not been performed in a timely manner.
26 | Value of materials claimed off site will only be paid if allowable under the main contract - It will be the responsibility of the subcontractor to furnish the main contractor with an indemnity form (obtained from the Main Contractor's QS) transferring title or ownership to the Main Contractor. This form will include insurance policy no., photographs and a list of all materials applied for. Furthermore the subcontractor is to provide reasonable proof that the title of ownership has transfererred to the Main Contractor in respect of any claimed 'unfixed materials on site' and that no sub-subcontractor or supplier (of any tier) has validly retained title to these goods.
27 | Appropriate provision should be made to allow for or fix any exchange rate fluctuations which may have an affect on the costs associated with the project up until completion. All applicable tender rates should be returned inclusive of any premiums associated with fixing the rates against currency fluctuations.
Key Dates & Working Hours
28 | The subcontractor is to be aware of the sensitivity & quiet times of the surrounding areas and make due allowance within his tender for compliance with instructions to cease work due to such restrictions. Noisy working can only completed on a 2 hours on and 2 hours off basis.
29 | Normal working hours are 8am to 6pm Mondays to Fridays. The site will not generally be open on weekends. Should the contractor require the site to be open on the weekend, they must give prior notice to BAM Construction Ltd. Please note that should the site be opened in order for the subcontractor to complete programmed works, BAM Construction Ltd reserve the right to contracharge the management time. Additional working hours will be subject to the approval of the Local Authority Environmental Health Officer. Noisy works to be avoided in normal voluntary quiet periods.
30 | All subcontractors are to take full advantage of the hours available on site in order to satisfy the programming requirements. BAM Construction Ltd will not entertain any non-productive overtime claims due to any programming shortfalls if the above hours have not been worked.
31 | BAM Construction Limited reserve the right to vary these times without notice. Any hours the subcontractor may wish to work outside the above will be by prior agreement with the Project Manager and will be subject to reimbursement to BAM of costs for BAM supervision and/or attendance [First Aider, Fire Officer, Site Manager etc.] and all associated compound, site set up, company tied and overhead costs.
32 | The Main Contractor's Overtime Charges:
The following allows for the extended opening of the site with BAM security and management present on site. Written application will be made for such requests and will be at the discretion of BAM.
Monday - Friday = £90/Hr
Saturday = £135/Hr
The City Law School, Sebastian Street Development
Supplementary Conditions
Contractual Conditions
Description
Item
Sunday = £180/Hr (Minimum 5 Hours duration)
Additional crane time will be charged at the following rates per crane and will include a Driver and Banksman. Written application will be made for such requests and will be at the discretion of BAM.
Monday - Friday = £97/Hr
Saturday = £114/Hr
Sunday = £131/Hr (Minimum 5 Hours duration)
Additional hoist time will be charged at the following rates per hoist and will include a Driver. Written application will be made for such requests and will be at the discretion of BAM.
Monday - Friday = £51/Hr
Saturday = £68/Hr
Sunday = £84/Hr (Minimum 5 Hours duration)
Access & Deliveries
33 | The sub-contractor is deemed to have inspected and satisfied himself with respect to adequacy of access to the site. All deliveries and sub-contractors personnel must report to BAM Construction site office prior to entering the site to sign in and be issued a visitor's pass.
34 | Access is permitted for off-loading, only if:
a] By prior arrangement with our Construction Manager
b] Provided 7 working days notice for deliveries is given to our Construction Manager.
35 | Freight vehicle safety requirements:
a] Ensure that all freight vehicles have the following:
a1] Audible alert to other road users to the planned movement of the vehicle when the vehicle's indicators are in operation.
a2] Prominent signage at the rear of the vehicle to warn cyclists of the dangers of passnig the vehicle on the inside.
a3] Properly adjusted class VI mirror's of Fresnel lense to eliminate the near side blind spot.
a4] Side under run guards.
b] Driver training:
b1] Drivers must be trained on vulnerable road users safety through an approved course and hold a current valid Certificate of Competence.
b2] Drivers must hold a valid driving licence and be legally able to dive the vehicle.
c] All frieght operators must be registered with the Freight Operator Registration Scheme and accredited to FORS Gold accreditation. Evidence of FORS Gold accreditation must be submitted at least 7 days prior to a delivery.
36 | All deliveries of plant and materials have to be co-ordinated with our site logistics manager. If the subcontractor or supplier fails to meet the delivery they may be turned away from site. No costs will be accepted by BAM for failure to make deliveries. If the unloading takes longer and the next delivery is waiting to gain entry to the site, the unloading may be stopped and the vehicle asked to leave site. It will be the subcontractors responsibility to pay all costs and reschedule the delivery of the remainder of the materials.
37 | Materials are to be delivered to site to suit the installation programme on a 'just in time' basis, but allow for working in loaded out areas. Storage of materials will be strictly by agreement with BAM and be in clearly designated locations.
38 | Sub-contractors are to provide experienced and competent personnel for all their deliveries and unloading activities. This is to include but not be limited to traffic marshals, slinger/signaller, banksman, general operatives etc.
39 | Deliveries and packages will not be signed for by BAM, subcontractors and suppliers must ensure that labour will be on site to unload and sign for any deliveries.
40 | Adaptions to site hoardings and gates to suit sub-contractor deliveries are to be allowed within the tender return.
The City Law School, Sebastian Street Development
Supplementary Conditions
Contractual Conditions
Description
Item
41 | The sub-contractor or supplier is responsible for all costs associated with out of hours deliveries and must give 7 working days notice to BAM Site Management of these deliveries. No costs will be accepted should these deliveries be cancelled for any reason.
42 | The sub-contractor or supplier is to allow for any road closures required for plant deliveries etc and accept timing of this procedure. Include management of traffic / pedestrians for all plant / materials deliveries.
43 | Prior to commencing fabrication, checks are to be made on site as to the means of access as no claims will be considered for any lack of knowledge of any restrictions on transporting the materials or equipment into the area of the works.
Site Visit
44 | The sub-contractor is advised to visit site and acquaint himself with the conditions affecting the execution of the works, including local conditions, accessibility of works and site, the nature of the ground, and the supply of and conditions affecting labour and materials. The sub-contractor shall make due allowance for the incomplete nature of the building, including humidity levels, lack of heating etc., that may affect unfixed or fixed materials. The sub-contractor is deemed to have included for all costs arising from the foregoing as no claim for extra payment or extension of time will be admissible due to want of knowledge or inadequate allowance.
Programme
45 | BAM’s programme is issued for information only and identifies the indicative programme requirements for the sub-contractor works and the anticipated start and completion dates of each section. The exact dates will be confirmed by our Construction Manager within the agreed periods. The sub-contractor is not to deviate from these dates without the written permission of our Construction Manager.
46 | The Main Contractor will require from the sub-contractor a detailed breakdown of the programme period for the purpose of regular progress assessment. Details of anticipated resource involvement will also be required.
The City Law School, Sebastian Street Development
Supplementary Conditions
Contractual Conditions
Description
Item
47 | On a weekly basis, on a date to be agreed, a progress report including revised programme will be required to be submitted to our Construction Manager recording not only the progress of works on site, but the progress of design, placing orders and manufacturing to meet future dates. Key dates should be highlighted for specific events and the capability of meeting these dates stated in these reports. The exact content of these progress reports will be discussed with the sub-contractor prior to their works commencing but should also include a section specifically on the quality of the sub-contractors work and the compliance (or otherwise) with the subcontract requirements. Failiure to deliver these reports by 5pm on the business day when the report is required a sum of £500.00 will be witheld until the report is issued to the BAM Construction Manager. Due allowance to be made within bid for necessary planning resources to accomodate this requirement and should be clearly identified with subcontract contract sum analysis.
Information Required Schedule
48 | Immediately an order or instruction has been issued, the sub-contractor must produce a schedule of the information required to enable the necessary ordering, manufacture, delivery and installation of his works. This schedule is to itemise the information required, and the date by which that information needs to be issued. It is the responsibility of the sub-contractor to ensure that this is lodged with Site Management at the earliest possible time to ensure compliance with the programme of works on site.
Site Instructions
49 | Site instructions varying the scope or content of the works will be given in writing via a site Instruction to Subcontractor (Form 310-11) from BAM Site Management only. The sub-contractor shall confirm in writing any financial or programme effect resulting from this instruction within 5 days. Under no circumstances are any instructions to be taken from any representative of the client or design team unless the same has been authorised with BAM Project Management. Issue of an instruction does not necessarily result in additional cost or programme implications.
Damage to Sub-Contractors Work
50 | Protection of the sub-contractor's work is the sole responsibility of the sub-contractor until the work is fully and finally completed and handed over to BAM.
51 | Damage caused to the sub-contractor's works is to be reported immediately to the Construction Manager. If damage is witnessed, BAM will act on the sub-contractors behalf against any third party, or arrange for reimbursement as applicable.
52 | Descriptions such as "damage by others" will not be accepted for payment.
Inclement/Adverse/ Exceptionally Adverse Weather
53 | Where the sub-contractor's operations are liable to be affected by weather conditions, they are to ensure that all reasonable efforts are made to maintain progress prior to the works being suspended. Payment for standing time or disruption as a result of inclement/adverse/exceptionally adverse weather will not be made. Any hours lost as a result of adverse weather conditions must be reported to and agreed with our Construction Manager on a weekly basis stating the days on which these delays occurred, together with the hours lost and proposals to mitigate any such delays.
Interfaces
45 | The sub-contractor is responsible for the provision of all interface's with other trades work which will include but not be limited to:
a] Coordinating design with adjacent, preceding and follow on trades
b] Coordinating site activities e.g. deliveries, storage, access to working areas etc with adjacent, preceding and follow on trades
c] Attending meetings as necessary to discuss and review design and site coordination.
d] All costs associated with meeting the interface requirements
Correspondence Procedures
55 | The subcontractor is required to direct all correspondence to our site office, for the attention of the Project Manager unless it is of a financial nature whereby it should be addressed to The Project Surveyor.
Industrial Relations
The City Law School, Sebastian Street Development
Supplementary Conditions
Contractual Conditions
Description
Item
56 | The sub-contractor is deemed to have employed his labour in a bona fide manner, have all holiday stamps fully paid and only employed labour eligible to work within the UK.
57 | The sub-contractor is responsible for maintaining good industrial relations at all times and shall confirm to the following principles in order to maintain a uniform standard of industrial relations on site:
a] All working rule arrangements to be rigidly adhered to.
b] Any site procedure agreement to be adhered to.
c] Sub-contractors shall be responsible for ensuring that their employees comply with such site regulations as may be introduced from time to time.
58 | The sub-contractor shall employ on the works such persons as are skilled and experienced in the performance of their duties. Each subcontractor, where possible, is to employ local labour. The Main Contractor reserves the right to have any person employed by the sub-contractor, removed from site, if in the opinion of the Main Contractor that person misconduct himself, is incompetent or negligent in the performance of his duties or fails to conform with site requirements or regulations as may have been advised to him.
59 | The sub-contractor is required to take such care as to ensure that the sub-contract work integrate with that of other sub- contractors and for ensuring that full co-operation is maintained with the main contractor.
Record Drawings, O&M Manuals and Health & Safety Files
60 | The subcontract will not be awarded practical completion until all record drawings, operation and maintenance files and health and safety files have been issued on Livelink and are signed off by BAM. The first draft of such documents are to be submitted to BAM 6 weeks prior to completion of the subcontractor's agreed programme of works. BAM will take 1 week to check and advise of any errors and amendments that need to be made to these documents and then the subcontractor shall rectify these and reissue within 1 week which will be 4 weeks prior to completion of the subcontractor's agreed programme of works. Any costs levied at BAM for failure to obtain practical completion due to non submission of the foregoing will be deducted from the subcontractor's account.
61 | The subcontractor shall record the 'as-built' position of all works etc., where they differ from the working drawings. 'As-Built' shall mean incorporating all requirements of the BAM Instructions together with further variations and minor alterations the Subcontractor may make by agreement with BAM to overcome site and erection problems including changes arising from site setting out.
62 | The subcontractor shall co-ordinate the preparation of his 'as-fitted' or 'as-built' record drawings for the Mechanical and Electrical Services and other Specialist Installations and for the submission of such drawings to BAM for submission to the Employer's Agent or Consulting Engineers in accordance with item 60 above.
63 | The subcontractor shall assemble in conjunction with BAM, the Employer's Agent and the Consulting Engineers operating and maintenance manuals including test certificates and commissioning results materials supplied giving such information on materials and equipment including installation diagrams, operating and maintenance instructions, and names and addresses of suppliers as is necessary to enable the Employer's personnel to operate and maintain the building.
64 | The subcontractor shall provide four fully co-ordinated copies of such manuals and drawings (2 paper copies / 2 electronic CD's) to be submitted to BAM for submission to the Employer's Agent or Consulting Engineers in accordance with item 62 above. Allow for making arrangements for and any necessary practical instruction of the Employer's personnel as detailed in the subcontract documents prior to practical completion.
65 | The subcontractors method statement will also include a description of the final cleaning procedure prior to Practical Completion. BAM expects that the completed buildings will be offered for Practical Completion in an exceptionally high standard of cleanliness and the Practical Completion will be refused unless the subcontract works reach this standard.
Access for Off Site Material Inspections
66 | The subcontractor shall facilitate access of all off site materials as and when required by BAM, Employer and/or the Design Team including access to any sub-subcontractor or suppliers workshop/premises.
The City Law School, Sebastian Street Development
Supplementary Conditions
Contractual Conditions
Description
Item
67 | Provision should be made for costs associated with inspection of off-site materials including transport and accommodation.
Meeting Attendance
68 | The subcontractor will attend all necessary design, progress, quality, financial and health and safety meetings deemed necessary by BAM Construction Management and his representative shall be a person relative to the discipline of which the meeting is concerned.
Ordering Materials
69 | The subcontractor should note that the ordering of materials or other resources using quantities stated in the enquiry document is at the subcontractor’s own risk.
Production Information
70 | Production Information / Shop Drawings must be provided by the subcontractor where required by the Design Team Specification, Employer’s Requirements and the enquiry document. The subcontractor is to be responsible for the final design.
71 | When preparing a master programme the subcontractor shall make reasonable allowance for completing production / shop drawings, builder's work drawings, inspection by the Employer's Agent and any subsequent amendment[s], resubmission[s] and reinspection[s].
72 | During the contract the subcontractor is to submit to the Employer's Agent the required number of copies of production information. The Employer's Agent will make comments on one copy, then return to the subcontractor and this will be deemed to be a direction, notice or instruction under the contract. The subcontractor shall ensure that any necessary amendments are made without delay.
73 | If submitted production information differs from the Employer's Requirements, each such difference must be subject to a request for substitution or variation, supported by all relevant information.
74 | BAM will issue all drawings, specifications and reports either by Livelink, email or compact disk and the subcontractor will ensure he has the facility to read these files which will be PDF or DWG and is able to print them off for his own distribution. BAM will not entertain any additional costs associated with the foregoing.
75 | The issue of a comment on a subcontract drawing or document by the employers agent shall not be treated as having cost or programme implications without being instructed in writing by BAM. It is the subcontractor’s responsibility to identify these changes, in writing, prior to the incorporation where such would have a cost or programme affect. Failure to do so will result in any change being treated as design development at the cost of the subcontract package.
76 | Subcontractor is to allow for connection, to use and operation of the Livelink electronic data management system including licenses.
77 | The Subcontractor will, and shall procure that all of his Sub-Subcontractors and suppliers will, use the Livelink electronic data management system including licenses.
The City Law School, Sebastian Street Development
Supplementary Conditions
Contractual Conditions
Description
Item
Copyright
78 | The subcontractor shall be responsible for acting upon and resolving or avoiding all issues of copyright which emanate from them or their suppliers works that are under the subcontractors control. This will include:
a] All information cross issue matters, including responsibility for ensuring that BAM and the Employer's rights are where reasonably possible maintained on all subcontract or other prepared documentation for this project.
b] Ensuring wherever possible it is under the subcontractor's control and that BAM, the Employer and the Professional Team are not liable for copyright infringement.
79 | The subcontractor shall ensure that no copyright obligations which may effect the execution of the works on cost and programme should lie with BAM, the Employer or the Professional Team where these could have reasonably been foreseen and resolved or avoided by the subcontractor without such effect.
Security / Safety / Protection / Fire
80 | The subcontractor shall take all necessary action to prevent personal injury, death and damage to the works or other property from fire. Comply with the Joint Code of Practice 'Fire Prevention on Construction Sites' published by the Building Employers Confederation and the Loss Prevention Council. Where work necessitates the use of naked flames in enclosed spaces, a portable fire extinguisher is to be provided in all areas where work is taking place. Fire escape routes are to be kept unobstructed at all times. The subcontractor is deemed to include for all costs involved in complying with these requirements.
Nuisance Generally
81 | The subcontractor shall prevent smoke, dust, fumes, spillage, pollution of waterways and other harmful activities. No bonfires will be allowed. Dispose of waste foodstuffs [e.g. from mess rooms] in a manner that does not encourage flies and other pests. Comply with any reasonable requests from the public and adjoining owners.
Noise
82 | The subcontractor shall keep noise to as low a level as can be practicably attained. Avoid the use of noisy tools [e.g. percussion tools] or restrict their use to agreed times. Fit compressors, percusion tools and vehicles with effective silencers of a type recomended by the manufacturers of the compressors, tools or vehicles. Use mufflers and acoustic enclosures when necessary. The use of radios, CD players and the like will be prohibited. Comply with BS 5228 'Noise control on construction sites'. No noise will be permitted at weekends unless specifically approved by the Employers Agent. The subcontractor will comply with statutory and local authorities with regard to noise control (reference London Borough of Islington Code for Contractors).
83 | The subcontractor's attention is also drawn to the 'Control of Pollution Act 1974 - Sections 60 and 61'. The Local Authority may impose a maximum noise level for the site and also lay down restrictions on the types of plant to be used and the methods of working to be adopted. It is the subcontractor's responsibility to ascertain if any impositions or restrictions will apply to the site for his works and to submit or at very least assist in the application to the Local Authority for prior consent. All costs associated with noise and vibration assessments and compliance with the above will be deemed to have been included.
Electrical Interference
84 | The subcontractor shall not cause any interference to radio and TV receivers, computers or other instruments in adjoining properties.
Electromagnetic Interferences
85 | The subcontractor shall take all necessary precautions to avoid excessive electromagnetic disturbance of apparatus outside the site.
The City Law School, Sebastian Street Development
Supplementary Conditions
Contractual Conditions
Description
Item
Laser Equipment
86 | The subcontractor is to install, use and store construction laser equipment in accordance with BS EN 60825
Vibration
87 | The subcontractor shall prevent any form of shock or vibration being transmitted into the retained structure, cladding or surrounding buildings.
Water
88 | The subcontractor shall prevent damage from storm and surface water as a direct result and consequence of his works.
Keep Highways Clean
89 | The subcontractor shall prevent soils and debris resulting from their works being deposited on the public highway and immediately remove any unavoidable deposits and pay any Local Authority charges for repairs etc. Any roads / paths with soils or debris arising from the subcontract works shall be swept and kept clean throughout the day as required.
Trespass by Plant
90 | The subcontractor shall not permit [unless permission has been previously obtained in writing] plant to encroach over or upon adjacent property; trespass by crane jibs into airspace is a particular consideration. Full details of mobile crane siting, height, jib length and agreements reached with adjacent property to be submitted before work commences.
Site and Adjacent Property
91 | The subcontractor shall protect site and any existing buildings or property on or adjacent to the site and not forming part of the works that may possibly be damaged or affected by the subcontract works. Should damage occur the subcontractor will be required to cover any repairs costs. Equally the subcontractor will be required to clean off any construction waste from the existing boundaries & structures and offer back to the main contractor in the same condition as provided at contract commencement. Additionally if the subcontractor requires any existing hoardings and or barriers to be moved for working space requirements the subcontractor will be required to pay all associated costs equally should same be damaged as a consequence of site works the subcontractor will be required to meet all repair costs.
92 | Compliance with all Principal Designer requirements, planning authority restrictions, and party wall agreements
Planted Areas
93 | The subcontract shall protect all plants and cultivated areas including associated hard landscaping and features that may possibly be damaged or affected by the subcontract works.
Existing Planted Areas
94 | Any plants damaged by the subcontractor's works shall be replaced with healthy stock from approved nurseries at the subcontractors cost. Established trees, if disfigured or permanently damaged by the subcontractors works, shall be replaced at the subcontractors cost. Any such tree shall be the responsibility of the subcontractor until healthy new growth is assured.
Paved Areas
95 | The subcontractor shall protect all site roads, paths, paved areas and access routes that may possibly be damaged or affected by the subcontract works. Should any of these areas including existing buildings be damaged the subcontractor will be expected to pay the full repair and or replacement cost to the same specification or better
The City Law School, Sebastian Street Development
Supplementary Conditions
Contractual Conditions
Description
Item
Stability
96 | The subcontractor shall accept responsibility for the stability and structural integrity of the works during the subcontract works and support as necessary. Details of design loads may be obtained from the Structural Engineer.
Publicity
97 | No advertisement of any kind will be permitted on site except with the written permission of the Employers Agent which can only be obtained through BAM.
98 | The subcontractor shall not at any time take any photographs or video recordings of the works or part thereof for purposes other than to demonstrate progress, unless the subcontractor has obtained the prior written permission of the Employers Agent which can only be obtained through BAM.
99 | The subcontractor shall give no statement, photographs or information of any kind or no such information shall be communicated to the press, radio/TV companies, company magazines, etc., unless the subcontractor has obtained the prior written permission of the Employers Agent which can only be obtained through BAM.
Pedestrian Access and Use of Site
100 | Upon arrival to the development, all personnel must report to the BAM Security Hut. All new comers to site must be inducted before stepping onto site. See Health & Safety Compliance Item 1 for notes on site induction.
101 | Other persons visiting the site in connection with the works must report in the first instance to the BAM Security Hut and sign in with reception upon entering and leaving the site. Whilst on site, visitors must be accompanied at all times by a member of the sub-contractors staff who have undergone the site induction systems and have escort authority. All visitors must wear the required Personal Protective Equipment. Work people or visitors who arrive at the site and whose name does not appear on the sub-contractors list may be delayed or refused access to the site.
102 | The subcontractor is to ensure that all operatives sign in & out each day using the biometric hand scanning security system. Failure to scan in and out will result in the operative being removed from site. Additionally any operative found scanning in and out for anybody other than themselves will automatically be removed from site on a permanent basis
103 | Operatives must adhere to the designated pedestrian routes and security procedures on site.
Maintenance of Existing Services
104 | Before commencing site operations the sub-contractor shall ascertain the location of all services, drains or sewers and inform our Project Manager. The sub-contractor shall also uphold, maintain and protect all pipes, ducts, drains, sewers, overhead cables etc during the execution of the works and make good any damage or pay any costs or charges in connection of same. Immediately any damage is caused the sub-contractor shall notify our Project Manager.
105 | All existing services shall be maintained in good working order. Any break in the service, howsoever caused, shall be made good at the sub-contractors expense.
The City Law School, Sebastian Street Development
Supplementary Conditions
Contractual Conditions
Description
Item
Archaeological Investigation
106 | Any items found on site of archaeological interest must be immediately handed to BAM's Site Management for transmission to the Local Archaeological Trust.
Bonds / Guarantees
107 | BAM Performance bond - subcontractor to agree to wording unamended
108 | BAM Parent Company Guarantee -subcontractor to agree to wording unamended
109 | Subcontractor Collateral Warranties - subcontractor to agree to wording unamended
110 | All bonds guarantees & warranties to be executed & returned to main contractor within 14 days of issue
111 | Acceptance of Liquidated & Ascertained Damages as laid down in the contract documents
General Items
112 | Acceptance of cost or lost time due to instruction to cease specific operations due to noise, dust or other pollution.
113 | The subcontractor will be responsible to retrieve all works information from the Livelink system including other subcontractors information which may interface and or co-ordinate with your works. BAM will not instruct the subcontractor to retrieve "other" subcontractors information or to implement same within their design, manufacture or construction works on site.
114 | The subcontractors work is to comply with all relevant British Standard latest regulation and codes of good practice. Subcontractor to comply with the design teams specifications and drawings, it is the Design Team's responsibility to ensure that these comply with British Standards. Subcontractor (as the specialist) is to advise Bam if they notice anything that they believe may not be compliant
115 | Samples and mock ups to be provided in accordance with the specification.
116 | The Subcontractor has included for obtaining approval from the Design team etc. prior to manufacturing materials in accordance with the programme requirements and in order to prevent any delays to the construction programme i.e. if extra tests, additional works, further samples etc. are required to satisfy them of their scheme then the Subcontractor is deemed to have included for these at no additional cost. No such approval, comment or otherwise shall relieve the Subcontractor of their responsibility for adhering to the programme. Subcontractor has allowed for all costs associated with the design, shop drawings, mock ups etc. Along with design work to any associated interfaces.
117 | The subcontractor is responsible for any design errors affecting the works, or its impact on other trades, by way of failing or by those of other interface with subcontractor design packages
118 | Subcontractor has made due allowance with regard the quality control of workmanship and materials including regular inspections in conjunction with BAM Site Management
119 | The Subcontractor is to allow for any necessary labours, notchings, trimmings, scribing, packing, supports, openings, chases, builderswork and the like, as is required, to overcome construction tolerances, or to comply with the new / existing structure. All setting out and marking out of builders works to be completed by the subcontractor.
120 | The Subcontractor has allowed for all holes, sinkings, plugging and screwing and similar as necessary into backgrounds of concrete, reinforced concrete, brick, block, steel, stonework, and the like so as to provide suitable fixings etc
121 | Subcontract design must be performed and comply within the construction tolerances of all other elements, including the existing structure.
122 | Where the consultants drawings, specifications and schedules refer to the "contractor" the subcontractor is to assume in each and every instance that "contractor" means "subcontractor" and that their tender should comply accordingly.
The City Law School, Sebastian Street Development
Supplementary Conditions
Contractual Conditions
Description
Item
123 | The subcontractor is to identify any discrepancy in the tender documentation and refer this matter to BAM for direction. In the event a discrepancy is not identified to the contractor in the tender period, the Subcontractor will be deemed to have made due allowance for the most appropriate solution determined solely by BAM.
Non Compliance
124 | Failure to comply with any of the above may result in BAM carrying out the works / facility on behalf of the subcontractor and deducting all direct and indirect cost of that service from the subcontractor's account.
The City Law School, Sebastian Street Development
Supplementary Conditions
Health and Safety Conditions
Item | Description
Health & Safety
1 | The Sub-Contractor will comply at all times with all current Statutory Provisions relevant to their operations, including but not limited to:- • Health and Safety at Work, etc. Act. • The Consumer Protection Act. • Management of Health and Safety at Work Regulations. • Personal Protective Equipment at Work Regulations. • Provision and Use of Work Equipment Regulations. • Manual Handling Operations Regulations. • Control of Substances Hazardous to Health Regulations. • The Construction (Health, Safety & Welfare) Regulations. • Consultation with Employee Regulations. • Working Time Regulations and all other current relevant statutory provisions.
2 | The sub-contractor shall have a fully competent and suitably experienced Foreman / Supervisor on site at all times in charge of operations on site at all times, who will act as the site point of contact for all matters relating to health, safety and welfare. This person is to be identified prior to commencement; supervisors must have received a minimum of two days’ Health and Safety training provided by Construction Skills or an affiliated training provider. Evidence of the occupational health monitoring undertaken by the employer must be provided. All instructions will be directed through the Supervisor. The Supervisor plus one other nominated person will be required to act as Fire/Liaison Officer on behalf of the sub-contractor’s employees and attend the regular site meetings as required. The sub-contractor will be deemed to have included for the foregoing within the tender.
3 | Safety helmets and all other P.P.E. must be provided by the sub-contractor for all their operatives and visiting personnel to site and be worn at all times on site. The sub-contractor is reminded that all operatives are to wear the appropriate clothing for their works including gloves, protective safety footwear, high-visibility jackets, vests, face-fit respiratory equipment and fitted harnesses. All P.P.E. must be suitable and fit for purpose with operative trained in its use and maintained and fitted correctly. Trainers are not allowed to be worn on site. Note: Safety helmets are to be a consistent colour.
4 | NO P.P.E, NO CSCS CARD OF CORRECT COMPETENCE FOR TASK AND NO HEALTH AND SAFETY TRAINING = NO WORK
5 | As well as holding the right CSCS competency card for the task, the sub-contractor must have the following standards of health and safety training: • Operatives - CITB Health and Safety Awareness: One Day • Supervisors - CITB Site Supervisors Safety Training Scheme: Two Days • Managers - CITB Site Manager Safety Training Scheme: Five Days • Directors - CITB Directors Role for Health and Safety or IOSH Directing Safely: One Day
6 | Should any delivery vehicles be required to drive onto site, the drivers must wear the all necessary P.P.E. required before leaving the vehicle.
7 | All operatives operating disc cutting, grinding, burning, welding or other noisy equipment must wear the appropriate eye and ear protectors. Failure to comply with the above instruction will result in either a removal of the operative from site or ultimately determination of the sub-contract for non-compliance.
8 | In the event of any disputes arising, BAM Construction Ltd's Safety Officers decision will be binding on all parties.
9 | All electrical equipment must have been ‘PAT’ tested and a copy of the electrical certificate issued to BAM. All mechanical equipment must be delivered to site with a certificate of worthiness and be suitable for purpose to which it is to be used. All diesel drums must be stored within a bunded area.
10 | Certificates of thorough examination for lifting equipment must be issued to BAM prior to any operations taking place.
11 | Operators of mobile work equipment must hold as a minimum a recognised certificate of training achievement (CTA) for the category for which they have been trained and tested. All trainers must be CITB accredited.
The City Law School, Sebastian Street Development
Supplementary Conditions
Health and Safety Conditions
Item | Description
12 | Only trained signallers are to give instructions to any crane operator and only trained slingers are to attach loads to any crane.
13 | Drivers of any vehicle or machine being loaded by excavator must vacate the vehicle/machine during loading.
14 | All contractors are to hold weekly toolbox talks, wherever possible these should be relevant to site operations. BAM may on occasions request certain subjects to be addressed. Records of toolbox talks must be forwarded to BAM, which must include at least a monthly environmental tool box talk.
15 | BAM will hold regular site safety review meetings and safety committee meetings, all contractors must ensure they are represented at these meetings.
16 | Any persons/contractor committing a misdemeanour relative to health & safety, will be issued with a health & safety improvement notice. The details of which must be rectified and actioned immediately.
17 | All accidents, near misses and dangerous occurrences must be reported to BAM Construction.
18 | Smoking will NOT be allowed on site.
19 | Operatives working in an unsafe manner may be permanently excluded from site for the safety of themselves and others.
20 | All subcontractors must carry out daily briefings / 'safe to start' briefings at the beginning of each working day. Records of these briefings must be retained for BAM inspection on a monthly basis.
Control of Substances Hazardous to Health [C.O.S.H.H.]
21 | In addition to the Control of Substances Hazardous to Health Regulations [issued under the Health and Safety at Work, etc. Act] the subcontractor shall give advance notice in writing to BAM warning of any "substances hazardous to health", provide BAM with a copy of the "assessment of health risks" as defined in the Regulation, specify the hazardous substances, their location and the dates when they could be encountered. Provide a similar notice to BAM about any hazardous substances to be used in works carried out after practical completion of any part of the works [such as maintenance, cleaning, etc]. Provide copies of notices given under this clause to BAM.
22 | In order to comply with the C.O.S.H.H. Regulations [1988], the sub-contractor must provide detailed information on the safe use, storage and handling of all goods and materials supplied to the site, irrespective of whether the goods and materials are manufactured directly by the sub-contractor or a third party.
23 | The information must be provided to our Construction Manager on site in writing before deliveries are made, if special precautions/storage facilities are required at the time of delivery. No work liable to expose persons to substances hazardous to health shall be undertaken without proper precautions having first been taken.
24 | Any product, which has flammable or toxic properties and is to be incorporated into the works, either for temporary or permanent operations is to be advised to the site management prior to its delivery to site.
25 | The sub-contractors attention is drawn to the requirements of the Consumer Protection Act 1987 in respect of providing information on the safe use, storage and handling of materials on site.
Permits to Work
26 | “Permits to Work” must be obtained before commencement for all maintenance, repair or installation works to elements of fabric, plant and equipment. They will be issued under the signature of, and controlled by, the site designated authority. If the sub-contractor identifies a potentially hazardous situation, he shall notify the site designated authority and subject to a separate “HOT WORK PERMIT”.
27 | The sub-contractor is to be aware of arrangements concerning fire precautions on site.
28 | Welding trolleys must have appropriate fire extinguishers affixed and ready for use and all hot work applications must also have suitable extinguishers adjacent to the workplace.
The City Law School, Sebastian Street Development
Supplementary Conditions
Health and Safety Conditions
Item | Description
29 | Due to the control exercised by the Electricity at Work Regulations Act 1989 in no circumstances shall the sub-contractor work on live systems without such written consent. Before any work is commenced which requires the isolation of electrical equipment under site control, approval must be granted by the site designated authority.
Safety Risk Management
30 | The sub-contractor will be required to provide a project specific method statement and risk assessment for their works package prior to site commencement.
31 | The main objectives are to identify the responsible person, consider the hazards of all work operations, including those to any other parties, devise alternative strategies for the controlling of these risks and to relate these alternative strategies to the general decision making framework. The objective of risk management involves the following strategy:-
a] Risk identification, e.g. experience, inspection etc.
b] Risk evaluation and assessment, e.g. risk to others.
c] Risk control, e.g. visual checks, instruction, training, immediate remedial action where necessary, implementation of emergency procedure plan, i.e. safe shutdown of plant and equipment, procedures for notifying and directing emergency services on site.
Site Induction
32 | All personnel must complete BAM's induction training for the development and collect the security pass. Please note all personnel must take with them their national insurance number and CSCS card to receive their induction training. All personnel must be present at the induction room at 8.00am to commence their induction training at 8.30am. All operatives must have been inducted by their employing company and have received a RAMS briefing prior to attending BAM's induction.
33 | A charge of £5.00 will be incurred against the sub-contractor for each security pass issued (this will be required if the operative does not have a CSCS card with a chip) & £15 should a replacement be required
34 | The sub-contractors attention is drawn to BAM Construction's Company Safety Policy and BAM Construction's Health and Safety Standards for sub-contractors.
35 | A copy of the sub-contractors current safety policy is to be submitted prior to commencement on site which is to be lodged with BAM Construction Ltd's Safety Department for reference purposes, with a copy on site.
36 | All subcontractors will be required to complete other prequalification questionnaires for approval by BAM before work
37 | Operatives discovered failing to comply with the requirements set out in the site induction, this document or generally acting in an unsafe manner may be required to be re-inducted at a charge of £30 per man.
C.D.M. Regulations
38 | The sub-contractor shall comply with The Construction Design & Management Regulations 2015 in respect of the duties and powers required under those regulations.
39 | The sub-contractor shall allow for allocating adequate resources to ensure compliance with and the implementation of the Regulations under the supervision of a competent person experienced in the requirements of all matters related to Health & Safety at Work.
40 | The subcontractor shall allow and afford his assistance to BAM in developing and implementing the Health and Safety Plan in relation to the works on site ensuring it always reflects the current situation.
41 | The sub-contractor shall ensure that all site operatives and other persons authorised to be on site are aware of and comply with the requirements of the Health and Safety Plan.
42 | The sub-contractor shall ensure all information which should be included in the Health and Safety File is provided to BAM.
43 | In accordance with the current Construction Design and Management Regulations 2005, the sub-contractor will be required to produce technical literature, CV's of staff and details of similar projects to prove their competence as a "contractor", prior to the placing of an order.
The City Law School, Sebastian Street Development
Supplementary Conditions
Health and Safety Conditions
Item | Description
44 | The sub-contractor will also be required to produce method statements, risk assessments, drawing and maintenance manuals [where applicable] throughout the progress of the works as well as any considerations and information relevant to the Health & Safety File.
45 | All sub-contractors will be required to complete a Health & Safety pre-qualification assessment, to prove their competency, before an order is placed.
Environmental
46 | The sub-contractor will comply with all current Statutory Provisions relevant to their operations:-
 Environmental Protection Act (Waste Control).
 Water Resources Act
 Control of Pollution (Oil Storage) (England) Regulations
 Hazardous Waste Regulations
and all other current waste legislation.
47 | The sub‑contractor shall acquaint himself with the current Control of Pollution Act and any amendment or notices, and with any Local Authority or Statutory requirements relating to the control of the emission of noise from this project.
48 | The sub-contractor is to ensure that all materials emanate from legal and sustainable sources.
49 | With reference to the Aecom Stage E Sustainability Report, note requirements and provide information to BAM to achieve the targeted credits to achieve BREEAM (2011) rating of excellent.
50 | All sub-contractor BREEAM information to be issued on a progressive basis and at least 3 months prior to completion of the sub-contract works.
51 | The subcontractor must comply with all measures implemented on site to achieve a Considerate Constructors Scheme score of 40 or over.
52 | All Non Road Mobile machinery (NRMM) above 37kW power rating should meet a minimum EU Stage IIIB emission criteria of Directive 97/68/EC. Subcontractor to provide engine plate details for all NRMM to enable the site register to be completed.
The City Law School, Sebastian Street Development
Supplementary Conditions
General Site Set-up Conditions
Item | Description
Accommodation / Hutting / Storage / Welfare
1 | The subcontractor shall allow for providing all his own site offices, containers, storage facilities, tool boxes, etc. necessary to supervise and manage the works. The security of these facilities will be the responsibility of the subcontractor. The location is to be agreed with BAM.
2 | A connection of power to the subcontractors site offices will be undertaken by BAM and the subcontractor is to include within his quotation a cost of £500.00 per connection for this service.
3 | Should the subcontractor require power to any other container, hut, storage facility, etc. then BAM will provide this at a cost of £500.00 per connection plus any builderswork necessary to install this supply e.g. trenches, ducting, etc.
4 | The subcontractor is then responsible for the electrical installation from the metered supply provided by BAM.
5 | BAM will monitor the metered supply on a monthly basis and deduct the cost of supplied power from the subcontractor's account. The subcontractor shall make due allowance within his quotation for this charge.
6 | The subcontractor shall make all his own provisions for any necessary telecom, power, water and drainage supply required to his site accommodation. The subcontractor shall not use BAM phones, fax or photocopying facilities and will be charged for doing so.
7 | BAM will provide and maintain Drying Rooms, Mess Rooms and WC facilities for male & female subcontract personnel. The subcontractors will be responsible to provide their own secure storage within the Drying Rooms. Padlocks are to be provided by operatives and any items will be stored at the operatives own risk.
8 | BAM will ensure that the welfare areas are kept in a clean and tidy state by cleaning at least once a day. This facility is provided for the benefit of all site personnel, however historically this has been abused by a minority of personnel to the detriment of the rest of the site and the welfare person in charge of maintaining a clean environment. If abuse occurs and graffiti of any nature appears on any surfaces within the welfare facilities the cost of BAM remedying such abuse will be charged to the relevant subcontractor. This will not be open for discussion or debate and although BAM will endeavour wherever possible to identify the culprit[s] behind such antisocial behaviour, where proof cannot be obtained, then equal contribution will be sort from the subcontractors.
9 | Notwithstanding the above any person[s] found mistreating the welfare facilities will be removed from site immediately.
10 | Eating or drinking anywhere other than in the mess room / canteen facility is strictly forbidden.
11 | The subcontractor accepts any liability for, and costs in association with, the relocation on site or removal from site of the subcontractor's site offices, containers, storage facilities, tool boxes, etc. deemed essential by BAM to progress the works.
12 | Full compliance with BAM logistics details including maintaining fire escape routes and pedestrian routes including working out of hours to maintain routes and re-routing where necessary.
Car Parking
13 | There will be no vehicle parking permitted on site, all subcontractors parking costs to be included within their tender
Electricity
14 | BAM will provide a temporary 110V electrical supply to locations to be advised by BAM.
15 | The subcontractor shall provide any specialist power supplies that he requires over and above 110V and include the cost of this plus advise of the nature of this requirement within the quotation return.
16 | BAM will provide safety lighting to the main core & circulation areas.
The City Law School, Sebastian Street Development
Supplementary Conditions
General Site Set-up Conditions
Item | Description
17 | The subcontractor shall provide any special lighting or task lighting that he requires to execute his works. Any special or task lighting installed by the subcontractor shall be capable of adaptation if required to permit the progress of the subcontractor and other trades work.
18 | The subcontractor shall not seek reimbursement from BAM for down time due to any loss of power supply irrespective of the cause of that loss.
Water
19 | BAM will provide a maximum of 25mm diameter mains pressure water supply to a location to be advised by BAM. The subcontractor is deemed to have satisfied himself in respect of the adequacy of this supply.
20 | The subcontractor shall provide any specialist water supplies that he requires over and above item 19 and include the cost of this plus advise of the nature of his requirement with his quotation return.
21 | The subcontractor shall allow for all transportation and storage of water required for his use on site from the supply provided by BAM in item 19 above.
22 | The subcontractor shall not seek reimbursement from BAM for down time due to any loss of water supply irrespective of the cause of that loss.
Materials Storage
23 | The subcontractor shall be responsible for the safe storage of his own materials whether temporary or for permanent inclusion into his works. The storage of these materials should be in accordance with the manufacturers recommendations and BAM Site Management may reject any such material that they believe has been detrimentally affected by non-conformance with the manufacturers recommended storage requirements.
The City Law School, Sebastian Street Development
Supplementary Conditions
General Site Attendance Conditions
Item | Description
Waste Management
1 | A third of all accidents on a building site are as a result of slips, trips and falls which is why BAM is determined to instil into subcontractors the absolute necessity to maintain a safe, clean and tidy site. Historically subcontractors have generally failed to comply with this and it is unfortunate that they are only galvanised into taking action when they feel the direct financial impact of their failure to comply with the foregoing. BAM believe that the safety of all site operatives and personnel takes priority over anything else on a construction site and will not hesitate to take whatever action is required to maintain that appropriate environment.
2 | BAM maintain that by reducing lost time as a result of accidents and keeping a safe, clean and tidy working environment actually improves subcontractor productivity a consequence of which is improved subcontractor profit.
3 | The following are measures that the subcontractor must take 'as a minimum' to eliminate the above statistic together with the penalties for non-conformance:
4 | The subcontractor shall remove all rubbish, debris, surplus material, spoil and all other waste resulting from their works on a daily basis to a designated location (excluding WP01 Piling, Groundworks, Drainage, Substructure & Superstructure RC Works, WP03 Structural Alterations, WP04 Structural Steelwork, and WP32 External Works who will remove from site ) in order to keep the site and works in a safe, clean and tidy state.
5 | The subcontractor shall remove all hazardous waste from site on a daily basis.
6 | The subcontractor shall remove all packaging and excessive surplus material from their works from site on a daily basis to keep the site and works in a safe, clean and tidy state.
7 | All subcontract related waste, rubbish, dirt and residues is to be removed from voids and cavities in the construction before closing in.
8 | BAM may decide to employ a waste management company to control waste and will seek a financial contribution from the subcontractor to finance this if the subcontractor does not comply with the above.
9 | The Subcontractors allowance for works in connection with waste removal must be a realistic one as any additional costs for labour and management time provided by BAM over and above the subcontractors quoted allowance will be deducted from the subcontractor's account. The minimum deduction for waste in skips provided by BAM that either:
a] exceeds the subcontractors skip allowance, or
b] should not be in that skip
will be:
● 4 hours Site Management @ £50.00 per hour
● 2 hours Project Surveyor @ £50.00 per hour
● Minimum of half of one skip @ £150.00 per 7 yard skip
● Any Sundry Cost [photographs, consumables, etc.]
● All Company Tied Costs
● Overhead Recovery
10 | If the subcontractor fails to remove all his own generated rubbish, debris, surplus material, packaging, spoil and all other waste in accordance with item 4 on a daily basis, then BAM will employ labour to do so. In such circumstances the procedure will be as follows:
a] BAM site management to photograph all waste not cleared to skips from subcontract works undertaken the previous day.
b] These photographs will be issued under cover of a form entitled 'Subcontract Request Notice' to the subcontractor's foreman by 12 noon of the following day on which the waste, rubbish, etc was generated.
c] The subcontractor shall then without question ensure that that waste, rubbish, etc is cleared by the end of the day of issue of the 'Subcontract Request Notice'. If it is not, BAM will remove and all costs arising will be charged to the subcontractor in accordance with item 6 above.
d] Failure to comply with this Subcontract Request Notice will result in BAM employing all labour and procuring the necessary plant and materials required to safely remove this waste, rubbish, etc. the cost of which will be deducted from the subcontractor's account.
e] The minimum deduction from the subcontractor's account for failure to comply with items a to d above will be:
● 4 hours Site Management @ £50.00 per hour [2 hours deducted irrespective of whether subcontractor attends to Subcontract Request]
The City Law School, Sebastian Street Development
Supplementary Conditions
General Site Attendance Conditions
Item | Description
● 2 hours Project Surveyor @ £50.00 per hour
● 4 hours Labour @ £20.50 per hour
● 2 hours Forklift & Driver @ £55.00 per hour
● Sundry Plant [cranage, wheelie bins, etc.]
● Minimum of half of one skip @ £150.00 per 7 yard skip
● Any Sundry Cost [photographs, consumables, etc.]
● All Company Tied Costs
● Overhead Recovery
11 | Ensure that non-hazardous material is disposed of at a tip approved by the Waste Regulation Authority. Remove all surplus hazardous materials and their containers regularly for disposal off site in a safe and competent manner as approved by the Waste Regulation Authority and in accordance with the relevant regulations. All waste transfer documentation to be retained on site. Any costs levied at BAM by the skip / tip companies for disposing of hazardous material in skips provided for non- hazardous waste will be deducted from the account of the subcontractor disposing such waste.
Site Deliveries
12 | The subcontractor must have the means and resource on site to safely unload his materials. If this resource is not available and BAM has to procure a labour and plant resource to undertake this operation so as not to cause congestion to delay to other deliveries then all direct and indirect costs associated with this will be deducted from the subcontractors account.
13 | The subcontractor will liaise with BAM's gateman / traffic controller and allow within their tender for all necessary traffic management to manoeuvre vehicles on, off & around the site. As a minimum the subcontractor should have trained traffic marshals with labour / banksman in attendance as necessary to manage the vehicle on, around & off the site. The subcontractor will need to consider the use of barriers, traffic cones, signage & suitable lighting to ensure the activity is undertaken in a safe manor
14 | The subcontractor shall ensure that all their vehicles leaving site whether operatives or deliveries do not in anyway cause damage or release anything that may result in damage, dirt or staining to surrounding roads and footpaths. If this occurs and the subcontractor fails to attend within a reasonable time period then BAM will undertake the necessary works and deduct the cost of same from the subcontractor's account.
15 | The subcontractor is to consider the availability of the turning space into the site access routes. The subcontractor should consider this & price the appropriate delivery vehicles to ensure the neighbours buildings and services are not damaged. Any damage will be chargeable to the subcontractor.
16 | Delay costs will be the subcontractors responsibility if deliveries are affected by local authority bodies statutory restrictions or road closure
17 | Due to the restrictive nature of the site, materials should be where possible delivered premixed to site
Unloading & Distribution
18 | BAM will provide 1 number tower crane for shared use by all subcontractors which can be booked on a "first come first served" basis. The tower crane will be available during the period specified on Programme Restraints Statement Appendix B. The hoist serving the Myddleton building will be available during the period specified on Programme Restraints Statement Appendix B, however priority will be given to critical programme activities as decided by BAM.
19 | Additional cranage, hoisting and lifting requirements required before or after the tower crane erection / dismantle dates will be provided by the subcontractors including all manual distribution
20 | Any cranage, hoisting or lifting requirements that are beyond the capacity of the tower crane are to be provided by the subcontractors
21 | Where BAM are providing the tower crane, we will provide 1 number driver & banksman, the subcontractors will be responsible for providing banksman & slingers from delivery to place of work. Each lift which is unsighted from unloading to place of distribution will require a minimum of 2 banksman / slingers. Radio's to be provided by the subcontractor to communicate with BAM crane drivers
The City Law School, Sebastian Street Development
Supplementary Conditions
General Site Attendance Conditions
Item | Description
22 | The subcontractor is to provide tower crane equipment compatible with BAM crane block to include but not to be limited to chains, slings, straps, skips, forks, lifting frames, boat skips, man cage.
23 | Loading platforms in or around the building to be provided by the subcontractor
24 | Use of the tower crane (where provided by BAM) outside the agreed site working hours must be agreed first with BAM site management. The subcontractor will be charged for all costs associated with operating the cranes outside the agreed site hours.
25 | BAM will provide one hoist for goods use only booked on a "first come first served" basis for material distribution. BAM will not be held responsible for any subcontractor delays for labour, material, plant or equipment distribution should the hoist be in use. Hoist 1 serving the new glazed tower building will be available during the period specified on Programme Restraints Statement Appendix B.
26 | Access to & from the work place before or after the hoist erection / dismantle dates will be via the staircases
27 | Any adaptions to the hoist for special deliveries will be charged to the subcontractor
28 | BAM will provide 1 number driver per goods hoist
29 | Any hoisting or vertical distribution requirements that are beyond the capacity of the hoists are to be provided by the subcontractor. Distribution across or to areas with changes in level of slabs or areas not serviced by the hoist is to be allowed for by the subcontractor.
30 | Use or the hoists outside the agreed site working hours must be agreed first with BAM site management. The subcontractor will be charged for all costs associated with operating the hoists outside the agreed site hours.
31 | The subcontractor is responsible for unloading materials to agreed storage areas as defined by BAM Site Management. Protection of stored materials is by the subcontractor.
32 | The subcontractor is to satisfy himself that he is aware of the size and restriction of the hoist including cage sizes, etc.
33 | The subcontractor is responsible for loading out and distributing materials to the face of his works both horizontally and vertically.
34 | Deliveries should be made on a “just in time” basis to meet the progress of the works the subcontractor is to make allowance for delivery via the most appropriate type of vehicle ie. Hiab lorry, rear unloader, side unloader, ridged back lorry. Your bid should allow for materials to be moved to suit site progress & sequence of other activities. Materials should not be stored next to the work face or other contractor’s works, on or against final or part completed works nor should materials be located in or around fire escape, access / egress routes. Materials should always be stored in a tidy manor clearly marked up the property of the contractor with labels identifying what the material is & installation location.
Setting Out
35 | BAM Construction will provide 1 no. master datum and 1 no. gridline in both N-S and E-W directions on each floor.
36 | The subcontractor will be responsible for all subsequent setting out of their works and are to make adequate provisions within their contract sum analysis for a competent site engineer.
37 | The Subcontractor has allowed for a post completion survey on immediate completion of the package works and shall issue same to BAM within 5 working days of completion.
38 | The subcontractor shall attend site as and when required to survey all previous trades works that they will interface with and satisfy themselves that construction design criteria in particular tolerances are correct. Should this not be the case the subcontractor is to notify BAM without delay and agree a process for rectification. BAM will not accept any costs from the subcontractor for commencing design, manufacture or construction on site that may incur additional cost over and above their tender allowance for not having first carried out the appropriate level of survey work
Scaffold
The City Law School, Sebastian Street Development
Supplementary Conditions
General Site Attendance Conditions
Item | Description
39 | BAM Construction will provide all external access scaffold [safety, access and working], handrail, edge protection, etc only as detailed within the BAM Scaffold Schedule. A copy of which can be obtained upon request.
40 | The subcontractor shall allow for any adaptions and / or alterations to the external scaffold which are over and above the scaffold allowed within the BAM Scaffold Schedule to allow access / egress of personnel and to facilitate and progress the works. A copy of which can be obtained upon request.
41 | Scaffold must not under any circumstances be erected, altered or adjusted by anyone other than a qualified scaffolder.
42 | Any access scaffold required for works up to 3.5m (working platform height) to be provided by the subcontractor. Scaffold towers and special scaffolding that is to be provided by the subcontractor is only to be erected by qualified personnel and must comply with NASC guidance. There will be no trafficking of these towers while operatives are on board. BAM will provide a working platform for the upper zone of slatted panelling to the main stairs
43 | Ladders / steps of any description will not be permitted for use on site unless it can be demonstrated that there is no other means of accessing the works irrespective of the cost of providing alternative measures. In any case ladders or steps shall only be used for access and not as a working platform to carry out works.
Protection
44 | The subcontractor shall allow for the protection of all his own materials while on site prior to inclusion into his works, during installation and until handed over and accepted by BAM's Site Management.
45 | The subcontractor shall make due allowance within his tender and / or fully advise of the protection required to surrounding trades works to ensure that damage does not occur to said works as a result of the subcontractor's works.
46 | Should the subcontractor choose to not adequately protect surrounding trades works or fails to advise of the protection required to prevent damage from his works and consequently damage occurs, the subcontractor will be liable for either:
a] The repair of damaged works to an equal or better standard prior to damage, or
47 | b] The direct and indirect cost of BAM instructing others to undertake this repair work on behalf of the subcontractor.
48 | The subcontractor shall allow for all adaptions required to the above protection to facilitate the works, to access / egress the works and to open up for inspection (a maximum limit of 1m2) as and when required by BAM Site management.
49 | The subcontractor shall allow for separate visit[s] to remove all his own protection and that he may have provided for the surrounding works.
50 | Allowance should be made for out of sequence working and making good where any opening up or leaving down for inspections or testing may be required. (a maximum limit of 1m2)
48 | The subcontractor shall allow for any protection necessary to holes, edges, steps, etc. formed as part of the subcontract works including any necessary warning signs.
51 | All protection materials provided by the subcontractor must be fire retardant flexible protective coverings to LPS 1207.
Demarcation / Warning Signs
52 | The subcontractor shall ensure that all necessary demarcation and / or warning signs are provided to safely facilitate the execution of his works and to ensure other trades are aware of the hazards and restrictions being imposed by the subcontract works.
Circulation and Common Areas
53 | The subcontractor shall include within his cost and programme for ensuring that all works in both common and circulation areas e.g. staircases, reception, corridors, etc. are undertaken outside of normal site hours. This cost will also include direct and indirect costs incurred by BAM for supervision and / or attendance [First Aider, Fire Officer, Site Manager etc.] and all associated compound, site set up, company tied and overhead costs.
The City Law School, Sebastian Street Development
Supplementary Conditions
General Site Attendance Conditions
Item | Description
Plant
54 | The subcontractor shall provide all necessary plant required to safely execute the subcontract works. BAM accept no liability in the event of mechanical breakdown or power failure.
55 | All plant should be maintained in good working order, with all test certificates available for BAM inspection 'on demand'.
56 | The subcontractor is responsible for the security of any plant, material [permanent or temporary], small tools, etc brought to site for use or incorporation into his works. BAM accept no liability for loss or damage to any of the foregoing. Subcontractor is to include all consumables required for the operation of plant.
Inspection of Work faces
57 | It is the responsibility of the subcontractor to inspect the tolerances of the workface at least 5 - 10 working days prior to start on site in order to establish the suitability of the structure / substrate. The subcontractor shall inform BAM Site Management in writing of any discrepancies in order for any remedial works to be carried out, 5 working days prior to the subcontractor's start on site date.
58 | BAM will not be held responsible for any cost incurred by the subcontractor building on or to substrate that is not within the recommended tolerance
59 | It is the subcontractor's responsibility to inspect the access provisions to the work face within reasonable time prior to work commencement.
60 | BAM will not entertain any claims for additional cost or time if these inspections have not been carried out.
Temporary Works
61 | The subcontractor is responsible for all temporary works applicable to his package and cost and programme implications of same.
Cleaning / Dust control
62 | The subcontractor shall allow for cleaning their works prior to offering them to BAM for snagging, once snagging is completed the subcontractor is required to re clean & offer the works to BAM.
63 | The subcontractor is to ensure that all interface, junctions & abutments with following trades are to be cleaned before the preceding trade commences their works.
64 | The subcontractor shall allow for a separate visit to return to site to carry out a final clean of their works prior to BAM contract PC.
65 | The subcontractor is to allow what ever measures necessary to control dust, vibration and noise pollution created by the subcontractors works.
66 | Upon completion clear all materials, debris, plant and equipment leaving site in a safe and suitable condition for the following trades, including any filling as necessary.