## SHEDULE OF WORKS
55 - 93 Knightsbridge
March & White scope Rev B
[13 empty] | Change |  | Change
| JMS | [8 empty] | Rev B |  | Rev A | B to A | Original | B to O | SRM comment on previous bid | RCL response
REF | REF | Item | Spec | Nr | Size | GA | Drawing | Details | Fine details | Value | Notes | Value |  | Value
|  | Preliminaries |  | 1 | [5 empty] | 98300 |  | 98300 | 0 | 98300 | 0 | Breakdown needed. Why the uplift? 52 weeks in your contract programme
|  | Fixed Price Adjustment |  | 1 | [5 empty] | 46500 |  | 46500 | 0 | 46500 | 0 | Why required? Can understand if install was years away but all materials will be bought and fitted this year. Fixed price adjustment already included in CSA (no omission made)
|  | Samples |  | 1 | [5 empty] | 20000 | Provisional Sum pending final confirmation of requirements | 20000 | 0 | 20000 | 0 | Sample requirements listed within spec but understand you would wait for confirmation on most of these
1 | 6728/26 | Grd floor reception desk |  | 1 |  | DR-I-X-400A | DR-I-X-2000A & 201A |  |  | 38176.594 | Softwood & MDF sub frame clad with flexable ply to outside and fiberglassed for liquid metal finish by Metal FX. Internal side to be veneered MDF with clear PU finish. All electrical goods & work to be by others. | 38176.594 | 0 | 38176.594 | 0
2 | 6728/129 | Grd floor reception wall panels elevation 1 | SF-02 | 1 | 4800mm X 3592mm | DR-I-X-300A | DR-I-X-1060A | DR-I-X-3100A,3001A & 3002A | DR-I-X-3100A (1 & 5) | 23063.3011 | MDF backing board with MDF rails, stiles & panels with hardwood timber moulds all applied to back boards. All finished Brushed white bronze by Metal FX. | 26265.7584 | -3202.4573 | 23063.3032 | -0.0021298 | Measure and tag ok
3 | 6728/130 | Grd floor reception wall panels elevation 1 | SF-03 | 1 | 4100mm X 2560mm & 1900mm X 3675mm | DR-I-X-300A | DR-I-X-1060A | DR-I-X-3100A,3001A & 3002A | DR-I-X-3100A (2) &3002 | 39533.0555 | MDF boards with hardwood cornice & corner/end piece. All finished Aged brushed brass by Metal FX. | 22590.3195 | 16942.736 | 39533.0609 | -0.005405 | Lift doors area incl in 4100mm measure. Please review | Please see marked up drawing. Lift doors not taken for
4 | 6728/131 | Grd floor reception wall panels elevation 2 | SF-03 | 1 | 4800mm X 2560mm | DR-I-X-300A | DR-I-X-1060A | DR-I-X-3100A,3001A & 3002A | DR-I-X-3100A (1 & 5) | 20589.071 | MDF boards, skirting & hardwood cornice & goal post all finished Aged brushed brass by Metal FX. Plaster finish by others. | 19340.3067 | 1248.7643 | 20589.0651 | 0.005934 | Measure and tag ok
5 | 6728/132 | Grd floor reception wall panels elevation 2 | SF-02 | 1 | 5300mm X 1100mm | DR-I-X-300A | DR-I-X-1060A | DR-I-X-3100A,3001A & 3002A | DR-I-X-3100A (2) &3001 (11) | 19264.1675 | MDF backing board with MDF rails, stiles & panels with hardwood timber moulds all applied to back boards. All finished Brushed white bronze by Metal FX. | 21809.0219 | -2544.8544 | 19264.1675 | 0 | This is tagged as SF-04, not SF-03. SF-03 skirting. Please review | This is the high level panel above SF-04, please refer marked up drawings
6 | 6728/133 | Grd floor reception wall panels elevation 3 | SF-03 | 1 | 4100mm X 2560mm & 1900mm X 3675mm | DR-I-X-300A | DR-I-X-1061A | DR-I-X-3100A,3001A & 3002A | DR-I-X-3100A (2) &3001 (11) | 50233.932 | MDF boards with hardwood cornice & corner/end piece. All finished Aged brushed brass by Metal FX. | 24315.995 | 25917.937 | 50233.9343 | -0.0023 | Measure and tag ok
7 | 6728/134 | Grd floor reception wall panels elevation 3 | SF-02 & SF-03 | 1 | 4800mm X 3592mm | DR-I-X-300A | DR-I-X-1061A | DR-I-X-3100A,3001A & 3002A | DR-I-X-3100A (1 & 5) | 24403.575 | MDF backing board with MDF rails, stiles & panels with hardwood timber moulds all applied to back boards. All finished Brushed white bronze OR Aged brushed brass by Metal FX. | 35063.9249 | -10660.3499 | 24403.5771 | -0.0021298 | Measure and tag ok
8 | 6728/135 | Grd floor reception wall panels elevation 4 | SF-03 | 1 | 450mm X 2560mm & 600mm X 2560mm | DR-I-X-300A | DR-I-X-1061A | DR-I-X-3100A,3001A & 3002A | DR-I-X-3100A (2) &3001 (11) | 10151.257 | MDF boards, skirting & hardwood cornice all finished Aged brushed brass by Metal FX. Metal trims & plaster finish by others. | 5705.2851 | 4445.9719 | 10151.2582 | -0.00115 | Measure and tag ok
9 | 6728/136 | Grd floor reception wall panels elevation 1 | SF-03 | 1 | 3000mm X 3700mm | DR-I-X-300A | DR-I-X-1062A | DR-I-X-3100A,3001A & 3002A | DR-I-X-3100A (2) &3001 (11) | 32962.979 | MDF boards with hardwood cornice & corner/end piece. All finished Aged brushed brass by Metal FX. | 18462.5727 | 14500.4063 | 32962.979 | 0 | Door included in SF-03 measure (not necessarily incorrect - just a note) | Door face panel included as same finish
10 | 6728/137 | Grd floor reception wall panels elevation 2 | SF-03 | 1 | 3000mm X 3700mm | DR-I-X-300A | DR-I-X-1062A | DR-I-X-3100A,3001A & 3002A | DR-I-X-3100A (2) &3001 (11) | 32538.629 | MDF boards with hardwood cornice & corner/end piece. All finished Aged brushed brass by Metal FX. | 19165.0007 | 13373.6283 | 32538.629 | 0 | Measure and tag ok
11 | 6728/138 | Grd floor reception ceiling panels (seating area) | SF-03 | 1 | 4100mm X 3000mm | DR-I-X-500A |  |  | DR-I-X-3100A (2) | 21350.8546 | MDF Boards All finished Aged brushed brass by Metal FX | 21350.8546 | 0 | 38257.7228 | -16906.8682 | High measure. Please review
12 | 6728/139 | Grd floor reception ceiling panels (bench area) | SF-03 | 1 | 5300mm X 4100mm | DR-I-X-500A |  |  | DR-I-X-3100A (2) | 34023.6793 | MDF Boards All finished Aged brushed brass by Metal FX | 34023.6793 | 0 | 52367.4248 | -18343.7454 | High measure. Please review
13 | 6728/140 | Grd floor reception ceiling panels (revolving door area) | SF-03 | 1 | 5300mm X 1900mm | DR-I-X-500A |  |  | DR-I-X-3100A (2) | 16384.7441 | MDF Boards All finished Aged brushed brass by Metal FX | 16384.7441 | 0 | 25123.7689 | -8739.0248 | High measure. Please review
14 | 6728/141 | Grd floor reception ceiling panels (reception desk) | SF-05 | 1 | 3500mm X 3500mm | DR-I-X-500A |  |  | DR-I-X-3100A (2) | 19893.0757 | MDF Boards All finished Brushed gun metal by Page lacquer | 25278.0542 | -5384.9785 | 19893.0757 | 0 | High measure. Please review | Original measure 3500mm x 3500mm, production x-010_1 drawing shows 3377mm x 3372mm
15 | 6728/142 | Grd floor reception ceiling panels (Chandelier area) | SF-05 | 1 | 4800mm X 5300mm | DR-I-X-500A |  |  | DR-I-X-3100A (2) | 39869.1583 | MDF Boards All finished Brushed gun metal by Page lacquer | 50998.4213 | -11129.263 | 39869.1583 | 0 | High measure. Please review | Original measure 4800mm x 5300mm, production x-010_1 drawing shows 4710mm x 5288mm
16 | 6728/143 | 1st floor lift lobby wall panels elevation 1 | SF-03 | 1 | 4 Nr 1200mm X 2600mm | DR-I-X-301A | DR-I-X-1063A |  | DR-I-X-3100A (2) &3001 (11) | 20891.3422 | MDF boards with hardwood cornice & corner/end piece. All finished Aged brushed brass by Metal FX. | 20891.3422 | 0 | 35887.8361 | -14996.4939 | 2 nr on this elevation. Further panels picked up below in elevation 2. Please review.
17 | 6728/144 | 1st floor lift lobby wall panels elevation 1 | PA-04 | 1 | 950mm X 2450mm & 950mm X 2450mm | DR-I-X-301A | DR-I-X-1063A |  | DR-I-X-3001 (7) | 4081.77 | MDF boards, metal trims & wallpaper | 4359.4947 | -277.7247 | 4081.7697 | 0.00025 | Measure and tag ok
18 | 6728/145 | 1st floor lift lobby wall panels elevation 2 | SF-03 | 1 | 2 Nr 1000mm X 2600mm, 2 Nr 900mm X 450mm, 1 Nr 1350mm X 2600mm & 1 Nr 700mm X 2600mm | DR-I-X-301A | DR-I-X-1063A |  | DR-I-X-3100A (2) &3001 (11) | 22095.8355 | MDF boards with hardwood cornice & corner/end piece. All finished Aged brushed brass by Metal FX. | 22095.8355 | 0 | 36435.1625 | -14339.327 | High measure. Please review
19 | 6728/146 | 1st floor lift lobby wall panels elevation 2 | PA-04 | 1 | 2 Nr 1200mm X 2600mm, 1 Nr 980mm X 500mm & 1 Nr 980mm X 2100mm | DR-I-X-301A | DR-I-X-1063A |  | DR-I-X-3001 (7) | 6119.4605 | MDF boards, metal trims & wallpaper | 6119.4585 | 0.0020125 | 6119.4585 | 0.0020125 | Measure and tag ok
20 | 6728/147 | 1st floor lift lobby wall panels elevation 4 | SF-03 | 1 | 1 Nr 700mm X 2600mm | DR-I-X-301A | DR-I-X-1064 |  | DR-I-X-3100A (2) &3001 (11) | 5263.3315 | MDF boards with hardwood cornice & corner/end piece. All finished Aged brushed brass by Metal FX. | 3140.1595 | 2123.172 | 5263.3315 | 0 | RCL to confirm SF-03 allowances around door | Please refer to marked up drawings
21 | 6728/148 | 1st floor lift lobby wall panels elevation 4 | PA-04 | 1 | 2 Nr 250mm X 2600mm, 3 Nr 1050mm X 550mm, 6 Nr 525mm X 1950mm, 1 Nr 500mm X 2600mm, 2 Nr 350mm X 2600mm, 2 Nr 900mm X 2100mm, 2 Nr 900mm X 550mm & 1 Nr 200mm X 2600mm | DR-I-X-301A | DR-I-X-1064 |  | DR-I-X-3001 (7) | 23080.6495 | MDF boards, metal trims & wallpaper | 23080.6455 | 0.004025 | 23080.6455 | 0.004025 | Measure and tag ok
22 | 6728/149 | 1st floor lift lobby ceilings (coridor area) | SF-03 | 1 | 2 Nr 2000mm X 1300mm | DR-I-X-501A |  |  | DR-I-X-5000A (3) | 15759.9488 | MDF Boards All finished Brushed gun metal by Metal FX | 14361.2671 | 1398.6817 | 15759.9488 | 0 | Measure and tag ok
23 | 6728/150 | 1st floor lift lobby ceilings (Lift area) | SF-05 | 1 | 6000mm X 2500mm | DR-I-X-501A |  |  | DR-I-X-5000A (3) | 20225.1778 | MDF Boards All finished Brushed gun metal by Page lacquer | 27346.7598 | -7121.582 | 20225.1778 | 0 | Measure and tag ok
24 | 6728/151 | 2nd floor lift lobby wall panels elevation 1 | SF-03 | 1 | 4 Nr 1200mm X 2600mm | DR-I-X-302A | DR-I-X-1065A |  | DR-I-X-3100A (2) &3001 (11) | 20891.3422 | MDF boards with hardwood cornice & corner/end piece. All finished Aged brushed brass by Metal FX. | 20891.3422 | 0 | 35887.8361 | -14996.4939 | High measure. Please revisit (2nr SF-03 panels withskirtings throughout)
25 | 6728/152 | 2nd floor lift lobby wall panels elevation 1 | PA-04 | 1 | 950mm X 2450mm & 950mm X 2450mm | DR-I-X-302A | DR-I-X-1065A |  | DR-I-X-3001 (7) | 4081.7755 | MDF boards, metal trims & wallpaper | 4359.4947 | -277.7193 | 4081.7697 | 0.00575 | Measure and tag ok
26 | 6728/153 | 2nd floor lift lobby wall panels elevation 2 | SF-03 | 1 | 2 Nr 1000mm X 2600mm, 2 Nr 900mm X 450mm, 1 Nr 1350mm X 2600mm & 1 Nr 700mm X 2600mm | DR-I-X-302A | DR-I-X-1065A |  | DR-I-X-3100A (2) &3001 (11) | 36435.1625 | MDF boards with hardwood cornice & corner/end piece. All finished Aged brushed brass by Metal FX. | 22095.8355 | 14339.327 | 36435.1625 | 0
27 | 6728/154 | 2nd floor lift lobby wall panels elevation 2 | PA-04 | 1 | 2 Nr 1200mm X 2600mm, 1 Nr 980mm X 500mm & 1 Nr 980mm X 2100mm | DR-I-X-302A | DR-I-X-1065A |  | DR-I-X-3001 (7) | 6119.4585 | MDF boards, metal trims & wallpaper | 6119.4585 | 0 | 6119.4585 | 0 | Measure and tag ok
28 | 6728/155 | 2nd floor lift lobby wall panels elevation 4 | SF-03 | 1 | 1 Nr 700mm X 2600mm | DR-I-X-302A | DR-I-X-1066A |  | DR-I-X-3100A (2) &3001 (11) | 5263.3315 | MDF boards with hardwood cornice & corner/end piece. All finished Aged brushed brass by Metal FX. | 3140.1595 | 2123.172 | 5263.3315 | 0 | SF-03 skirtings missed? | Please refer to marked up drawings
29 | 6728/156 | 2nd floor lift lobby wall panels elevation 4 | PA-04 | 1 | 2 Nr 250mm X 2600mm, 3 Nr 1050mm X 550mm, 6 Nr 525mm X 1950mm, 1 Nr 500mm X 2600mm, 2 Nr 350mm X 2600mm, 2 Nr 900mm X 2100mm, 2 Nr 900mm X 550mm & 1 Nr 200mm X 2600mm | DR-I-X-302A | DR-I-X-1066A |  | DR-I-X-3001 (7) | 23080.6495 | MDF boards, metal trims & wallpaper | 23080.6455 | 0.004025 | 23080.6455 | 0.004025 | Measure and tag ok
30 | 6728/157 | 2nd floor lift lobby ceilings (coridor area) | SF-03 | 1 | 2 Nr 2000mm X 1300mm | DR-I-X-502A |  |  | DR-I-X-5000A (3) | 15759.9488 | MDF Boards All finished Brushed gun metal by Metal FX | 14361.2671 | 1398.6817 | 15759.9488 | 0 | Measure and tag ok
31 | 6728/158 | 2nd floor lift lobby ceilings (Lift area) | SF-05 | 1 | 6000mm X 2500mm | DR-I-X-502A |  |  | DR-I-X-5000A (3) | 20225.1778 | MDF Boards All finished Brushed gun metal by Page lacquer | 27346.7598 | -7121.582 | 20225.1778 | 0 | Measure and tag ok
32 | 6728/159 | 1st floor lift lobby floor trim | MS-01 | 1 | 1 Nr 1900mm, 2 Nr 2000mm & 1 Nr 3200mm | DR-I-X-201A |  |  |  | 721.8393 | Supplied as B620 Antique brass from CAT in 5 Nr 2.715M lengths | 721.8393 | 0 | 721.8393 | 0 | Measure and tag ok
33 | 6728/160 | 2nd floor lift lobby floor trim | MS-01 | 1 | 1 Nr 1900mm, 2 Nr 2000mm & 1 Nr 3200mm | DR-I-X-202A |  |  |  | 721.8393 | Supplied as B620 Antique brass from CAT in 5 Nr 2.715M lengths | 721.8393 | 0 | 721.8393 | 0 | Measure and tag ok
34 | 6728/161 | 1st floor finish to RGA historic doors | PA-06 | 1 |  | DR-I-X-301A | DR-I-X-1063A |  |  | 6975.693 | Priced for collection of doors & overpanels and taken to Metal FX for finishing PA-06 to one side and Smooth colour to other to balance. | 12545.2396 | -5569.5466 | 6975.6909 | 0.0021275 | Ok
35 | 6728/162 | 2nd floor finish to RGA historic doors | PA-06 | 1 |  | DR-I-X-302A | DR-I-X-1065A |  |  | 6975.693 | Priced for collection of doors & overpanels and taken to Metal FX for finishing PA-06 to one side and Smooth colour to other to balance. | 12545.2396 | -5569.5466 | 6975.6909 | 0.0021275 | Ok
36 | 6728/163 | Grd floor reception coffer ceiling trims | MS-02 | 1 | 3500mm X 3500mm | DR-I-X-500A |  |  | DR-I-X-5000A (3) | 3192.0294 | Supplid as 75mm X 2mm MS-02 Metal trim | 3071.7509 | 120.2785 | 3192.0294 | 0 | Ok
37 | 6728/164 | 1st floor reception coffer ceiling trims | MS-02 | 1 | 6000mm X 2500mm | DR-I-X-501A |  |  | DR-I-X-5000A (3) | 2499.6144 | Supplid as 75mm X 2mm MS-02 Metal trim | 2412.6744 | 86.94 | 2499.6144 | 0 | Ok
38 | 6728/165 | 2nd floor reception coffer ceiling trims | MS-02 | 1 | 6000mm X 2500mm | DR-I-X-502A |  |  | DR-I-X-5000A (3) | 2499.6144 | Supplid as 75mm X 2mm MS-02 Metal trim | 2412.6744 | 86.94 | 2499.6144 | 0 | Ok
39 | 6728/166 | Grd floor reception lobby trims elevation 2 | MS-02 | 1 | 6 Nr 2700mm, 4 Nr 1400mm, 4 Nr 300mm & 2 Nr 2800mm |  | DR-I-X-1060A |  | DR-I-X-3101A (6) | 4067.0389 | Supplied as 10 Nr 3M lengths | 3927.2219 | 139.817 | 4067.0389 | 0 | Ok
40 |  | PROVISIONAL SUM as an EXTRA OVER to upgrade Dixon Jones specified doorsets to March & White details and specifications and to incorporate access control |  | 4 |  |  | DR-I-X-201A & 202A |  |  | 6000 | The doorsets as drawn by M & W will not achieve fire certification and/or have buildability issues | 6000 | 0 | 6000 | 0 | TBC
41 |  | Ted Todd Cymphoma Chevron Flooring. 450 x 80 x 19mm Smooth Satin Lacquered glued to base using Manufacturers approved adhesive; laid on and including 18mm ¦T & G plywood; secret nailed to New Era S2 Strata Cradle system (total height 142mm) , laid on 1000 gauge polythene. | T1-01 | 60 |  |  | DR-I-X-201A & 202A |  |  | 20043.81 |  | 20043.81 | 0 | 20043.81 | 0 | Ok
42 |  | Ted Todd Cymphoma Border. 220 x 20mm Oak Plank Brushed Burnished hardwax oiled glued to perimeters of Chevron using Manufacturers approved adhesive; laid on and including 18mm ¦T & G plywood; secret nailed to New Era S2 Strata Cradle system (total height 142mm) , laid on 1000 gauge polythene | T1-02 | 55 |  |  | DR-I-X-201A & 202A |  |  | 7329.41 |  | 7329.41 | 0 | 7329.41 | 0 | Ok
43 |  | Brass Angle trim | MS-01 | 72 |  |  | DR-I-X-201A & 202A |  |  | 3146.4 |  | 3146.4 | 0 | 3146.4 | 0 | Ok
|  | Total ADDITIONS | [7 empty] | 900785.4171 |  | 861398.5575 | 39386.8596 | 989107.3572 | -88321.9401
|  | OMIT RCL's assessment of Dixon Jones scope as attached |  | 1 | [5 empty] | 75929.85 |  | 75929.85 |  | 75929.85 |  | DJA omissions appear reasonable
|  | Extra Over value of SI Nr 2 | [7 empty] | 824855.5671 |  | 785468.7075 |  | 913177.5072
WE DO NOT HAVE FULL DETAILS THEREFORE SHOULD BE REGARDED AS BUDGETARY UNTIL THESE ARE RECEIVED OR THEY ARE DEVELOPED AT WORKSHOPS
ALTERNATIVE MANUFACTURERS / SUPPLIERS
ON SITE REPAIR COSTS

## Rev A
55 - 93 Knightsbridge
March & White scope Rev A | [14 empty] | JMS have produced a schedule of all panel sizes for all elements
[9 empty] | Rev A | Rev A |  | Previous | Previous | Change | SRM comment on previous bid | JMS response
REF | Item | Spec | Nr | Size | GA | Drawing | Details | Fine details | Rate | Value | Notes | Rate | Value
| Preliminaries |  | 1 | [5 empty] | 98300 | 98300 |  | 98300 | 98300 | 0 | Breakdown needed. Why the uplift? 52 weeks in your contract programme
| Fixed Price Adjustment |  | 1 | [5 empty] | 46500 | 46500 |  | 46500 | 46500 | 0 | Why required? Can understand if install was years away but all materials will be bought and fitted this year. Fixed price adjustment already included in CSA (no omission made)
| Samples |  | 1 | [5 empty] | 20000 | 20000 | Provisional Sum pending final confirmation of requirements | 20000 | 20000 | 0 | Sample requirements listed within spec but understand you would wait for confirmation on most of these
1 | Grd floor reception desk |  | 1 |  | DR-I-X-400A | DR-I-X-2000A & 201A |  |  | 38176.594 | 38176.594 | Softwood & MDF sub frame clad with flexable ply to outside and fiberglassed for liquid metal finish by Metal FX. Internal side to be veneered MDF with clear PU finish. All electrical goods & work to be by others. | 38176.594 | 38176.594 | 0
2 | Grd floor reception wall panels elevation 1 | SF-02 | 1 | 4800mm X 3592mm | DR-I-X-300A | DR-I-X-1060A | DR-I-X-3100A,3001A & 3002A | DR-I-X-3100A (1 & 5) | 26265.7584 | 26265.7584 | MDF backing board with MDF rails, stiles & panels with hardwood timber moulds all applied to back boards. All finished Brushed white bronze by Metal FX. | 23063.3032 | 23063.3032 | 3202.4551 | Measure and tag ok
3 | Grd floor reception wall panels elevation 1 | SF-03 | 1 | 4100mm X 2560mm & 1900mm X 3675mm | DR-I-X-300A | DR-I-X-1060A | DR-I-X-3100A,3001A & 3002A | DR-I-X-3100A (2) &3002 | 22590.3195 | 22590.3195 | MDF boards with hardwood cornice & corner/end piece. All finished Aged brushed brass by Metal FX. | 39533.0609 | 39533.0609 | -16942.7414 | Lift doors area incl in 4100mm measure. Please review | Overall area but does not include for lift doors themselves
4 | Grd floor reception wall panels elevation 2 | SF-03 | 1 | 4800mm X 2560mm | DR-I-X-300A | DR-I-X-1060A | DR-I-X-3100A,3001A & 3002A | DR-I-X-3100A (1 & 5) | 19340.3067 | 19340.3067 | MDF boards, skirting & hardwood cornice & goal post all finished Aged brushed brass by Metal FX. Plaster finish by others. | 20589.0651 | 20589.0651 | -1248.7584 | Measure and tag ok | Should be SF-03 see revised quote
5 | Grd floor reception wall panels elevation 2 | SF-02 | 1 | 5300mm X 1100mm | DR-I-X-300A | DR-I-X-1060A | DR-I-X-3100A,3001A & 3002A | DR-I-X-3100A (2) &3001 (11) | 21809.0219 | 21809.0219 | MDF backing board with MDF rails, stiles & panels with hardwood timber moulds all applied to back boards. All finished Brushed white bronze by Metal FX. | 19264.1675 | 19264.1675 | 2544.8544 | This is tagged as SF-04, not SF-03. SF-03 skirting. Please review | Should be SF-02 see revised quote
6 | Grd floor reception wall panels elevation 3 | SF-03 | 1 | 4100mm X 2560mm & 1900mm X 3675mm | DR-I-X-300A | DR-I-X-1061A | DR-I-X-3100A,3001A & 3002A | DR-I-X-3100A (2) &3001 (11) | 24315.995 | 24315.995 | MDF boards with hardwood cornice & corner/end piece. All finished Aged brushed brass by Metal FX. | 50233.9343 | 50233.9343 | -25917.9393 | Measure and tag ok
7 | Grd floor reception wall panels elevation 3 | SF-02 & SF-03 | 1 | 4800mm X 3592mm | DR-I-X-300A | DR-I-X-1061A | DR-I-X-3100A,3001A & 3002A | DR-I-X-3100A (1 & 5) | 35063.9249 | 35063.9249 | MDF backing board with MDF rails, stiles & panels with hardwood timber moulds all applied to back boards. All finished Brushed white bronze OR Aged brushed brass by Metal FX. | 24403.5771 | 24403.5771 | 10660.3477 | Measure and tag ok
8 | Grd floor reception wall panels elevation 4 | SF-03 | 1 | 450mm X 2560mm & 600mm X 2560mm | DR-I-X-300A | DR-I-X-1061A | DR-I-X-3100A,3001A & 3002A | DR-I-X-3100A (2) &3001 (11) | 5705.2851 | 5705.2851 | MDF boards, skirting & hardwood cornice all finished Aged brushed brass by Metal FX. Metal trims & plaster finish by others. | 10151.2582 | 10151.2582 | -4445.973 | Measure and tag ok
9 | Grd floor reception wall panels elevation 1 | SF-03 | 1 | 3000mm X 3700mm | DR-I-X-300A | DR-I-X-1062A | DR-I-X-3100A,3001A & 3002A | DR-I-X-3100A (2) &3001 (11) | 18462.5727 | 18462.5727 | MDF boards with hardwood cornice & corner/end piece. All finished Aged brushed brass by Metal FX. | 32962.979 | 32962.979 | -14500.4064 | Door included in SF-03 measure (not necessarily incorrect - just a note) | Door face panel included as same finish
10 | Grd floor reception wall panels elevation 2 | SF-03 | 1 | 3000mm X 3700mm | DR-I-X-300A | DR-I-X-1062A | DR-I-X-3100A,3001A & 3002A | DR-I-X-3100A (2) &3001 (11) | 19165.0007 | 19165.0007 | MDF boards with hardwood cornice & corner/end piece. All finished Aged brushed brass by Metal FX. | 32538.629 | 32538.629 | -13373.6283 | Measure and tag ok
11 | Grd floor reception ceiling panels (seating area) | SF-03 | 1 | 4100mm X 3000mm | DR-I-X-500A |  |  | DR-I-X-3100A (2) | 21350.8546 | 21350.8546 | MDF Boards All finished Aged brushed brass by Metal FX | 38257.7228 | 38257.7228 | -16906.8682 | High measure. Please review | See revised quote for correct cost and panel sizes
12 | Grd floor reception ceiling panels (bench area) | SF-03 | 1 | 5300mm X 4100mm | DR-I-X-500A |  |  | DR-I-X-3100A (2) | 34023.6793 | 34023.6793 | MDF Boards All finished Aged brushed brass by Metal FX | 52367.4248 | 52367.4248 | -18343.7454 | High measure. Please review | See revised quote for correct cost and panel sizes
13 | Grd floor reception ceiling panels (revolving door area) | SF-03 | 1 | 5300mm X 1900mm | DR-I-X-500A |  |  | DR-I-X-3100A (2) | 16384.7441 | 16384.7441 | MDF Boards All finished Aged brushed brass by Metal FX | 25123.7689 | 25123.7689 | -8739.0248 | High measure. Please review | See revised quote for correct cost and panel sizes
14 | Grd floor reception ceiling panels (reception desk) | SF-05 | 1 | 3500mm X 3500mm | DR-I-X-500A |  |  | DR-I-X-3100A (2) | 25278.0542 | 25278.0542 | MDF Boards All finished Brushed gun metal by Page lacquer | 19893.0757 | 19893.0757 | 5384.9785 | High measure. Please review | See revised quote for correct cost and panel sizes
15 | Grd floor reception ceiling panels (Chandelier area) | SF-05 | 1 | 4800mm X 5300mm | DR-I-X-500A |  |  | DR-I-X-3100A (2) | 50998.4213 | 50998.4213 | MDF Boards All finished Brushed gun metal by Page lacquer | 39869.1583 | 39869.1583 | 11129.263 | High measure. Please review | See revised quote for correct cost and panel sizes
16 | 1st floor lift lobby wall panels elevation 1 | SF-03 | 1 | 4 Nr 1200mm X 2600mm | DR-I-X-301A | DR-I-X-1063A |  | DR-I-X-3100A (2) &3001 (11) | 20891.3422 | 20891.3422 | MDF boards with hardwood cornice & corner/end piece. All finished Aged brushed brass by Metal FX. | 35887.8361 | 35887.8361 | -14996.4939 | 2 nr on this elevation. Further panels picked up below in elevation 2. Please review. | See revised quote for correct cost and panel sizes
17 | 1st floor lift lobby wall panels elevation 1 | PA-04 | 1 | 950mm X 2450mm & 950mm X 2450mm | DR-I-X-301A | DR-I-X-1063A |  | DR-I-X-3001 (7) | 4359.4947 | 4359.4947 | MDF boards, metal trims & wallpaper | 4081.7697 | 4081.7697 | 277.725 | Measure and tag ok
18 | 1st floor lift lobby wall panels elevation 2 | SF-03 | 1 | 2 Nr 1000mm X 2600mm, 2 Nr 900mm X 450mm, 1 Nr 1350mm X 2600mm & 1 Nr 700mm X 2600mm | DR-I-X-301A | DR-I-X-1063A |  | DR-I-X-3100A (2) &3001 (11) | 22095.8355 | 22095.8355 | MDF boards with hardwood cornice & corner/end piece. All finished Aged brushed brass by Metal FX. | 36435.1625 | 36435.1625 | -14339.327 | High measure. Please review | See revised quote for correct cost and panel sizes
19 | 1st floor lift lobby wall panels elevation 2 | PA-04 | 1 | 2 Nr 1200mm X 2600mm, 1 Nr 980mm X 500mm & 1 Nr 980mm X 2100mm | DR-I-X-301A | DR-I-X-1063A |  | DR-I-X-3001 (7) | 6119.4585 | 6119.4585 | MDF boards, metal trims & wallpaper | 6119.4585 | 6119.4585 | 0 | Measure and tag ok
20 | 1st floor lift lobby wall panels elevation 4 | SF-03 | 1 | 1 Nr 700mm X 2600mm | DR-I-X-301A | DR-I-X-1064 |  | DR-I-X-3100A (2) &3001 (11) | 3140.1595 | 3140.1595 | MDF boards with hardwood cornice & corner/end piece. All finished Aged brushed brass by Metal FX. | 5263.3315 | 5263.3315 | -2123.172 | RCL to confirm SF-03 allowances around door | See revised quote for correct cost and panel sizes
21 | 1st floor lift lobby wall panels elevation 4 | PA-04 | 1 | 2 Nr 250mm X 2600mm, 3 Nr 1050mm X 550mm, 6 Nr 525mm X 1950mm, 1 Nr 500mm X 2600mm, 2 Nr 350mm X 2600mm, 2 Nr 900mm X 2100mm, 2 Nr 900mm X 550mm & 1 Nr 200mm X 2600mm | DR-I-X-301A | DR-I-X-1064 |  | DR-I-X-3001 (7) | 23080.6455 | 23080.6455 | MDF boards, metal trims & wallpaper | 23080.6455 | 23080.6455 | 0 | Measure and tag ok
22 | 1st floor lift lobby ceilings (coridor area) | SF-03 | 1 | 2 Nr 2000mm X 1300mm | DR-I-X-501A |  |  | DR-I-X-5000A (3) | 14361.2671 | 14361.2671 | MDF Boards All finished Brushed gun metal by Metal FX | 15759.9488 | 15759.9488 | -1398.6817 | Measure and tag ok
23 | 1st floor lift lobby ceilings (Lift area) | SF-05 | 1 | 6000mm X 2500mm | DR-I-X-501A |  |  | DR-I-X-5000A (3) | 27346.7598 | 27346.7598 | MDF Boards All finished Brushed gun metal by Page lacquer | 20225.1778 | 20225.1778 | 7121.582 | Measure and tag ok
24 | 2nd floor lift lobby wall panels elevation 1 | SF-03 | 1 | 4 Nr 1200mm X 2600mm | DR-I-X-302A | DR-I-X-1065A |  | DR-I-X-3100A (2) &3001 (11) | 20891.3422 | 20891.3422 | MDF boards with hardwood cornice & corner/end piece. All finished Aged brushed brass by Metal FX. | 35887.8361 | 35887.8361 | -14996.4939 | High measure. Please revisit (2nr SF-03 panels withskirtings throughout) | See revised quote for correct cost and panel sizes
25 | 2nd floor lift lobby wall panels elevation 1 | PA-04 | 1 | 950mm X 2450mm & 950mm X 2450mm | DR-I-X-302A | DR-I-X-1065A |  | DR-I-X-3001 (7) | 4359.4947 | 4359.4947 | MDF boards, metal trims & wallpaper | 4081.7697 | 4081.7697 | 277.725 | Measure and tag ok
26 | 2nd floor lift lobby wall panels elevation 2 | SF-03 | 1 | 2 Nr 1000mm X 2600mm, 2 Nr 900mm X 450mm, 1 Nr 1350mm X 2600mm & 1 Nr 700mm X 2600mm | DR-I-X-302A | DR-I-X-1065A |  | DR-I-X-3100A (2) &3001 (11) | 22095.8355 | 22095.8355 | MDF boards with hardwood cornice & corner/end piece. All finished Aged brushed brass by Metal FX. | 36435.1625 | 36435.1625 | -14339.327
27 | 2nd floor lift lobby wall panels elevation 2 | PA-04 | 1 | 2 Nr 1200mm X 2600mm, 1 Nr 980mm X 500mm & 1 Nr 980mm X 2100mm | DR-I-X-302A | DR-I-X-1065A |  | DR-I-X-3001 (7) | 6119.4585 | 6119.4585 | MDF boards, metal trims & wallpaper | 6119.4585 | 6119.4585 | 0 | Measure and tag ok
28 | 2nd floor lift lobby wall panels elevation 4 | SF-03 | 1 | 1 Nr 700mm X 2600mm | DR-I-X-302A | DR-I-X-1066A |  | DR-I-X-3100A (2) &3001 (11) | 3140.1595 | 3140.1595 | MDF boards with hardwood cornice & corner/end piece. All finished Aged brushed brass by Metal FX. | 5263.3315 | 5263.3315 | -2123.172 | SF-03 skirtings missed? | See revised quote for correct cost and panel sizes
29 | 2nd floor lift lobby wall panels elevation 4 | PA-04 | 1 | 2 Nr 250mm X 2600mm, 3 Nr 1050mm X 550mm, 6 Nr 525mm X 1950mm, 1 Nr 500mm X 2600mm, 2 Nr 350mm X 2600mm, 2 Nr 900mm X 2100mm, 2 Nr 900mm X 550mm & 1 Nr 200mm X 2600mm | DR-I-X-302A | DR-I-X-1066A |  | DR-I-X-3001 (7) | 23080.6455 | 23080.6455 | MDF boards, metal trims & wallpaper | 23080.6455 | 23080.6455 | 0 | Measure and tag ok
30 | 2nd floor lift lobby ceilings (coridor area) | SF-03 | 1 | 2 Nr 2000mm X 1300mm | DR-I-X-502A |  |  | DR-I-X-5000A (3) | 14361.2671 | 14361.2671 | MDF Boards All finished Brushed gun metal by Metal FX | 15759.9488 | 15759.9488 | -1398.6817 | Measure and tag ok
31 | 2nd floor lift lobby ceilings (Lift area) | SF-05 | 1 | 6000mm X 2500mm | DR-I-X-502A |  |  | DR-I-X-5000A (3) | 27346.7598 | 27346.7598 | MDF Boards All finished Brushed gun metal by Page lacquer | 20225.1778 | 20225.1778 | 7121.582 | Measure and tag ok
32 | 1st floor lift lobby floor trim | MS-01 | 1 | 1 Nr 1900mm, 2 Nr 2000mm & 1 Nr 3200mm | DR-I-X-201A |  |  |  | 721.8393 | 721.8393 | Supplied as B620 Antique brass from CAT in 5 Nr 2.715M lengths | 721.8393 | 721.8393 | 0 | Measure and tag ok
33 | 2nd floor lift lobby floor trim | MS-01 | 1 | 1 Nr 1900mm, 2 Nr 2000mm & 1 Nr 3200mm | DR-I-X-202A |  |  |  | 721.8393 | 721.8393 | Supplied as B620 Antique brass from CAT in 5 Nr 2.715M lengths | 721.8393 | 721.8393 | 0 | Measure and tag ok
34 | 1st floor finish to RGA historic doors | PA-06 | 1 |  | DR-I-X-301A | DR-I-X-1063A |  |  | 12545.2396 | 12545.2396 | Priced for collection of doors & overpanels and taken to Metal FX for finishing PA-06 to one side and Smooth colour to other to balance. | 6975.6909 | 6975.6909 | 5569.5487 | Ok
35 | 2nd floor finish to RGA historic doors | PA-06 | 1 |  | DR-I-X-302A | DR-I-X-1065A |  |  | 12545.2396 | 12545.2396 | Priced for collection of doors & overpanels and taken to Metal FX for finishing PA-06 to one side and Smooth colour to other to balance. | 6975.6909 | 6975.6909 | 5569.5487 | Ok
36 | Grd floor reception coffer ceiling trims | MS-02 | 1 | 3500mm X 3500mm | DR-I-X-500A |  |  | DR-I-X-5000A (3) | 3071.7509 | 3071.7509 | Supplid as 75mm X 2mm MS-02 Metal trim | 3192.0294 | 3192.0294 | -120.2785 | Ok
37 | 1st floor reception coffer ceiling trims | MS-02 | 1 | 6000mm X 2500mm | DR-I-X-501A |  |  | DR-I-X-5000A (3) | 2412.6744 | 2412.6744 | Supplid as 75mm X 2mm MS-02 Metal trim | 2499.6144 | 2499.6144 | -86.94 | Ok
38 | 2nd floor reception coffer ceiling trims | MS-02 | 1 | 6000mm X 2500mm | DR-I-X-502A |  |  | DR-I-X-5000A (3) | 2412.6744 | 2412.6744 | Supplid as 75mm X 2mm MS-02 Metal trim | 2499.6144 | 2499.6144 | -86.94 | Ok
39 | Grd floor reception lobby trims elevation 2 | MS-02 | 1 | 6 Nr 2700mm, 4 Nr 1400mm, 4 Nr 300mm & 2 Nr 2800mm |  | DR-I-X-1060A |  | DR-I-X-3101A (6) | 3927.2219 | 3927.2219 | Supplied as 10 Nr 3M lengths | 4067.0389 | 4067.0389 | -139.817 | Ok
40 | PROVISIONAL SUM as an EXTRA OVER to upgrade Dixon Jones specified doorsets to March & White details and specifications and to incorporate access control |  | 4 |  |  | DR-I-X-201A & 202A |  |  | 1500 | 6000 | The doorsets as drawn by M & W will not achieve fire certification and/or have buildability issues | 1500 | 6000 | 0 | TBC
41 | Ted Todd Cymphoma Chevron Flooring. 450 x 80 x 19mm Smooth Satin Lacquered glued to base using Manufacturers approved adhesive; laid on and including 18mm ¦T & G plywood; secret nailed to New Era S2 Strata Cradle system (total height 142mm) , laid on 1000 gauge polythene. | T1-01 | 60 |  |  | DR-I-X-201A & 202A |  |  | 334.0635 | 20043.81 |  | 334.0635 | 20043.81 | 0 | Ok
42 | Ted Todd Cymphoma Border. 220 x 20mm Oak Plank Brushed Burnished hardwax oiled glued to perimeters of Chevron using Manufacturers approved adhesive; laid on and including 18mm ¦T & G plywood; secret nailed to New Era S2 Strata Cradle system (total height 142mm) , laid on 1000 gauge polythene | T1-02 | 55 |  |  | DR-I-X-201A & 202A |  |  | 133.262 | 7329.41 |  | 133.262 | 7329.41 | 0 | Ok
43 | Brass Angle trim | MS-01 | 72 |  |  | DR-I-X-201A & 202A |  |  | 43.7 | 3146.4 |  | 43.7 | 3146.4 | 0 | Ok
| Total ADDITIONS | [8 empty] | 861398.5575 |  |  | 989107.3572 | -127708.7997
| OMIT RCL's assessment of Dixon Jones scope as attached |  | 1 | [5 empty] | 75929.85 | 75929.85 |  | 75929.85 | 75929.85 | 0 | DJA omissions appear reasonable
| Extra Over value of SI Nr 2 | [8 empty] | 785468.7075 |  |  | 913177.5072 | -127708.7997
WE DO NOT HAVE FULL DETAILS THEREFORE SHOULD BE REGARDED AS BUDGETARY UNTIL THESE ARE RECEIVED OR THEY ARE DEVELOPED AT WORKSHOPS
ALTERNATIVE MANUFACTURERS / SUPPLIERS
ON SITE REPAIR COSTS