## Table 1
Project Name: |  | 21 Moorfields Mock-Up Schedule 21M-WEA-XX-XXX-SH-A-00500MockupSchedule.xlsb 13.11.2020 C03
Document:
Job/File Ref:
Date:
Ref no. | Specification |  | Product Ref. Details | Description | Size | Sample | Mock-Up | Prototype | Benchmark | Comments
SRM 013 and M006 |  |  | TYPICAL GROUND FLOOR PASSENGER LIFT LOBBY - INTERIOR FINISHES & LEVEL 01 LIFT LOBBY LIGHTING STRATEGY | For details of size and content of the Visual Mock-up, refer to 21M-WEA-CMA-XXX- SK-A-0048 - P04. To include: Metal Tile Ceiling (CLG-911) Bespoke edge trim to interface lighting detail Bespoke edge trim to interface stone wall detail Stone Wall Panel / Lining (LIN-801) Metal trim to interface of linear light (AMW-312) Timber Wall Panel / Lining (LIN-803) Lift Signage Bespoke Stone Feature Wall Lining Natural Stone Floor Tiling (FLH-121 & FLH-122) Linear light MA1 to front face of door frame and ceiling - wall and ceiling detail as per design intent |  |  | SRM 013 and M006 |  |  |  | 7300 | Timber Wall Panel / Lining (LIN-803)
SRM 015, M009 BENCHMARK and M010 BENCHMARK |  |  | WASHROOM DESIGN INTENT MALE WC- INTERIOR FINISHES & LIGHTING STRATEGY | Working mock-up of Male WC (whole room to be constructed based on typical washroom: Core 02, Level 05) to include: SRM 015 to include: Plasterboard MF Ceiling-Moisture Resistant (CLG-103) Metal Tile Ceiling (CLG-305) Mirror (FFE-401) including Metal Tile Trim (TRM-602) Behind Mirror Soap Dispenser (SAN-611) Behind Mirror Paper Towel Dispenser (SAN-601) Ceramic Wall Tiling (LIN-104) Wall mounted infrared sensor tap (SAN-401) 3 no. Built in white glazed steel basin (SAN-101) Vanity Unit (PAN-301) Bespoke hook to underside of vanity (SAN-671) Exposed Bottle Trap (SAN-501) Bespoke stainless steel bin (SAN-621) Duct Access Panel (PAN-201) Back to wall floor standing toilet (SAN-201) 1 no. WC Sensor Flush (SAN-211) Toilet Roll Holder (SAN-631) Toilet Brush Holder (SAN-702) Glazed Urinal Screen / Divider (IWS-521) 1 no. Urinal (SAN-301) Stainless Steel Skirting ( TRM-161) Ceramic Floor Tiling (FLH-104 & FLH-101) Raised Floor- Calcium Sulphate (RAF-111) M009 and M010 Lighting mock-up to include MB ceiling cove lighting detail (with wall and ceiling detail as design intent) and MV luminaire behind mirror (one mirror complete with lights on both sides - wall and ceiling as per design intent) | [6 empty] | 7300 | Free issue one number entrance door frame and architraves
| L20 |  | INTERNAL DOORS | L20.2100 SUBMITTALS |  | L20.2103 Post Contract Award Samples | L20.2104 Mock-up Requirements | L20.2105 Prototype Requirements | L20.2106 Quality Benchmark Requirements
|  |  |  | Tender Submittals |  | In accordance with Section A.4000, submit post contract award samples of the following: | Submit mock-ups in accordance with Section A.4000 as follows: | Submit prototypes in accordance with Section A.4000 as follows: | Submit quality benchmarks, in location(s) to be agreed with the Employer, in accordance |  | WP7300 | As described in column H.
|  |  |  | L20.2101 Tender Response |  | a) 300mm x 200mm samples of doors, including lipped edge detail, forming the proposed | a) Not required. | a) Not required. | with Section A.4000: |  | WP7300 | As described in column H.
|  |  |  | a) Provide tender submittals in accordance with the requirements of Section A.4000 of |  | control samples for the project. |  |  | a) First completed installation of each type of system. |  | WP7300 | As described in column H.
|  |  |  | the Specification. |  | b) Door frame minimum 300mm of each type. |  |  |  |  | WP7300 | As described in column H.
|  |  |  | b) Submit a design response with the tender proposal, to include profiles of typical |  | c) Samples of fire and smoke seals. |  |  |  |  | WP7300 | As described in column H.
|  |  |  | conditions, with dimensions. |  | d) Samples of acoustic seals. |  |  |  |  | WP7300 | As described in column H.
|  |  |  | c) The tender design response shall include: |  | e) Samples of glazing materials. |  |  |  |  | WP7300 | As described in column H.
|  |  |  | i) Samples where specified. |  | f) Refer to Section P21 for sample requirements of ironmongery. |  |  |  |  | WP7300 | As described in column H.
ii) List of Tests included.
iii) QA/ QC programme.
iv) List of proposed Working Drawings.
v) Summary of deviations from the Design Drawings and the Specification.
vi) Outline technical specifications reflecting proposed materials/ systems.
vii) A list of proposed suppliers and subcontractors to be used.
Samples, Mock-ups, Prototypes and Quality Benchmarks
| P20 |  | UNFRAMED ISOLATED TRIMS/ SKIRTINGS/ SUNDRY | P20.2100 SUBMITTALS |  | P20.2103 Post Contract Samples | P20.2104 Mock-ups | P20.2105 Prototypes | P20.2106 Quality Benchmark Requirements |  | WP7300 | 300mm sample of all skirting types
|  |  |  | Tender Submittals |  | In accordance with Section A.4000, submit post contract samples of the following: | Not required. | Not required. | Submit the following quality benchmarks, in locations to be agreed with the Employer, in
|  |  |  | P20.2101 Tender Response |  | a) Minimum 300mm of each type of proposed work, including specified finish. |  |  | accordance with Section A.4000:
|  |  |  | a) Provide tender submittals in accordance with the requirements of Section A.4000 of |  | b) A sample of each proposed visible fixing. |  |  | a) First completed room/ area of each type of work.
the Specification.
b) A design response shall be submitted with the tender proposal, to include profiles of
typical conditions, with dimensions.
c) The tender design response shall include:
i) Samples where specified.
ii) List of Tests included.
iii) QA/ QC programme.
iv) List of proposed Working Drawings.
v) Summary of deviations from the Design Drawings and the Specification.
vi) Outline technical specifications reflecting proposed materials/ systems.
vii) A list of proposed suppliers and subcontractors to be used.
Samples, Mock-ups, Prototypes and Quality Benchmarks
| P21 |  | IRONMONGERY | P21.2100 SUBMITTALS |  | P21.2103 Post Contract Award Samples | P21.2104 Mock-up Requirements | P21.2105 Prototype Requirements | P21.2106 Quality Benchmark Requirements
|  |  |  | Tender Submittals |  | Refer to the Ironmongery Schedule. | Refer to the Ironmongery Schedule. | Submit prototypes in accordance with Section A.4000 as follows: | Submit quality benchmarks, in location(s) to be agreed with the Employer, in accordance |  | WP7300 | Full Ironmongery Sample boards including all door signage.
|  |  |  | P21.2101 Tender Response |  |  |  | a) Refer to the requirements of Section L20 of the Specification. | with Section A.4000:
|  |  |  | a) Provide tender submittals in accordance with the requirements of Section A.4000 of |  |  |  |  | a) Refer to the requirements of Section L20 of the Specification.
the Specification.
b) A design response shall be submitted with the tender proposal, to include profiles of
typical conditions, with dimensions.
c) The tender design response shall include:
i) Samples where specified.
ii) List of Tests included.
iii) QA/ QC programme.
iv) List of proposed Working Drawings.
v) Summary of deviations from the Design Drawings and the Specification.
vi) Outline technical specifications reflecting proposed materials/ systems.
vii) A list of proposed suppliers and subcontractors to be used.
Samples, Mock-ups, Prototypes and Quality Benchmarks