## N D Queries
RAPHAEL CONTRACTING LTD
SRM - VSW - Hilton Hotel
Schedule of Order Queries
[5 empty] | Comment | SRM Response 06/03/2020 | Further comments - 16/03/2020 | SRM Response - 23/03/2020 | RCL Response - 23/03/2020 | SRM Response 07/05/2020 | RCL Response 21/05/2020
Item | Document | Section | Subject | Ref
1 | Works Contract Sum | Gensler Doors | Ironmongery Set |  | As stated within our tender return our quotation is based upon 3v's Schedule TS0162-T16, should disceprencies exist between this and the ironmongery set column the schedule takes precedence | Agreed | SRM's agreement will need to be confirmed within Volme 2 or the Works Contract Sum | Wording to be adivised - MC | Awaiting SRM response | Assume this is in relation to Gensler door tab within CSA. Agree that 3v scheudle takes precedence. | Correct. Please include a statement that the 3v schedule takes precedence
2 | Works Contract Sum | Gensler Doors | Ironmongery |  | As stated within our tender return our quotation is based upon 3v's Schedule TS0162-T16, should disceprencies exist between this and the Gensler Schedule referred to and/or the quantities listed the 3v schedule takes precedence | Agreed | SRM's agreement will need to be confirmed within Volme 2 or the Works Contract Sum | Wording to be adivised - MC | Awaiting SRM response | Assume this is in relation to Gensler door tab within CSA. Agree that 3v scheudle takes precedence. | Correct. Please include a statement that the 3v schedule takes precedence
22 | Volume 2 | Page 4 | Spec & Drawings | 1.7.3.4 | We have not allowed for any works descibed within a specification but not shown on the drawings | This clarification also needs to read "We have not allowed for any works descibed within a specification but not shown on the drawings, unless described and priced within the CSA." | Volume 2 does not appear to have been amended | Wording to be adivised - MC | Awaiting SRM response | Ammended on Page 10 of Volume 2 and front sheet on CSA. | Vol 2 amended please issue revised CSA
23 | Volume 2 | Pages 6 to 10 | Scope |  | Where discrepencies exist between volume 2 and the works contract sum and / or this document, the works contract sum / this document take precedence | No, when agreed all these amendmants will be included within the CSA/ Volume 2 etc. - To be reviewed by Raphael | SRM's comment has resulted in the following additional queries:- | Wording to be adivised - MC | No action required from SRM |  | Closed out
a | Volume 2 | Page 6 |  | 2.1.1 |  |  | Veneered bedroom entrance doors and all doors that are specified as being painted are to be provided primed | Wording has no mention on door finish so wording to remain. | Wording states (in line 3) "supplied primed or factory finished however stated in the specification". The specification has the bedroom entrance doors as veneered and any painted doors as factory finished whereas, in both instances, they are actually primed for on site decoration by others | Ammended on page 6 of volume 2. | Closed out
b | Volume 2 | Page 6 |  | 2.1.4 |  |  | We do not believe that all of these metal finishes are by RCL | TBC | Awaiting SRM response | Clarified in VOL 2 scope. | Clause 2.1.4 not amended?
e | Volume 2 | Page 6 |  | 2.1.14 |  |  | Protection will not be installed until the works have been signed off by SRM | Agreed and amended. | Please line through the sentence that is still in a black font | Do not agree to remove sentence in black. Still stands. | This clause is too open ended RCL cannot be in a position where they could be continually instructed by SRM to remove and replace protection
g | Volume 2 | Page 8 |  | 2.3.5 |  |  | We assume that the veneered panelling referred to is in fact PL-001 | Agreed | Please amend wording | Agreed. | Clause reference amended to 2.20.5. Wording not amended?
j | Volume 2 | Page 9 |  | 2.3.12 |  |  | These works have "excluded" noted against them within the works contract sum | Further clarification needed. What item within CSA do you think it refers too? | Ballroom tab. Excel row 36 | Agreed. | Clause reference amended to 2.20.12. Wording not amended?
27 | Volume 2 | Page 7 | Moisture / humidity | 2.1.11 | The control of moisture / humidity is not our responsibility | All material until handed over is under the management and protection of Raphael. All humidity and moisture to be controlled by SRM. | Volume 2 does not appear to have been amended | Agreed and amended. | We are not sure what is meant by "agreed with SRM works staff", please make it clear that RCL are not "to control moisture / humidity" in any areas of the building | Ammended; SRM are to provide moisture contol. Updated and agreed. This wording is to clairfy that SRM will take control of moisute control if the materials are stored where requested by SRM e.g. not left out to get wet etc… | This clause does not make it clear that SRM are responsible for the control of moisture / humidity in finished work locations as well as storage areas
NEW |  | Page 12 | Design Responsibility | 3 |  |  |  |  | Please line through "Applicable - CDP LEVE 3" | MC Confirmed with ST and ammended. | Closed out
NEW |  | Page 12 | Design Responsibility | 3.1.1 |  |  |  |  | Please line this clause through | MC Confirmed with ST and ammended. | Clause 3.1.1 not amended?
34 | Volume 2 | Page 11 | Design Responsibility | 3.1.3 | It is the design teams responsibility to ensure that all specified materials comply with ER's, Building Regs etc | Agreed, Raphael to ensure this complies with specification and SRM requirments. | Volume 2 does not appear to have been amended | This is to be done in collaboration with SRM and Gensler Design Team. | Please line through the text in a black and remove the text in a red font and replace it with "The works contractor (utilising his technical expertise) will, if requested, assist SRM and the Gensler Design Team in a reviw of all of the documents in this enquiry to advise whether, in their opinion, they conform to Genslers specifications | Amenmant made - remain RCL comments incorporated in clause already. | The amendment made by SRM to clause 3.4 is not sufficient, it still reads that it is RCL's responsibility to satisfy ourselves that the design teams proposals are correct, albeit we are now to do this in conjunction with Gensler and SRM. It also states that RCL are responsible for testing which we have not allowed for. Please reword this clause as proposed by RCL 23/03/2020
38 | Volume 1 | Page 46 | Working Hours | 9.3.1 | Our working hours are 7:30 to 17:00 Monday to Friday | Noted | Volume 1 does not appear to have been amended | No need for amendmant. | Awaiting SRM response | As stated previously, no ammendmant required. | Please confirm that the working hours within Vol 1 are the hours the site is open for not RCL's working hours which are 07:00 to 17:00 Monday to F.riday
39 | Volume 1 | Page 47 | Return visits | 10.2.5 | We have not allowed for return visits, we have assumed reasonable continuity | Agreed | Volume 1 does not appear to have been amended | As per programme section within Works Contract order. | Awaiting SRM response | The Works contract order covers this statement. | In the SRM response 06/03/2020 column SRM agreed with RCL's comments
40 | Volume 1 | Page 47 | Spec & Drawings | 10.2.9 | We have not allowed for any works descibed within a specification but not shown on the drawings | Agreed, "We have not allowed for any works descibed within a specification but not shown on the drawings, unless described and priced within the CSA." | Volume 1 does not appear to have been amended | Wording to be adivised - MC | Awaiting SRM response | Agreed. As stated in Volume 2 Page 10. | Please amend volume 1 as well