## N D Queries
RAPHAEL CONTRACTING LTD (RCL)
SRM - 21 Moorfields
Commentary Table
[5 empty] | RCL Comments - 01/12/2020 | SRM Comments - 02/12/2020 | RCL Comments - 27/12/2020
Item | Document | Page | Clause | Subject
1 | Volume 1 |  | Generally | Generally | If discrepencies exist between Volume 1 and the PTI minutes the latter takes precedence | The PTI is not a sub-contract document. Please send proposed ammendments in relation to Vol 1 to SRM for reviewal (if any).The Vol 1 takes precedence. | Please refer to items 2 & 3 below
2 | Volume 1 | 48 | 9.3.1 | Site Working Hours | For the avoidance of doubt whilst the site may open between 8am and 6pm on weekday's, RCL's working hours are 8am to 5:30pm | RCL to confirm that they can deliver the tender programme. | Confirmed
3 | Volume 1 | 48 | 9.3.1 | Site Working Hours | For the avoidance of doubt whilst the site may open between 9am and 2pm on Saturday's, RCL have not allowed to work Saturdays | RCL to confirm that they can deliver the tender programme. | Confirmed
4 | Sub-Con Mods | 8 | 2.1.5 | Consents | It is the architects responsibility to ensure that the design complies with these consents | Clause 2.1.5 specifies the requirement on Raphael to be compliant to consents only in relation to their Sub-Contract Works and the Sub-Contractor's Designed Works rather than all works, therefore this is limited in scope. It is standard compliance for sub-contractors to comply with Consents. | Closed out
5 | Sub-Con Mods | 8 | 2.1.6 | Design | This clause needs to be read in conjunction with the agreed definition of RCL's design responsibility within Volume 2 | Noted. No further action required. | Closed out
6 | Sub-Con Mods | 13 | 2.13.1 | Sub-Contractors warranty | This clause needs to be read in conjunction with the agreed definition of RCL's design responsibility within Volume 2 | Noted. No further action required. | Closed out
7 | Sub-Con Mods | 24 | 3.3B | Sub-Sub-Contractors warranty | We have not allowed to provide Sub-Sub-Contractors warranties | So long as all of the materials and works are being installed by RCL, we will not be seeking a sub-sub warranty. Please note that all product warranty's will need to be provided in accordance to the specifications and upon SRMs request. RCL to confirm?
8 | PCG | 3 | 8 | Assignment | We cannot accept unlimited assignments | This is a flow down from the Main Contract. We require all sub-contractors to accept unlimited assignments.
9 | Sub-Contractors warranties | 6 & 13 | 5 | P I Insurance | We carry £5m cover | Noted. No further action required. | Closed out
10 | Sub-Contractors warranties | 7 & 14 | 7 | Assignment | We cannot accept unlimited assignments | This is a flow down from the Main Contract. We require all sub-contractors to accept unlimited assignments.