## N D Queries
RAPHAEL CONTRACTING LTD
SRM - VSW - 21 Moorfields
Schedule of Volume Two Queries
[5 empty] | Comment | Comment between RCL and SRM on 19/11/2020 | SRM Design Manager Response on 24/11/2020 | SRM and RCL Meeting on 27/11/2020
Item | Section | Page | Clause | Subject
1 | Generally |  | Generally | Testing | We have allowed for all necessary fire and acoustic certificates etc but we have not allowed for any actual testing | RCL do not foresee this as a requirment from their experiences. The doors already have been tested off-site by others and RCL can forward on the relevant certification. Stafford Bridge supplier still outstanding and await comments from WEA. | This is satisfactory if RCL can provide historical data - RCL will provide this to SRM. | RCL have agreed on this.
2 | Generally |  | Generally | Sealants | We have allowed for all necessary intumescent and acoutic sealants but no other, the sealant will not be fair faced | Sealant will not be visible for the timber doors. RCL do not have the capacity nor the capability for fair faced mastic. SRM can arrange a mastic man, as we understand the current specified dooes will be concealed by the drames/architraves. | Ok - Can RCL advise from the detail drawings if the sealants will be visible and which ones? If sealants are not visible this should not be a problem. Note: RCL should fully fill and seal these where possible. | RCL and SRM - to advise if there are any visible mastic on the metal doors drawings.
3 | Generally |  | Generally | Drawings | We will need to agree with yourselves a list of drawings and schedules that we are to provide that will then need to approved by the Design Team. We have not allowed for "as built" drawings | Sue to respond. | RCL to submit proposed list. We would expect, at the very least, a door schedule , ironmongery schedule and typical door details drawings | RCL to action as per Sue's requirements as per cell I13.
4 | 1. Scope of Works | 3 | 1.2 | Door types | There do not appear to be any door types DRS-405 or DRS-305 within our package | Noted. This will be omitted and ammended in the Vol 2.
5 | 1. Scope of Works | 4 | Bullet point 2 | Door types | We have not allowed for "any other door types within the building envelope" | RCL have allowed for doors as per the door schedules excluding the glazing doors as this will be by others. |  | Noted. Will be ammended.
6 | 1. Scope of Works | 4 | Bullet point 3 | Samples | We have allowed to provide representative samples of door types not "samples of all door types" etc | RCL will provide a scaled down sample of a typical door type along with all the ironmongery finishes etc. | RCL should respond to 21M Sample schedule and populate with their proposed samples. | RCL to allow for all the listed items that is joinery and doors related in the sample schedule document.
7 | 1. Scope of Works | 4 | Bullet point 4 | Decoration | We have not allowed to decorate the doors | Decoration by others Stafford bridge come pre-installed finish but not PPC. |  | Noted.
8 | 1. Scope of Works | 4 | Bullet point 6 |  | We have not allowed for the contents of this clause (reinforcement, waterproofing etc) | Not Applicable to the works at 21m |  | Noted. Will be ammended.
9 | 1. Scope of Works | 4 | Bullet point 10 | Security | We have not allowed to fix free issue equipment to our doors | SRM would prefer that RCL to install all the ironmongery including those that are free issued by others to be installed upon the works that RCL will be providing. E.g. doors, frames etc. |  | SRM have asked Grattes to provide a list that will be free issued to RCL for install. SRM will forward once received.
10 | 1. Scope of Works | 4 | Bullet point 11 | Temp doors | Are not currently within the CSA | This will be included in your order. Quantum / Scope Tbc. |  | This is now included.
11 | 1. Scope of Works | 4 | Bullet point 13 | Temp locks | We have currently allowed for temporary cylinders not temporary locks and for cylinders with 4 keys but this clause may need to be amended as a result of VE | SRM agree with this methodology. Vol 2 has been ammended. RCL Is this as per the suiting requirements? |  | SRM to check with BK and PJ and the site team to see if they agree to this methodology.
12 | 1. Scope of Works | 5 | Bullet point 2 | Undercuts | If necessary we will comment upon this clause under separate cover
13 | 1. Scope of Works | 5 | Bullet point 3 | Doc M | It is the architects responsibilty NOT ours to ensure doors & ironmongery comply with Doc M | Sue - to respond | Agreed - RCL should still assist and advise if and where there is a lack off compliance in this regard.
14 | 1. Scope of Works | 5 | Bullet point 5 | Sealants | We have allowed for all necessary intumescent and acoutic sealants but no other, the sealant will not be fair faced | Same as item 2.
15 | 1. Scope of Works | 5 | Bullet point 7 | Vision panels | If necessary we will comment upon this clause under separate cover
16 | 1. Scope of Works | 5 | Bullet point 8 | Sequencing | The only return visit allowed for as those that are identified within an agreed programme. There are not currently any temporary leaves within our order | Programme has been issued to RCL for comments. RCL added that they will genrerally provide return visit to doors but not at every single one. RCL advise approximately 3 return visits per floor.
17 | 1. Scope of Works | 5 | Bullet point 9 | Protection | Generally primed doors will not receive any protection, frames to high traffic areas will receive proprietary jamb protectors, a regime for the protection of ironmongery will need to be agreed | All doors and frames need to be protected.
18 | 1. Scope of Works | 6 | 1.3 | Skirting | In general skirting will be secret fixed with adhesive, the occasional mechanical fixing will be required, the fixing hole will need to be filled by others | SRM notes this comment. The reason for this is to accommodate site dimensions/tolerances.
19 | 1. Scope of Works | 6 | 1.7 | Surveys | We have not allowed for the contents of this clause (reinforcement, waterproofing etc) | Same as item 8
20 | 1. Scope of Works | 7 | 1.13 | CDP | Our design responsibilty is defined in section 1.5 (subject to the queries that we have raised) | Sue to respond. | See below
21 | 1. Scope of Works | 7 | 1.18 | Design | Our design responsibilty is defined in section 1.5 (subject to the queries that we have raised), ultimate responsibilty for managing interfaces lies with SRM | Sue to respond. | Agreed
22 | 1. Scope of Works | 7 & 10 | 1.19 & 1.42 | Liason | We will assist SRM in liasing with the Environmental Health Officer etc but this is not our responsibilty | RCL have do dealings with these authorities. RCL would assist SRM with any queries or liasons by these authorites.
23 | 1. Scope of Works | 8 & 10 | 1.23 & 1.43 | Storage | We have not allowed for storage off site | All deliveries will be delivered straight to site from the suppliers.
24 | 1. Scope of Works | 8 | 1.26 | Finish | We have allowed for all doors and frames to be supplied primed, the finish to the ironmongery will be as the approved ironmongery board | Noted.
25 | 1. Scope of Works | 8 | 1.28 | Compliance | This clause needs to be read in conjunction with the balance of the agreed order numbered documents | This will be agreed between SRM and RCL. No action required.
26 | 1. Scope of Works | 9 | 1.32 | Surveys | We have not allowed to survey the structure | RCL allowed to survey structure openings. RCL will not be doing building surveys. I.e. Where the opening is RCL will simply install their works. | Noted.
27 | 1. Scope of Works | 9 | 1.35 | Mock ups | We do not currently have any mock-ups within our order | RCL to include mock up in the order, but not in the CSA at present. | Agreed
28 | 1. Scope of Works | 9 | 1.36 | Frames | We have not allowed for any temporary frames or permanent sub-frames (might be required to allow the plasterer to give the relevant lines) | The temporary frames part of temporary fire doors scope. Permanent sub-frames not included. AB to investigate the drylining plasterboard information.
29 | 1. Scope of Works | 9 | 1.38 | Scaffolding | We have not allowed for any scaffolding | Not required for the works at 21M. | Agreed
30 | 1. Scope of Works | 9 | 1.39 | Surveys | We have not allowed to carry out survey checks against site grid | RCL will install doors to the openings but will not check that the openings is in the correct location. | Agreed
31 | 1.3 & 1.4 Design Responsibilities / Duties | 11 |  | Design | Our design responsibilty is defined in section 1.5 (subject to the queries that we have raised) | Sue - to respond | Agreed as below
32 | 1.5 Design Statement | 12 | Paragraph 2 | Design | We do not agree that our design responsibilities described elsewhere in this section amount to a full CDP, please delete the phrase "delivering the full CDP Elements of this package of works, that is;" | Sue - to respond | Ok - omit the word 'full' and any reference to '3D' | Wording shall be ammended
33 | 1.5 Design Statement | 12 | Paragraph 3 | 1st sentence | The phrase "(General) (Discussion need for package specific items)" would appear not to be relevant, please delete it | Sue - to respond | Ok - omit
34 | 1.5 Design Statement | 12 | Paragraph 3 | Bullet point 2 | We have not allowed for 3D model information | Sue - to respond | Ok - omit the reference to provsion of 3D information | Wording shall be ammended
35 | 1.5 Design Statement | 13 |  | Bullet point 4 | It is the architects responsibilty to correctly enter the required fire and acoustic ratings on the door schedule | Sue - to respond | Agreed
36 | 2 Drawings and specifications list | 14 |  |  | If necessary we will comment upon this section under separate cover | RCL to check the documents for comments. | RCL to advise
37 | 3 Programme | 15 | 3.1 | Paragraph 5 | The only return visit allowed for as those that are identified within an agreed programme. | Programme issued to RCL, currently RCL are reviewing. | RCL to advise
38 | 3 Programme | 15 | 3.2 | Paragraph 1 | We have not received a programme | Programme issued to RCL, currently RCL are reviewing. | RCL to advise
39 | 4 Attendances | 17 | 4.3 | a | Please confirm what the "Package specific attendances" are | Omit this wording.
40 | 5 Sustainability requirements | 18 |  |  | We will comment upon this section under separate cover | Following on from the conversation between ST and Tom, RCL are to provide commentary on this from their suppliers. | RCL to advise
41 | 6 Price Basis | 35 | 6.2 | Skirtings | As we understand it the skirtings are now to be a lump sum | To be priced fixed price lump sum, until further notice. Re-change the wording to suit.
42 | 7 Price Basis | 35 | 6.3 | Defects Liability | Please amend the period to 12 months | RCL to review and action. | RCL to advise